Gas Gap Production Rate.

The press facilities consist at present in Korea University of 5 layers in 2 jigs.  Three are in regular use today as the other 2 require the use of 20 Pb blocks each.  Assuming a gap assembly cycle and bonding requires 1 day and all other operations are accomplished in parallel.

The gaps to be made for each chamber type are referred to as;

SC = Small cut gap		4 per layer

BC = Big cut gap		2 per layer

Bot = Bottom gap		1 per layer

They are for RE1/2,

40 SC + 40 BC + 40 Bot =  120 gaps.

Building Gaps sets:

Using the 3 layers of press in operation today that gives:

4 x 1 SC gaps

2 x 2 BC gaps		= 8 gaps/ day

1 x 3 Bot Gaps	= 3 gaps /day

SC gaps + BC gaps = 80 gaps  	>	10 days  of press work

Bot Gaps		40 gaps	>	14 days of press work

Toal required time for 40 full gap sets	> 	5 weeks

This is below the required rate but still rather satisfactory.

Ian Crotty

15 March 04

Gas Gap Production Rate.

More realistic

The press facilities consist at present in Korea University of 5 layers in 2 jigs.  Three are in regular use today as the other 2 require the use of 20 Pb blocks each.  Assuming a gap assembly cycle and bonding requires 1 day and all other operations are accomplished in parallel.

The gaps to be made for each chamber type are referred to as;

SC = Small cut gap		4 per layer

BC = Big cut gap		2 per layer

Bot = Bottom gap		1 per layer

They are for RE1/2,

40 SC + 40 BC + 40 Bot =  120 gaps.

Building Gaps sets:

However today work progresses in periods of 2 weeks.

Using the 3 layers of press in operation today that gives:

SC gaps + BC gaps		=  	40 gaps/week		> 	80 gaps / 2 weeks

Bot  Gaps			=	15 gaps / week 	>	30  gaps / 2 weeks

Total				 				>110 gaps / month

Ian Crotty

15 March 04

Gas Gap Production Rate.

In the beginning the Rate of Production

is estimated to be

The press facilities consist at present in Korea University of 5 layers in 2 jigs.  Three are in regular use today as the other 2 require the use of 20 Pb blocks each.  Assuming a gap assembly cycle and bonding requires 3 days  with all other operations accomplished in series.

The gaps to be made for each chamber type are referred to as;

SC = Small cut gap		4 per layer

BC = Big cut gap		2 per layer

Bot = Bottom gap		1 per layer

They are for RE1/2,

40 SC + 40 BC + 40 Bot =  120 gaps.

Building Gaps sets:

Using the 3 layers of press in operation today that gives:

Batches		weeks

4 x 3 SC/batch         	3.5			2

2 x 3 BC/batch	7			3.5

1 x 3 Bot/batch	14			7

Total							12.5 	=	3 months

Ian Crotty

15 March 04