## Sheet1
RE1/1 ONE Endcap
Copper Cables
Type | Quantity | Connector Ref. | Costs | Status | Connector Ref. | Costs | Status | Cable Ref. | Costs | Status | Remarks | Status
Nos
CSC Com. | 36 | AMP 1376245-1 abandoned |  | 12 weeks | AMP 1376245-1 abandoned |  | 12 weeks | 04.21.51.550.4 |  | 1.8km in ISR | USA funds | Waiting LBX slot
|  | 09.55.03.340.4, |  | 1800328 | 09.55.03.340.4, |  | 1800328 |  |  |  | AMP dropped
|  | 09.55.03.440.1 |  | 90%del. | 09.55.03.440.1 |  | 90%del.
LV LBB Power | 36 | undefined |  | NA | undefined |  | NA | 04.08.61.564.5 |  | 1.9km in ISR | Cut to length | Need L
LV LBX Sense | 36 | undefined |  | NA | undefined |  | NA | 04.21.70.104.6 |  | 2km in ISR | Cut to length | Need L
HV RPC | 36 | CPE |  | In ISR | CPE |  | In ISR | Novacavi |  | In ISR | Replace RB ordered | 70%
|  | 28.002.512_020 |  |  | 28.002.512_020 |  |  | P0825_03
Signal Cables | 288 | 09.55.03.340.4, |  | Ordered | 09.55.03.340.4, |  | Ordered | 04.71.06.400.0 |  | Tender in Process | Mount with RE1/1 | 9km in ISR
|  | 09.55.03.440.1 |  |  | 09.55.03.440.1
LV RPC | 18 | Molex |  | In ISR | Molex |  | In ISR | Novacavi |  | In ISR | 1 cable for 2 chambers | start week 9
|  | 43025 |  |  | 43025 |  |  | FMOH2M1
Temp Sensor |  | To be specified with RE1/1 |  | NA | To be specified with RE1/1 |  | NA | 04.21.51.055.4 |  | 2km in ISR |  | Need L
| Optical fibres |  |  | RE1/1 ONE Endcap
Type | Quantity | Connector Ref. |  | Status |  |  |  | Cable Ref. |  | Status | Remarks | Status
Nos
Trigger | [10 empty] | Warsaw | Sent
Spares
DCS | [10 empty] | Warsaw | ?
Spares
TTC | [10 empty] | Warsaw | Sent
Spares
RE1/2 ONE Endcap
Copper Cables
Type | Quantity cables | Connector Ref. | Costs Quant. | Status | Connector Ref. | Costs | Status | Cable Ref. | Costs | Status | Remarks | Status
CSC Com. | 36 | AMP 1376245-1 abandoned |  | 12 weeks | AMP 1376245-1 abandoned |  | 12 weeks | 04.21.51.550.4 |  | 1.8km in ISR | USA funds | Waiting LBX slot
|  | 09.55.03.340.4, |  | 1800328 | 09.55.03.340.4, |  | 1800328 |  |  |  | AMP dropped
|  | 09.55.03.440.1 |  | 90%del. | 09.55.03.440.1 |  | 90%del.
LV LBB Power | 36 | undefined |  | NA | undefined |  | NA | 04.08.61.564.5 |  | 1.9km in ISR | Cut to length | Need L
LV LBX Sense | 36 | undefined |  | NA | undefined |  | NA | 04.21.70.104.6 |  | 2km in ISR | Cut to length | Need L
HV RPC | 36 | CPE |  | In ISR | CPE |  | In ISR | Novacavi |  | In ISR | Replace RB ordered | 70%
|  | 28.002.512_020 | x36 |  | 28.002.512_020 | x36 |  | P0825_03
Signal Cables | 216 | 09.55.03.340.4, |  |  | 09.55.03.340.4, |  |  | 04.71.06.400.0 |  | Cable chosen | Mount with RE1/1 | <4km in ISR
|  | 09.55.03.440.1 |  |  | 09.55.03.440.1
LV RPC | 18 | Molex |  | In ISR | Molex |  | In ISR | Novacavi |  | In ISR | 1 cable for 2 chambers | start week 9
|  | 43025 |  |  | 43025 |  |  | FMOH2M1
Temp Sensor |  | To be specified with RE1/1 |  | NA | To be specified with RE1/1 |  | NA | 04.21.51.055.4 |  | 2km in ISR |  | Need L
RE1/3 ONE Endcap
Copper Cables
Type | Quantity | Connector Ref. | Costs | Status | Connector Ref. | Costs | Status | Cable Ref. | Costs | Status | Remarks | Status
Nos
CSC Com. | 36 | AMP 1376245-1 abandoned |  | 12 weeks | AMP 1376245-1 abandoned |  | 12 weeks | 04.21.51.550.4 |  | 1.8km in ISR | USA funds | Waiting LBX slot
|  | 09.55.03.340.4, |  | 1800328 | 09.55.03.340.4, |  | 1800328 |  |  |  | AMP dropped
|  | 09.55.03.440.1 |  | 90%del. | 09.55.03.440.1 |  | 90%del.
LV LBB Power | 36 | undefined |  | NA | undefined |  | NA | 04.08.61.564.5 |  | 1.9km in ISR | Cut to length | Need L
LV LBX Sense | 36 | undefined |  | NA | undefined |  | NA | 04.21.70.104.6 |  | 2km in ISR | Cut to length | Need L
HV RPC | 36 | CPE |  | In ISR | CPE |  | In ISR | Novacavi |  | In ISR | Replace RB ordered | 70%
|  | 28.002.512_020 |  |  | 28.002.512_020 |  |  | P0825_03
Signal Cables | 288 | 09.55.03.340.4, |  | Ordered | 09.55.03.340.4, |  | Ordered | 04.71.06.400.0 |  | Tender in Process | Mount with RE1/1 | 7km in ISR
|  | 09.55.03.440.1 |  |  | 09.55.03.440.1
LV RPC | 18 | Molex |  | In ISR | Molex |  | In ISR | Novacavi |  | In ISR | 1 cable for 2 chambers | start week 9
|  | 43025 |  |  | 43025 |  |  | FMOH2M1
Temp Sensor |  | To be specified with RE1/1 |  | NA | To be specified with RE1/1 |  | NA | 04.21.51.055.4 |  | 2km in ISR |  | Need L