## Slide 1: New Detectors: Services, Integration and Installation Plan in CMS
Andrey Marinov
On behalf of the CMS Muon Collaboration

## Slide 2
GE2/1:
ME0:
2
Forward muon system upgrade overview
Trigger and reconstruction
1.55 < |η| < 2.45
18 staggered SC per endcap, each chamber covers 20°
2 layers of GEM-like technology
Muon tagger at highest η
each chamber spans 20°
6 layers of GEM-like technology
Trigger and reconstruction
1.8 < |η| < 2.4
18 chambers per endcap, each chamber spans 20°
1 layer (per station) RPC-like technology
RE 3/1 –RE4/1 :

## Slide 3: GE2/1 Envelope

## Slide 4: GE2/1 Services
GE2/1 will be mounted on the back of YE1, station 2. It will be installed layer by layer in order to form the super-chamber configuration
Thus all the services should be installed on YE1 to secure minimum length, and avoid the usage of the YE1-YE2 mini cable chains. LS2 is the best moment for the GE2/1 services installation
Services | Per GE2/1 Single Chamber
LV | 5V, ~15A – Based on the usage of the FEAST DCDC converters
HV | 32 channels. Divided by 4 groups of 8. Maximum potential is -4kV on the drift electrodes.
Fibers | 26 to USC plus 8 to SCS ME2/1 TMB
Gas | ArCO2 70-30% with flow 1l/h
Cooling | Water of 18C with speed of 2l/min, Δt of GE2/1 is ~2C

## Slide 5: GE2/1 Single Chamber Services
24 VFAT3
18 VFAT3
18 VFAT3
OH
OH
OH
OH
12 VFAT3
HV Multi-conductor cable
LV Cable from the PS to FEAST DCDC
26 Fibers in total to USC
12 for Tracking
8 for Trigger
8 Fibers to ME2/1 TMB
Gas (Supply Return)
Cooling (Supply Return)
Optohybrid (OH) board will be specially design for GE2/1 modules. Less bandwidth and VFATs per OH compare with the GE1/1.

## Slide 6: HV System for GE2/1
The HV power system will be based on CAEN A1515
In total we need 5 mainframes per endcap in USC S2 level (one rack per endcap).
72 HV multiconductor cables per endcap. Each with 16 HV channels inside
All must go via the YE1’s main cable chains
It is the same HV power supply as GE1/1.
Long term maintenance will be secured by CAEN-CERN contract.
DCS software will be identical as GE1/1.
USC
UXC

## Slide 7: LV System for GE2/1
Less LV channels per detector
Smaller cross-section of power cables
Less power dissipation inside the detector
The CERN FEASTMP DCDC converter will be integrated on the GEB boards to provide LV power for the on detector electronics – VFATs and OHs for each GE2/1 module
FEASTMP DCDC modules are developed at CERN to meet the LHC requirements
SY4527

## Slide 8: UXC Rack Space Budget for the GE2/1 LV per Endcap
EASY3000
A3486S
EASY3000
3U
6U
6U
A3016
A3016
A3016
A3016
A3016
EASY3000 with 5x A3016
30 LV channels, each module has 6 channels up to 90W per ch.
EASY3000
A3486S
EASY3000
3U
6U
6U
12x A3016
4 EASY3000 crates
2x A3486S dual AC/DC converters
Total U space is 30 per endcap
Plus Ventilation U

## Slide 9: GE2/1 Fibers
YE-1
YE-2
GE2/1s
Mini Cable-Chain (Caterpillar)
Mini Cable-Chain (Caterpillar)
YE+1
YE+2
In addition there are 18x16 (288) fibers from GE2/1 (YE1) to the ME2/1 TMB(YE2). The length is between 30 and 50m and must go through the mini cable chains YE1 YE2.
ME2/1
936 fibers per endcap to USC
8x40mm duct to USC S2 per endcap
To patch them we need 40U rack space in UXC (Balcony) and 40U in USC S2 level

## Slide 10: GE2/1 Gas System
During LS2 we have to install all the gas pipes.
3 GE2/1 super-chambers connected in serial from the 12 available flow cells
We can use the same gas distribution pattern as GE1/1
GE2/1 distribution rack
Ar-CO2 70-30%
As baseline

## Slide 11: GE2/1 Cooling
New Cooling pipes should be placed between the RE2s the YE1 yoke. They should run from the GE2/1 patch panels to the cooling manifolds of the YE1
 | Per GE2/1 Super-Chamber
VFAT3 | 74.88W
OH | 120W
DCDC converters | 160W
 | 354.88W
Per Disk, On detector electronics 6387.84W
Power in the USC Racks per disk 3577W
Total Power per disk 9964 W

## Slide 12: Proposed Alignment of GE2/1 Chambers
Two-fold chamber alignment (same as in GE1/1 and ME0):
Precisely align the Readout boards in the superchamber
  Measure the strips of the Readout Boards within the frame of the chamber (defined by this step)
  Locate the inter-chamber alignment sensors (technology is the same, ie Fiber Bragg Grating-based (FBG) displacement sensor that is being developped for the GE1/1)
  Locate the survey target holders within this frame in order to be able to relate the two chambers in the superchamber and to be able to perform survey measurement after installation
By the observation of the FBG displacement sensor data the mutual positions (and orientations) of the (super)chambers in the GEM disk can be reconstructed  rigid disk that can either be localised by few tracks (this allows indirect tests of the track-based alignment of the disk chambers), and the disk itself can be localised within the Barrel Alignment frame with the redesigned EndCap alignment components:

## Slide 13: Proposed Localization of GE2/1 in Barrel System
Existing EndCap Ali laser lines are going to be blocked by GE2/1  redesign needed!
EndCap Ali laser lines
Shielding
GE1/1 chambers
TrPlate1
TrPlate6
TrPlate5
TrPlate4
TrPlate3
TrPlate2
Instead of the crossing laser lines a ‘target observing’ method is proposed. It works well in the Barrel Alignment. However instead of LEDs a high refraction index (n=2) reflective targets are to be used (good results in ISOLDE).
Frame
Glass sphere (precisely known positions!)
Transfer lines
GE2/1
MAB-ring +3
MAB-ring +1
MAB-ring -1
MAB-ring -3
These radial lines can be connected with the existing “transfer Lines” connecting the two endcaps through the Barrel Alignment System
Locate the rigid GEM disk within the Barrel frame of reference to allow studies of the tracking systematics/weak modes between the Barrel and the Endcaps
Final Aim:

## Slide 14: GE2/1 LS2 Schedule YE+1
We start On week 16 (end of March 2019) with the installation of the GE2/1 Pipes Gas, Cooling. Time allocated for this is 2 weeks.

## Slide 15: GE2/1 LS2 Schedule YE-1
We start On week 25 (beginning of May2019) with the installation of the GE2/1 Pipes Gas, Cooling. Time allocated for this is 2 weeks.

## Slide 16: GE2/1 Schedule Proposal
The LS3 period will be mainly focused on the YE1 noses and the Barrel part of the CMS. Access to YE1 station 2 will not be in the priorities.
It is under discussion with the CMS Technical Coordinators to anticipate the GE2/1 Services installation during LS2 and to install the detectors on YETS2021/22 and YETS2022/23

## Slide 17: ME0

## Slide 18: ME0

## Slide 19: ME0
Structure of 6 layer detector.
Electronics Volume
DC/DC converter and OHs
Services path
225mm
1860mm
1350.47mm
568mm

## Slide 20: ME0 Services Envelope
6 LV cables, 6x ~10mm dia.
96 fibers for Data – 4 patch cords of 24 fibers = 4x ~12mm
HV cable 3x ~10mm
Gas pipes – Supply and Return – 2 x 6mm
Cooling pipes – 2x 10mm
BH
BH
Side view
BH

## Slide 21: ME0 Services and integration
View from IP
HGC and ME0 will be mounted in Prevessin B904 before installing in CMS.
Commissioning will be done in bd904 after insertion in HGC.
BD904
HGC

## Slide 22
ME0 production, commissioning and installation in LS3

## Slide 23: RE3/1 and 4/1 Envelopes
Dimensions are being established with the CMS Integration Office

## Slide 24: RE3/1 and RE4/1 Geometry
RE4/1
A mock-up will be tested in situ for mounting and service study during EYETS2016/17
1244mm
1717mm
638mm
RE3/1

## Slide 25
RE3/1 and RE4/1 single chamber services
+
1 Optical Link
Data Concentrator Card
18 OL
2 OL
1 OL for data
1 OL for trigger
1 HV cable
1 LV cable
1 GBT optical link per chamber to transmit data to one data concentrator card per station
Data Concentrator Card: One card, common for one disk of 18 chambers
2 gas lines per 60° sector
12 gas flow cells per rack
Cooling (supply/return)
Gas Up layer (supply/return)
UXC
USC
Gas Down layer (supply/return)

## Slide 26
RPC Gas Rack
Mini Cable Chains for HV
RE3 and RE4 Services on YE3
DCC
Mini Cable Chains for HV
LV crates
LV Easy crates
Near Side
Far Side

## Slide 27: HV System for RE3/1 and RE4/1
The HV power system will be based on CAEN EASY system:
SY4527 – 1 (using the existing endcap main frame)
A3485S - 2 modules
A3512N – 6 boards
4 HV multiconductor cables per endcap. Each with 20 HV channels
All must go via the YE1’s main cable chains
Long term maintenance will be secured by CAEN-CERN contract.
DCS software to be integrated in the RPC DCS.
USC
UXC
A3485S
A3512N

## Slide 28
2 A3016 LV boards per tower to power the RE3/1 and RE4/1 chambers.
6U for tower
LV System for RE3/1 and RE4/1
SY4527 with A1676A
USC
UXC
EASY3000
with A3016
A3486S
48V Service power
50p Communication bus

## Slide 29: RE3/1 and RE4/1 Gas and Cooling
Distribution rack for RE3/1 and RE4/1
RE3/1 & RE4/1 Gas mixture
C2H2F4 95.2%
iso-C4H10 4.5%
SF6 0.3%
40% humidification
Per Chamber | Per Disk | Power in the UXC Racks per disk | Total Power per Disk
53W | 1.9kW | 1.6kW | 3.6kW
We will use the present CMS RPC gas mixture . Installation of gas pipes to be made on the disk surface.
Cooling estimates
C2H2F4
C4H10
SF6
95.2
4.5
0.3

## Slide 30: RE3/1 and RE4/1 Schedule
Services Installation during LS2
Ready for installation Endcap2
Ready for installation Endcap1

## Slide 31
Sub-system | Power System Component | Total Quantity | Length/Diam. [m/mm] | Service Installation Duration | Installation LS2 Period
RPC | HV Umbilical cables | 8 | ~90/40 | 2 weeks per end | RE+: W16-17 RE-: W47-48
RPC | Gas copper pipes | 4 | ~110/12 | 1 week per end | RE+: W17 RE-: W48
GE2/1 | HV | 72 | ~100/10 | 1 week per end | GE+2/1: W16 GE-2/1: W25
GE2/1 | Optical Fibres | 1872 | ~80/40 | 2 weeks per end | GE+2/1: W16 GE-2/1: W25
GE2/1 | DCS, Alignment, Tempar | 8 | ~100/10 | 1 week per end | GE+2/1: W16 GE-2/1: W25
GE2/1 | Gas | 4 | ~110/12 | 2 weeks per end | GE+2/1: W16 GE-2/1: W25
USC – UXC new station services summary

## Slide 32
Sub-system | Power System Component | Total Quantity | Length/Diam. [m/mm] | Service Installation Duration | Installation LS2 Period
RPC | HV power cables | 72 | ~30/6 | 2 weeks per end | RE+: W18-19 RE-: W49-50
RPC | LV power cables | 72 | ~15/10 | 1 week per station & end | RE+3/1: W51 RE+4/1: W57 RE-3/1: W38 RE-4/1: W44
RPC | DCS cables | 72 | ~15/5 |  | 
RPC | LVDS signal cables | 1440 | ~15/10 |  | 
RPC | Supply Gas copper pipes | 24 | ~20/6 | 1 week per station & end | RE+3/1: W50 RE+4/1: W39-40 RE-3/1: W37 RE-4/1: W20-21
RPC | Return Gas copper pipes | 24 | ~20/8 |  | 
RPC | Cooling | 36 |  |  | 
RPC UXC Services

## Slide 33: GE2/1 UXC Services
Services | GE2/1 Chamber | GE2/1 Super-Chamber | Per Endcap | Installation LS2 Period
HV | 1 cable of 32 conductors inside | 2 cables | 36 cables | GE+2/1: W16 GE-2/1: W25
LV Up to the Periphery of the YE1 | 1 cable of 4 conductors inside | 2 | 36 | GE+2/1: W16 GE-2/1: W25
Fibers to UXC pp – toward USC S2 | 26 | 52 | 936 | GE+2/1: W16 GE-2/1: W25
Fibers to ME2/1 TMB. Vie the miniCC | 8 | 16 | 288 | GE+2/1: W16 GE-2/1: W25
Gas Daisy chain with 3 chambers | 2 | 4 | 24 pipes 12 supply and 12 return Copper pipes 8 mm external diameter | GE+2/1: W16 GE-2/1: W25
Cooling | - | 2 | 36 pipes | GE+2/1: W16 GE-2/1: W25

## Slide 34: Conclusion
The services needed for the new stations are defined.
Services will be installed before and during LS2
Chambers will be installed during YETS before LS3.

## Slide 35: Thank You