## Slide 1: Draft LS2 Draft Schedule
Goal: Collect all work objectives

## Slide 2
Assumptions
  5 working days/week
  Bank holidays / Lab closure not included
  Shift work possible when required
  Current levels of expertise maintained
  Using proven existing tooling
Design Method

## Slide 3
Infrastructure:
UXC55 2nd crane (beginning of shutdown – 4w) - EN-HE
  PM54 Lift (should start mid May 2017 till 21st July)
Refurbish magnet control system
Modify SCX5 Ctrl room by beginning of LS2 – CMS/GS
Build Multipurpose SX5 extension – CMS/GS
Add UPS for the DAQ computer farm – EN-EL
Move SCX5 UPS out of ctrl room to dedicated UPS building – EN-EL
Add 1.5 MW cooling capacity to the chilled water system –EN-CV
Refurbish SUX5 control infrastructure for chilled/mixed water production – EN-CV
Refurbish USC55 control infrastructure for all water distribution system – EN-CV
Consolidate instrument air infrastructure in SH5 – EN-CV
Refurbish underground ventilation control system– EN-CV
Test RP shielding in battle condition (before taking BP out)
Key objectives

## Slide 4
Work on End Caps:
HE - Carry out phase1 upgrade of Front-End electronics, i.e. replacement of HPD->SiPMs
  Carry out sourcing program for HB (to define if we need to refurbish HB during LS3) & HE (2016-17 for HE & 2015-16 for HF): compulsory as cables will have been disconnected
Switch EC HF CT2 FWD Beam Pipes to Al2219 – (no CASTOR operation after LS2)Option to move to higher eta. The double bellow will be dealt with during LS3
Remove T1 & T2 for good
Install GE1/1 (including pipes + cables – remove “slice test” detector installed in 2016)
  2 teams, one on each side; SL and CP needed; UXC55 crane + jig needed for top sectors (30kg/Schamber)
  Installation rate: 2 Super chambers per day (36 total per end) – tbc by slice tests during YETS16-17
  Installation rate for services: 2 weeks per ECap
Reinforce polythene shielding (depends on thickness) – 1 shell taken as one single piece
Refurbish ME2/1, ME3/1, ME4/1? (duration? After new crane installed) – trigger latency boards
  Take away all MEx/1chambers to SX5 (2CPs)
  7 working days per gap (e.g. YE+1/2) to disconnect and remove the chambers
  15 working days per gap to re-install and commission the chambers
  60 working days per end for refurbishment
  Could the available area in the SX5 gas detector area be extended? 2m towards the PX56
  Input collected from A Lanaro and D Morse on 02.03.2016
Repair DT minicrates (4w per Barrel gap + 2w at EC-B interface)
  tbc: Install shielding on top sectors of YBs (crane)
Key objectives

## Slide 5
Work on Barrels:
Fix RPC leaks in barrel region (tackle worse chambers first)
Repair 40% of YBs mini-crates using cherry pickers in all barrel gaps
Options / activities to be further defined:
High luminosity related tasks
Change HE Mega-Tiles
Key objectives

## Slide 6: Week 1
SL
CP
TX54
End of Heavy Ion Run
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Install 2nd UXC55 crane
W1/4
CMS beam pipe at Atm pressure
Start of Visits in UXC55
6. Inject Ne
2. Open VAC shielding
5. Prepare GIS
3. EN-HE: Restart Crane 1
Open TX54
4. Open PX56 Plug
Full RP sweep

## Slide 7: Week 2
SL
CP
TX54
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Install 2nd UXC55 crane
W2/4

## Slide 8: Week 3
SL
CP
TX54
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Install 2nd UXC55 crane
W3/4

## Slide 9: Week 4
SL
CP
TX54
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Install 2nd UXC55 crane
W4/4
1. Install collar switchboards
2. Lower 4 CPs + 2SL

## Slide 10: Week 5
SL
CP
Remove shims between collar and RS-Z
B. Open RS-Z
2. Remove shims between collar and RS+Z
3. Open RS+Z
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP

## Slide 11: Week 5
SL
CP
1. Move HF+Z away from IP
2. Disconnect T1 services
3. Open HF+
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP

## Slide 12: Week 5
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
2. Remove beam pipe support at 13.5m
3. Remove access gangway to HF+Z
5. EN-HE – Remove HF+ I beams
4. Remove HF+Z towers reinforcement
1. Open T2 & BSC

## Slide 13: Week 5
SL
CP
Lower HF+ on 2 risers
2. EN-HE – lift up 2 risers
A. Move HF-Z away from IP
3. Install HF access staircase
B. Open HF- + platform flooring
C. Open T2 & BSC
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP

## Slide 14: Week 6
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
1. Install tooling for extension beam
2. Install extension beam on FIN
3. Perform load transfer @ 13.6m
A. Remove BP support @ 13.5m
B. Remove access gangway to HF-Z
EN-HE – Remove HF- I beams
Remove HF-Z towers reinforcement

## Slide 15: W6
SL
CP
Extract T1+Z
RE
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Lower HF-Z on 2 risers
B. EN-HE – lift up 2 risers
2. EN-HE – lift up T1+ to SX5

## Slide 16: W6
SL
CP
RE
Extract T1+Z
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
3. Perform load transfer on Ext beam
4. EN-HE – Remove FIN Plug
Remove CT2-FWD bellow + FWD+Z module
Install tooling for extension beam
2. Install extension beam on FIN
0. EN-HE – Remove FIN Plug

## Slide 17: W6
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Extract T1-Z
RE
2. EN-HE – lift up T1- to SX5
Remove CT2-FWD bellow + FWD+Z module

## Slide 18: W6
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RE
1. Remove CT2-FWD bellow + FWD+Z module

## Slide 19: W7
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RE
Remove CT2-FWD bellow + FWD-Z module

## Slide 20: W7
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Lower HF to floor
2. EN-HE – lift up 2 risers
2. Remove Collars
3. Install HF Pb doors

## Slide 21: W7
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RE
RE
Lower HF to floor
2. EN-HE – lift up 2 risers
3. Remove Collars
4. Install HF Pb doors
Move HF+ in garage

## Slide 22: W7
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RE
RE
1. Install YE traction system
0. Remove BP support at 10.6m
Before opening EC

## Slide 23: W8
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RE
RE
Open YE-1/2/3/4 – 1w

## Slide 24: W9
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Open YE+1/2/3/4 – 1w

## Slide 25: W10
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
1. Install 20t Platform + supports
2. Install handrails for platform
3. Install BP support at 10.6m
A. Install 20t Platform + supports
B. Install handrails for platform
C. Install BP support at 10.6m
4. Install PIX platform+ Bosch rails
5. Install PIX scissor table
D. Install PIX platform+ Bosch rails
E. Install PIX scissor table
F. Survey BP
6. Survey BP

## Slide 26: W11
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
1. Release horizontal wire at 3.2m
2. Modify BP support for PIX extraction
3. Disconnect FPIX+Z
4. Extract FPIX+Z
Gino D1/2 WP:
5. Lift up FPIX+Z to SHL5
Eric 1h WP:
6. Extract FPIX-Z
7. Lift up FPIX-Z to SHL5

## Slide 27: W12
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
3. Install BP Bosch rails
4. Disconnect HF/CT2 pipe + slide outwards
1. Disconnect BPIX-/+Z
2. Extract 2 half shells BPIX from –Z end

## Slide 28: W13
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
1. Disconnect & Remove EndCap-Z pipe
2. Remove HF/CT2-Z pipe
3. Disconnect HF/CT2+Z pipe + Slide outwards

## Slide 29: W14
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
1. Disconnect & Remove EndCap+Z pipe
2. Remove HF/CT2+Z pipe

## Slide 30: W15
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Remove 20t platforms
Remove 20t platforms
Remove Central BP
2d

## Slide 31: W16
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Open YB-2
DT
Move YE-1
Remove GE1/1 slice test detector
Repair DT MiniCrates
YB-2-1 w1/4
Install RE HV umbilical cables NEAR

## Slide 32: W17
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
Open YB-2
DT
Install GE+1/1 super-chambers
2/day W1/4
GEM
Disconnect ME-2/1services
3d
CSC
Remove 18 ME-2/1 chambers
2d 2/4d
Repair DT MiniCrates
YB-2-1 w2/4
Install RE HV umbilical cables FAR
Install RE gas pipes in CC FAR

## Slide 33: W18
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
DT
Install GE+1/1 super-chambers
2/day W2/4
GEM
CSC
Remove 18 ME-2/1 chambers
2d 4/4d
Move YE-2
1d
Disconnect ME-3/1services
2d 2/3d
Time to ME-x/1 refurbishment complete | 12w
Repair DT MiniCrates
YB-2-1 w3/4
Install RE+3/1 HV cables FAR
Install RE+3/1 HV cables NEAR

## Slide 34: W19
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
DT
Install GE+1/1 super-chambers
2/day W3/4
GEM
CSC
Disconnect ME-3/1services
1d 3/3d
Remove 18 ME-3/1 chambers
4d 4/4d
Time to ME-x/1 refurbishment complete | 11w
Repair DT MiniCrates
YB-2-1 w4/4
Install RE+4/1 HV cables FAR
Install RE+4/1 HV cables NEAR

## Slide 35: W20
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
Install GE+1/1 super-chambers
2/day W4/4
GEM
RPC
Move YE-3/4 (YE4 anchored?)
1d
Time to ME-x/1 refurbishment complete | 10w
DT
Move YB-1
1d
Repair DT MiniCrates
YB-1-0 w1/4
Remove 36 RE4 chambers
4d d4/5
Install Cu gas pipes for RE-4/1
5d/10d

## Slide 36: W21
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
Install GE+1/1 services
W1/3
GEM
CSC
Time to ME-x/1 refurbishment complete | 9w
Disconnect ME-4/1services
3d 3/3d
Remove 18 ME-4/1 chambers
1d 1/4d
Remove 36 RE4 chambers
1d d5/5
DT
Repair DT MiniCrates
YB-1-0 w2/4
Install Cu gas pipes for RE-4/1
10d/10d

## Slide 37: W22
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
GEM
Install GE+1/1 services
W2/3
GEM
CSC
Remove 18 ME-4/1 chambers
3d 4/4d
Time to ME-x/1 refurbishment complete | 8w
DT
RP
Repair DT MiniCrates
YB-1-0 w3/4

## Slide 38: W23
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
GEM
Time to ME-x/1 refurbishment complete | 7w
Move YE-3/4, 2
2d
DT
Repair DT MiniCrates
YB-1-0 w4/4
Move YB+2

## Slide 39: W24
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
Install GE+1/1 services
W3/3
GEM
Time to ME-x/1 refurbishment complete | 6w
DT
Move YB-2-1
Repair DT MiniCrates
YB+2+1 w1/4

## Slide 40: W25
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
Commission GE+1/1
W1/4
GEM
Time to ME-x/1 refurbishment complete | 5w
GEM
GEM
Install GE-1/1 super-chambers
2/day W1/4
DT
Repair DT MiniCrates
YB+2+1 w2/4

## Slide 41: W26
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
Commission GE+1/1
W2/4
GEM
Time to ME-x/1 refurbishment complete | 4w
GEM
GEM
DT
Install GE-1/1 super-chambers
2/day W2/4
Repair DT MiniCrates
YB+2+1 w3/4

## Slide 42: W27
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
Commission GE+1/1
W3/4
GEM
Time to ME-x/1 refurbishment complete | 3w
GEM
GEM
DT
Install GE-1/1 super-chambers
2/day W3/4
Repair DT MiniCrates
YB+2+1 w4/4

## Slide 43: W28
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
GEM
Commission GE+1/1
W4/4
GEM
Time to ME-x/1 refurbishment complete | 2w
GEM
GEM
DT
Install GE-1/1 super-chambers
2/day W4/4
Repair DT MiniCrates
YB+1+0 w1/4
Move YB+1

## Slide 44: W29
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Time to ME-x/1 refurbishment complete | 1w
GEM
GEM
Install GE-1/1 services
W1/3
DT
Repair DT MiniCrates
YB+1+0 w2/4

## Slide 45: W30
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Time to ME-x/1 refurbishment complete | 0w
Install GE-1/1 services
W2/3
GEM
GEM
DT
Move YE+1
Repair DT MiniCrates
YB+1+0 w3/4

## Slide 46: W31
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Install 9 Back ME-2/1 chambers
2d
GEM
GEM
Connect 9 Back ME-2/1 chambers
2d
DT
CSC
Disconnect services and cables for ME+2/1
1d d1/3
Repair DT MiniCrates
YB+1+0 w4/4
Install GE-1/1 services
W3/3
Perform connectivity tests on Back ME-2/1 chambers
1d d1/2

## Slide 47: W32
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
GEM
GEM
CSC
Move YB+1, +2
Commission GE-1/1
W1/4
Perform connectivity tests on Back ME-2/1 chambers
1d d2/2
Install 9 Front ME-2/1 chambers
2d
Connect cables on 9 Front ME-2/1 chambers
2d d2/2
Disconnect services and cables for ME+2/1
1d d2/3

## Slide 48: W33
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
GEM
GEM
CSC
DT
Repair DT MiniCrates
YB+1 w1/2
Commission GE-1/1
W2/4
Perform connectivity tests on Front ME-2/1 chambers
2d d2/2
Connect services on 18 ME-2/1 chambers
2d d2/2
Disconnect services and cables for ME+2/1
1d d3/3

## Slide 49: W34
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
GEM
GEM
Move YE-2
1d
Remove 18 ME+2/1 Chambers
3d d3/4
CSC
DT
Repair DT MiniCrates
YB+1 w2/2
Commission GE-1/1
W3/4
Carry out leak tests on ME-2/1 chambers
3d

## Slide 50: W35
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
GEM
GEM
Install 9 Back ME-3/1 chambers
2d
Connect 9 Back ME-3/1 chambers
2d
Carry out full commissioning tests on ME-2/1 chambers
3d Gas and cooling required
Remove 18 ME+2/1 Chambers
1d d4/4
CSC
Time to ME+x/1 refurbishment complete | 12w
Commission GE-1/1
W4/4
Perform connectivity tests on Back ME-3/1 chambers
1d d1/2

## Slide 51: W36
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Perform connectivity tests on Back ME-3/1 chambers
1d d2/2
Install 9 Front ME-3/1 chambers
2d
Connect cables on 9 Front ME-3/1 chambers
2d d2/2
Move YE+3
1d
CSC
Time to ME+x/1 refurbishment complete | 11w

## Slide 52: W37
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Perform connectivity tests on Front ME-3/1 chambers
2d d2/2
Connect services on 18 ME-3/1 chambers
2d d2/2
CSC
Disconnect services and cables for ME+3/1
2d d2/3
Time to ME+x/1 refurbishment complete | 10w
Install RE-3/1 Cu gas pipes

## Slide 53: W38
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Move YE-3
1d
Carry out leak tests on ME-3/1 chambers
3d
Time to ME+x/1 refurbishment complete | 9w
CSC
Disconnect services and cables for ME+3/1
1d d3/3
Remove 18 ME+3/1 chambers
4d
Install RE-3/1 LV & signal cables
4d

## Slide 54: W39
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Install 9 Back ME-4/1 chambers
2d
Connect cables on 9 Back ME-4/1 chambers
2d
Perform connectivity tests on Back ME-4/1 chambers
1d d1/2
Carry out full commissioning tests on ME-3/1 chambers
3d
Time to ME+x/1 refurbishment complete | 8w
RPC
Move YE+3/4 (YE4 anchored?)
1d
Remove 36 RE+4 chambers
4d D4/5
Install Cu gas pipes for RE+4/1
5/10d

## Slide 55: W40
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Perform connectivity tests on Back ME-4/1 chambers
1d d2/2
Install 9 Front ME-4/1 chambers
2d
Connect cables on 9 Front ME-4/1 chambers
2d d2/2
Time to ME+x/1 refurbishment complete | 7w
CSC
Remove 36 RE+4 chambers
1d d5/5
Install Cu gas pipes for RE+4/1
10d/10d

## Slide 56: W41
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Perform connectivity tests on Front ME-4/1 chambers
2d d2/2
Connect services on 18 ME-4/1 chambers
2d d2/2
Time to ME+x/1 refurbishment complete | 6w
CSC
Disconnect services and cables for ME+4/1
2d d2/3

## Slide 57: W42
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Carry out leak tests on ME-4/1 chambers
3d
Carry out full commissioning tests on ME-4/1 chambers
2d d2/3
Time to ME+x/1 refurbishment complete | 5w
CSC
Disconnect services and cables for ME+4/1
1d d3/3
Remove 18 ME+4/1 chambers
4d

## Slide 58: W43
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RPC
Install 36 RE-4/2 4/3 chambers
Time to ME+x/1 refurbishment complete | 4w
Move YE+3,2
2d

## Slide 59: W44
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RPC
Commission 36 RE-4/2 4/3 chambers
Time to ME+x/1 refurbishment complete | 3w
Install 9 Back ME+2/1 chambers
2d
Connect 9 Back ME+2/1 chambers
2d
Perform connectivity tests on Back ME+2/1 chambers
1d d1/2
CSC
Install RE+4/1 LV & signal cables

## Slide 60: W45
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RPC
Commission 36 RE-4 chambers
Time to ME+x/1 refurbishment complete | 2w
Install 9 Front ME+2/1 chambers
2d
Perform connectivity tests on Back ME+2/1 chambers
1d d2/2
Connect cables on 9 Front ME+2/1 chambers
2d d2/2
CSC

## Slide 61: W46
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RPC
Commission 36 RE-4 chambers
Time to ME+x/1 refurbishment complete | 1w
Perform connectivity tests on Front ME+2/1 chambers
2d d2/2
Connect services on 18 ME+2/1 chambers
2d d2/2
CSC

## Slide 62: W47
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Time to ME+x/1 refurbishment complete | 0w
CSC
Move YE+2
1d
Carry out leak tests on ME+2/1 chambers
3d
DT
Repair DT MiniCrates
YB-1 w1/2
Install RE HV umbilical cables NEAR

## Slide 63: W48
DT
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Install 9 Back ME+3/1 chambers
2d
Connect 9 Back ME+3/1 chambers
2d
Carry out full commissioning tests on ME+2/1 chambers
3d
Perform connectivity tests on Back ME+3/1 chambers
1d d1/2
Repair DT MiniCrates
YB-1 w2/2
Install RE HV umbilical cables FAR
Install RE gas pipes in CC FAR

## Slide 64: W49
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Perform connectivity tests on Back ME+3/1 chambers
1d d2/2
Install 9 Front ME+3/1 chambers
2d
Connect cables on 9 Front ME+3/1 chambers
2d d2/2
Install RE-3/1 HV cables FAR
Install RE-3/1 HV cables NEAR

## Slide 65: W50
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Perform connectivity tests on Front ME+3/1 chambers
2d d2/2
Connect services on 18 ME+3/1 chambers
2d d2/2
Install RE-4/1 HV cables FAR
Install RE-4/1 HV cables NEAR
Install RE+3/1 Cu gas pipes

## Slide 66: W51
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Move YE+3
1d
Carry out leak tests on ME+3/1 chambers
3d
Install RE+3/1 LV & signal cables
4d

## Slide 67: W52
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Install 9 Back ME+4/1 chambers
2d
Connect cables on 9 Back ME+4/1 chambers
2d
Perform connectivity tests on Back ME+4/1 chambers
1d d1/2
Carry out full commissioning tests on ME+3/1 chambers
3d

## Slide 68: W53
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Perform connectivity tests on Back ME+4/1 chambers
1d d2/2
Install 9 Front ME+4/1 chambers
2d
Connect cables on 9 Front ME+4/1 chambers
2d d2/2

## Slide 69: W54
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Perform connectivity tests on Front ME+4/1 chambers
2d d2/2
Connect services on 18 ME+4/1 chambers
2d d2/2

## Slide 70: W55
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CSC
Carry out leak tests on ME+4/1 chambers
3d
Carry out full commissioning tests on ME+4/1 chambers
2d d2/3

## Slide 71: W56
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RPC
Install 36 RE+4/2 4/3 chambers

## Slide 72: W57
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
RPC
Commission 36 RE+4/2 4/3 chambers
Install RE+4/1 LV & signal cables

## Slide 73: Another example of potential configuration for CSC work
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
YE4 as shield against FIN

## Slide 74
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Configure CMS for BP re-installation
Ready for Beam – 29Ws

## Slide 75
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install Beam Pipe W1/6
Ready for Beam – 28Ws

## Slide 76
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install Beam Pipe W2/6
Ready for Beam – 27Ws

## Slide 77
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install Beam Pipe W3/6
Ready for Beam – 26Ws

## Slide 78
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install Beam Pipe W4/6
Ready for Beam – 25Ws

## Slide 79
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install Beam Pipe W5/6
Install BP bake out jackets -Z
Ready for Beam – 24Ws

## Slide 80
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install Beam Pipe W6/6
Remove 20t platform
Ready for Beam – 23Ws

## Slide 81
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Install bake out jackets and racks
Move –Z EndCap in BO position
Install BO scaffolding
Install YB0 gangway
Remove 20t platform
Ready for Beam – 22Ws

## Slide 82
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Prepare BO operations
Install FWD BP
Move +Z EndCap in BO position
Install BO scaffolding
Install YB0 gangway
Ready for Beam – 21Ws

## Slide 83
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Install FWD BP
Prepare BO operations
Install Bake Out jackets + cables
Ready for Beam – 20Ws

## Slide 84
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Bake Out CMS beam Pipe W1/3
Ready for Beam – 19Ws

## Slide 85
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Bake Out CMS beam Pipe W2/3
Ready for Beam – 18Ws

## Slide 86
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Bake Out CMS beam Pipe W3/3
Ready for Beam – 17Ws

## Slide 87
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Remove YB0- access gangway
Remove –Z Surkov frame
Open –Z EC
Ready for Beam – 16Ws

## Slide 88
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Remove YB0- access gangway
Remove –Z Surkov frame
Open +Z EC
Ready for Beam – 15Ws

## Slide 89
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Install 20t platforms
Ready for Beam – 14Ws

## Slide 90
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install PIX/BCM W1/6
Ready for Beam – 13Ws

## Slide 91
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install PIX/BCM W2/6
Ready for Beam – 12Ws

## Slide 92
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install PIX/BCM W3/6
Ready for Beam – 11Ws

## Slide 93
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install PIX/BCM W4/6
Ready for Beam – 10Ws

## Slide 94
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install PIX/BCM W5/6
Ready for Beam – 9Ws

## Slide 95
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Re-Install PIX/BCM W6/6
Ready for Beam – 8Ws

## Slide 96
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Remove 20t platforms
Prepare to close and lock YEs
Ready for Beam – 7Ws

## Slide 97
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Close & Lock YE-Z
Ready for Beam – 6Ws

## Slide 98
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Close & Lock YE+Z
Ready for Beam – 5Ws

## Slide 99
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CRUZET Run
Position HF-
Ready for Beam – 4Ws

## Slide 100
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
CRUZET Run
Position HF+
Ready for Beam – 3Ws

## Slide 101
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Close Rotating Shielding
BP pump down W1/2
Ready for Beam – 2Ws

## Slide 102
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
BP pump down W2/2
Magnet Re-commissioning
Ready for Beam – 1W

## Slide 103: Ready for Beam
SL
CP
ECAL
CMX
ZEC
CSC RE
DT+ RB
TK FPIX
Survey
HCAL
TE-VSC
EN Dept
GS Dept
RP
Ready for re-commissioning with Beam

## Slide 104
Time windows without basic services, e.g. power or cooling, to be included
Opening of CMS + removal of PIX and beam pipe: up to W15
CSC project: Start W16 (April 2019)
Complete: W56 (March 2020)
Closing of CMS + installation of PIX and beam pipe:
Start 29w from ready for beam
Very first look at scheduling constraints

## Slide 105: Back-up