## Slide 1
Service Installation for RE3/1 and RE4/1: status and plan
Andrés Leonardo Cabrera Mora
January 30th, 2020
1
Ian Crotty
On behalf of the RPC group

## Slide 2
Outline
High Voltage
Low Voltage
Fiber Optics
Cooling System
Gas System
January 30th, 2020
2

## Slide 3
High Voltage
January 30th, 2020
3
Cables certified up to 15 kV during one hour.
144 Cables tested -> 143 Ok / 1 Rejected and fixed.
Installed:
For RE+4/1: 36 cables from chamber side to YE+1 patch panel
For RE-3/1: 36 cables from chamber side to YE-1 patch panel
To be completed:
For RE+3/1: 36 cables [Ready to be installed]
For RE-4/1: 36 cables [Ready to be installed]
Cable connectorization in UXC/USC.
Patch panel modification in UXC.
Thanks to: Fatma, Manuel, Margarida, Darwish
https://indico.cern.ch/event/835724/
Missing connectors and patch panel
A3512N
Jupiter coaxial connector

## Slide 4
January 30th, 2020
4
Low Voltage
3.8 V (5 A)
GND
2 V (5 A)
GND
FEB 1
FEB 2
3.8 V (5 A)
2 V (5 A)
5V (1.5 A)
2 V (5 A)
GND
GND
GND
GND
GND
2 V (5 A)
Given the revised version of the FEB, Lyon engineers proposed an independent source of voltage.
It implies an additional LV cable for each RPC
144 Cables tested and prepared for installation (Length, continuity test, connector protection installed, labeled)
Installed:
For RE+4/1: 54 cables from chamber side to balcony racks.
For RE-3/1: 36 cables from chamber side to balcony racks.
To be completed:
For RE+3/1: 36 cables [Ready to be installed], 18 cables [ordered]
For RE-3/1: 18 cables [ordered]
For RE-4/1: 18 cables [Ready to be installed], 36 cables [ordered]

## Slide 5
Low Voltage
January 30th, 2020
5
Missing material
https://edh.cern.ch/Document/SupplyChain/DAI/8088990
LV Cables for RE3/1 and RE4/1 (Novacavi)
Order sent on 12.12.2019.
Delivery: 8-10 working weeks from order (February)
https://edh.cern.ch/Document/SupplyChain/DAI/8061905
Cable connectorization (Cavitech)
Waiting for the cable.
Delivery: 3-4 weeks depending on material reception. (March)

## Slide 6
Optical Fibers
January 30th, 2020
6
More details at:
http://project-cms-rpc-endcap.web.cern.ch/project-cms-rpc-endcap/rpc/UpscopeHighEta/RPCDevelopements/RE31and41/Services/OpticalFibres/QA/Method/OpticalFiberTest.pptx

## Slide 7
January 30th, 2020
7
Fiber quality assurance test
Length measurement and qualitative test for power loss
Connection mapping
Labeling

## Slide 8
January 30th, 2020
8
Optical Fibers
Fiber protection: corrugated conduit installation on fibers

## Slide 9
January 30th, 2020
9
Optical Fibers
Patch panel preparation to P5: assembly and installation of YE3PP
RE-3/1 FO
RE-4/1 FO

## Slide 10
January 30th, 2020
10
Optical Fibers
576 fibers tested with OTDR
Installed:
YE+3, YE+1, YE-1 and YE-3 patch panels.
For RE+3/1: 144 fibers from YE+3 patch panel till YE+1 patch panel.
For RE+4/1: 144 fibers from chamber side until YE+1 patch panel.
For RE-3/1: 144 fibers from chamber side until YE-1 patch panel.
For RE-4/1: 144 fibers from YE-3 patch panel till YE-1 patch panel.
To be completed:
For RE+3/1: 144 fibers from YE+3 patch panel until chamber side.
For RE-4/1: 144 fibers from YE-3 patch panel until chamber side.
For all disks: From YE±1 patch panel to USC rack.

## Slide 11
Cooling
January 30th, 2020
11
RE3/1 cooling link to RE3/2
The rigid copper piping will be replaced by flexible hose links to reduce the strain on the unions.
Installation to be done after RE3/1 installation.
x2 RE3/2 circuits feed x1 RE3/1 chamber
For RE+4/1:
Added 9 “t” connection to the mini-manifold (ZEC). [Pressure test performed]
RE+4/1 Cooling
Supply Blue
Return Red

## Slide 12
Gas System
January 30th, 2020
12
Latest drawings of RE+4/1 gas service.
The RE-3/1 gas service installation is 100% done in March (pipes and impedance boxes).
Pressure test performed.
For RE+4/1 gas service installation is 100% done (pipes and impedance boxes).
Pressure test performed.
Gas impedance boxes
To be completed:
RE+3/1 gas service installation
RE-4/1 gas service installation

## Slide 13
Gas System
January 30th, 2020
13
Missing material (order ongoing)
1) Flexible hoses: 40 short + 40 long, we have 1 quote from ZEC, expecting a second one from CEIHP this week.
2) Swagelok unions for flaoating patch panel end of flexible hoses.
3) Legris unions + 6mm caps on the CH side of the flexible hoses.
4) Drill and tap holes for RE-3/1 and RE-4/1 ground cables
5) 2 RE-4/1 impedance boxes are to be finalized and tested
Delivered
https://edh.cern.ch/Document/SupplyChain/DAI/7826363
40 short flexible pipes, 40 long flexible pipes-> Delivered (12.07.2019)
https://edh.cern.ch/Document/SupplyChain/DAI/7818647
Ferrules for CMS RPC Impedance Boxes, Swagelok material needed for the CMS RPC RE4/1 -> Delivered (19/06/2019)
https://edh.cern.ch/Document/SupplyChain/MAG/7819757
Double ferrule unión, Ferr. Union tube caps -> Delivered

## Slide 14
January 30th, 2020
14
Readiness and Schedule

## Slide 15
January 30th, 2020
15
RE-3/1 cable installation 9 days Thu 13/06/19 Tue 25/06/19 (Done)
RE+4/1 cable installation 14 days Fri 02/08/19 Wed 21/08/19 (Done)
RE+3/1 cable installation 10 days Fri 24/04/20 Mon 11/05/20 (Ready)
RE-4/1 cable installation 9 days Fri 29/05/20 Thu 11/06/20 (Ready)
Optical fibre from UXC to USC:
Positive side: 14-20.May.2020 (5 days)
Negative side: after the end of the muon critical path
Readiness and Schedule

## Slide 16
January 30th, 2020
16
Gas and cooling -> ZEC
Optical Fibers -> Russian team
High Voltage -> Russian team
Low Voltage -> Russian team
Manpower for installation

## Slide 17
Thanks!
January 30th, 2020
17

## Slide 18
Backup Slides
January 30th, 2020
18

## Slide 19
January 30th, 2020
19
High Voltage
All cables tested.

## Slide 20
January 30th, 2020
20
Low Voltage

## Slide 21
January 30th, 2020
21
Low Voltage

## Slide 22
January 30th, 2020
22
RE-3/1 cable installation 9 days Thu 13/06/19 Tue 25/06/19 (Done)
RE+4/1 cable installation 14 days Fri 02/08/19 Wed 21/08/19 (Done)
RE+3/1 cable installation 11 days Wed 13/05/20 Wed 27/05/20 (Ready, cooling incomplete)
RE-4/1 cable installation 10 days Wed 15/04/20 Tue 28/04/20 (Ready, cooling incomplete)
Optical fibre from UXC to USC:
Positive side: 04-11.May.2020 (6 days)
Negative side: after the end of the muon critical path
Readiness and Schedule (to be updated)

## Slide 23
January 30th, 2020
23
Labeling Status today
Type | Location | Printed | Installed | # Individual Labels | # Copies | Total | Comments
HV | RE+3/1 | Yes | Done by Fatma | 18 | 2 | 36 | 
HV | RE-3/1 | Yes | Yes | 18 | 2 | 36 | 
HV | RE+4/1 | Yes | Done by Fatma | 18 | 2 | 36 | 16 July finished
HV | RE-4/1 | Yes | Done by Fatma, Gamal, Ekhlas | 18 | 2 | 36 | 18 July finished
LV | RE+3/1 | Yes | Yes | 18 | 2 | 36 | 
LV | RE-3/1 | Yes | Yes | 18 | 2 | 36 | 
LV | RE+4/1 | Yes | Done by Fatma, Gamal, Ekhlas, Manuel | 18 | 2 | 36 | Correction done on UXC by Daniel and Andres, missing chamber side
LV | RE-4/1 | yes | Done by Fatma, Gamal, Ekhlas, Manuel | 18 | 2 | 36 | Correction done on 904 by Manuel and Andres
Fiber | RE+3/1 Cable 1 | Yes | Yes | 18 | 2 | 36 | 
Fiber | RE-3/1 Cable 1 | Yes | Yes | 18 | 2 | 36 | 
Fiber | RE+4/1 Cable 1 | Yes | Yes | 18 | 2 | 36 | Correction done on 904 by Daniel and Andres
Fiber | RE-4/1 Cable 1 | Yes | Yes | 18 | 2 | 36 | Correction done on UXC by Daniel and Andres