## Slide 1: Services RE3 & 4/1
Ian on behalf of the RPC Group
5 Sept 2018

## Slide 2
HV cables and connectors, Umbilical cables USC to UXC. Coaxial cables from YE1PP to YE3 via mini-cable chains
LV cables & connectors on YE3
Fibre optics & Patch Panels from YE3 to YE1PP through to USC
Gas System piping, Impedances and Bulkheads on YE3
Cooling, flexibles on RE4 face of YE3, RE3/1 cooling comes with chambers
RE 3/1 & RE 4/1

## Slide 3
HV System in UXC
We have selected a coaxial connector, tested over many years, namely the C.P.E. “Jupiter” coaxial connector.
The order for the cables and connectors is ready, only awaiting the choice of dielectric. The cables will be QA in the company under our supervision and retested in 904.
Commissioning will be enhanced with resistances in boxes, simulating the chamber load, placed in place of the chambers .

## Slide 4
HV System in the USC
A new rack, S1H12, is installed for the RE3/1 and RE4/1 components.
The TDR version, an extension of the present system is planned.
However an alternative preferred version is planned for testing in 2019
Layout from Anton with calculation of components.
Which ever solution is finally taken does not influence the cabling from UXC.

## Slide 5
HV system routing from USC to UXC
Routing from the USC HV racks to the YE1 PPs
The Main Cable chains in X0 under CMS
Cable sections and lengths, including spares, to be evaluated with CMS Integ Office, S. Bally and Boki

## Slide 6
Modification of the YE1 PP to accept the alternative Jupiter connecter
Cable routing done by Integration office. Requires finalising
YE1 Patch Panel (PP)
Cable installation, 2 weeks for each station starting in March 2019 and finishing in March 2020

## Slide 7
LV Cables UXC, Rack to chamber on YE3
LV tests done, different cable sections and stiffnesses.
Measured time response, using sense wires tested on restive loads, to be repeated on the FEBs during firmware upload ?
Supply of 3.5km of the cable (in P5) previously used for LB
Connectors at chamber end are more or less defined , “D-Sub’ with sense pins
2 cables per chamber but what of the connection in the CAEN module ? Choice of two.
Assembly can be done in Geneva EPI or Cavitech , Boudry, Neuchatel
As with the HV the load should be simulated by a resistance in place to
aid in rapid commissioning.
Communication cable from USC to UXC to be installed in main cable chains Jan 2019
Cable installation, 2 weeks for each station starting in March 2019 and finishing in March 2020

## Slide 8
Fibre optics.
From the choice between Blown fibres and Trunk cables, we have taken the latter, with approval from TC .
As the main protagonists, Zhenan and Behzad are here at CERN we will come out with a full spec by end of next week
The order should leave CERN before the end of September.
Fibres to be installed in week 5 of 2019

## Slide 9: Schematic
1
2
3
4
5
6

## Slide 10: RE4(3)/1 chambers gas distribution schematic
Sagana brass union
reduction from 8mm to 6mm
Legris brass unions (6mm)
8 mm copper pipe
6 mm copper pipe
RE4(3)/3 chamber
RE4(3)/2 chamber
RE4(3)/1 chamber
Impedance box 6 channel
Gas Rack
Bottom layer
Top layer
Supply
Return
Parallel flow

## Slide 11: Piping from USC to UXC distribution racks
From USC gas room to UXC gas racks: new pipes will be installed (2 pipes per disk (negative/positive) for supply/return lines).
To be installed by ZEC in Jan 2019.

## Slide 12
YE3 gas rack to be modified to make the 12 channels independent from the present channels
Impedance boxes positioned at three points around the periphery for both RE4/1 and RE3/1
Impedance box for parallel operation, 2 channel shown
Material proqurement in 1st week of October.
Installation occurs over 2 weeks for each station starting in March 2019 and finishing March 2020
Gas piping, bulkheads and Impedances

## Slide 13
Cooling
Cooling load per station is 540W
RE3/1
Verify the assembly of the flexibles with simplified safer version, namely direct from RE3/2 PP to RE3/1 PP with three elements only, as opposed to 3 times as many unions with a “L” Cu pipe producing a lever arm on the chamber PP.
RE4/1
Modify the present Mini-manifolds to take additional “take offs” direct to the chambers with flexibles all the way to the RE4/1 PP.

## Slide 14
Mini manifold . To be modified to accept the necessary “T”s for the RE4/1 cooling.
The same flow regulators will be kept with individual cut off valves to each chamber, if costs permit.
RE4/1 cooling
Details of which unions to be arranged with cooling group

## Slide 15: Actions required
HV. Outstanding points with CPE, assembly QC methods and timeline
LV
  Do test with New FEB while loading firmware and max cable length ~30m
  S. Bally for exact cable lengths
  Contact Houari for cable length in P5 store.
Fibres, check where we are with spec and supplier in next 10 days as Bezhad and Zhenan are here.
  Check procurement details with Austin.
Gas requires details drawing for installation.
See with cooling suppliers for the inch size on “T” mini manifolds and the metric on the chamber.

## Slide 16: Additional Material

## Slide 17
https://www.epi.ge.ch/prestations-entreprises-particuliers/ateliers/microtechnique/

## Slide 18: RPC Power System Review
Anton Dimitrov, Ian Crotty
RPC Upgrade Mini Workshop, 05.Sep.2018, CERN

## Slide 19
The HV power system will be based on CAEN EASY system
(practically, extension of the existing HV system):
SY4527 – 1 (existing)
A3485S - 2 modules (existing)
4 EASY3000 crates
A3512N – 12 HV Boards
4 HV multiconductor cables per endcap. Each with 20 HV channels
All must go via the YE1’s main cable chains (MCC)
Long term maintenance will be secured by CERN-CAEN contract.
To be integrated in the RPC DCS.
A3512N
A3485S
SY4527
EASY3000
HV Power System Upgrade for RE3/1 & RE4/1 (I)
USC
UXC
TDR Baseline: Variant I
1

## Slide 20
A3485S
A3485S
A3485S
A3485S
SY4527
SY4527
S1H07
HEX
HEX
ENDCAP RACKS S1H11 – S1H08
Crate4
RE-3/1 RE-4/1
Crate4
RE+3/1 RE+4/1
HV Distribution Box
HV Distribution Box
HV Distribution Box
HV Distribution Box
HV Distribution Box
HV Distribution Box
HEX
HEX
S1H12
HV Distribution Box
HV Distribution Box
48V DC cable connected after Crate3 in rack S1H09
48V DC cable connected after Crate3 in rack S1H11
1 new rack (already defined S1H12, to be equipped)
2 EASY crates
8 umbilical cables all arriving to one rack
6 A3512N HV boards in each Crate (12 boards in total)
8 HV Distributor Boxes in total (all in one rack)
2

## Slide 21
The HV power system will be based on CAEN NON-EASY system:
SY4527 – 2 (new)
New HV boards – prototype ready in 2019
4 HV multiconductor cables per endcap. Each with 20 HV channels
All must go via the YE1’s main cable chains (MCC)
Long term maintenance will be secured by CERN-CAEN contract.
To be integrated in the RPC DCS.
A3512N
A3485S
SY4527
EASY3000
HV Power System Upgrade for RE3/1 & RE4/1 (II)
USC
UXC
Preferred Variant: Variant II
3

## Slide 22
A3485S
A3485S
A3485S
A3485S
SY4527
SY4527
S1H07
HEX
HEX
ENDCAP RACKS S1H11 – S1H08
HV Distribution Box
HEX
HEX
S1H12
- No EASY system  no EASY crates
- 2 SY4527 mainframes more
- 8 umbilical cables all arriving to one rack
- New type of HV boards!
- 8 HV Distributor Boxes in total (all in one rack), but bigger in size since all inputs and outputs should be at the back side of the rack
- No rack cross reference in DSS Action Matrix
SY4527
SY4527
HV Distribution Box
HV Distribution Box
HV Distribution Box
HV Distribution Box
HV Distribution Box
HV Distribution Box
HV Distribution Box
4

## Slide 23
24 A3016 LV boards in total to power the FE of all RE3/1 and RE4/1 chambers.
9U in each YE3 X4Far tower rack for
  1 CAEN EASY3000S crate
  1 CAEN A3486S MAO- AC/DC 48V PS
15U in each X2Near YE3 tower rack for
  2 CAEN EASY3000S crates
  1 CAEN A3486S MAO- AC/DC 48V PS
SY4527 with A1676A
CAEN EASY3000S
with CAEN A3016 in X2Near && X4Far racks
A3486S
48V Service power
50p Communication bus
USC
UXC
YE1 LV PP
RPC LV Power System for RE3/1 & RE4/1
1
going directly to YE3
Relay
YE+3: X2J52, X3J51, X3A51, X4A51
YE-3: X2V52, X3V51,X3S51, X4S51
Existing RE3&RE4 detector

## Slide 24
mini Cable Chains for OF
LV Easy crates
Near Side
Far Side
mini Cable Chains for OF
LV Easy crates
X2
X4
RPC LV Services
2
X2Near – X4Far diagonal

## Slide 25
Air Deflector
HEX
X2J52
RE3 LBB
Cable Distribution
RE A3486S AC/DC-0 CH0 CH1
EMU Maraton
EMU Maraton
Turbine
Power Distribution
X3J51
X4A51
YE+3
Near Side
Far Side
RE4 LBB
HEX
HEX
RE3/1 FE EASY3000S Crate0
RE4/1 FE EASY3000S Crate1
HEX
Turbine
Power Distribution
EMU
EMU VME
Air Deflector
HEX
RE3 LBB
Cable Distribution
RE3-4 FEB EASY3000S Crate2
RE3-4 LBB EASY3000S Crate3
RE A3486S AC/DC-1 CH0 CH1
RE4 LBB
Power Dist.
Power Dist.
Power Dist.
HEX
Turbine
Power Distribution
RE3 LBB
RE4 LBB
EMU Maraton
HEX
EMU Maraton
HEX
Air Deflector
Alignment DAQ
RE3-4/1 FE EASY3000S Crate2
RE A3486S AC/DC-1 CH0 CH1
Power Dist.
HEX
Turbine
Power Distribution
HEX
Air Deflector
RE4 LBB
RE4 LBB
Cable Distribution
RE3-4 LBB EASY3000S Crate1
RE3-4 FEB EASY3000S Crate0
RE A3486S AC/DC-0 CH0 CH1
X3A51
EMU
EMU VME

## Slide 26
DCS daisy chain
YE+3
Near Side
Far Side
X2J52
X3J51
X3A51
X4A51
YE3Near and YE3far equipment (including existing RE3&RE4 detector on X3) on separate branch controllers, therefore 4 new A1676 branches will be needed in total.