## Sheet1
|  |  |  | Gas Gaps for 2007 |  |  |  | Ian Crotty
| DEC. 06 | Jan. 07 | Feb. 07 | March. 07 | April. 07 | 2007-05-07 | June. 07 | July. 07 | Aug. 07 | Sept. 07
Delivery to Korea | Full station -3 50% contingency |  | 20 gap sets *3 + *2
Gap prod. Start |  |  | 46 Sets *2 |  | 40-45 Sets *3 | 10 Sets *2 start mid May
Gap Prod ends |  |  |  | 46 Sets *2 end march |  | 40-45 Sets *3 ends 10 may | 10 Sets *2 End 1st June
Delivery to PK (or India) |  |  |  |  | 46 Sets *2 Mid April | 40-45 Sets *3 arrive 20 May | 10 Sets *2 20 June
Assemble in PK (or India) 5ch/week | [6 empty] | 46 Sets *2 Mid June | 8 weeks 40-45 Sets *3 ready 20 July | 10 Sets *2
Arrival CERN | [7 empty] | 46 Sets *2 1st July | 40-45 Sets *3 arrive 1 Aug | 10 Sets *2
Cosmic Testing | [7 empty] | 46 Sets *2 16 July | 40-45 Sets *3 Ready Mid August | 10 Sets *2
Installation Start | [7 empty] | 46 Sets *2 16 July | 40-45 Sets *3 Ready End August
Installation Finish
Services