## Chamber RE4-2
Chamber ID | Expected arrival | QC4 arrival | Status | Coonectivity | Status | Electric test | Status | HV scan | Status | Stability start | Stability test time [days] | Stability end | Status | Removed | Leak test | Status | DB updated | Back to QC3 | Back to QC4 | SM delivery | SM ID
CMS-RE4-2-CERN-017 |  | 2013-04-11 | 1900-02-01 | 2013-04-11 | 1900-02-01 | 2013-04-24 | 1900-01-02 | 2013-04-29 | 1900-01-02 | 07/24/2013, 5 /09/2013 |  | 08/20/2013 15:30, 10/07/2013 | 1899-12-31 | 1900-01-02 | 2013-06-13 | 1900-01-02 |  | 20/08/2013, 07/10/2013 | 2013-08-31 | 2013-04-13
CMS-RE4-2-CERN-012 |  | 2013-04-08 | 1900-02-01 | 2013-05-07 | 1900-01-02 | 2013-05-07 | 1900-01-02 | 2013-05-06 | 1900-01-02 | 2013-05-06 18:40 | 30.0972 | 2013-06-05 21:00 | 1900-01-02 | 1900-01-02 | 2013-06-11 | 1900-01-02 | 1900-01-02 | 2013-04-17 | 2013-05-02 | 2013-04-08 | 8
CMS-RE4-2-CERN-013 |  | 2013-05-02 | 1900-02-01 | 2013-05-07 | 1900-01-02 | 2013-05-07 | 1900-01-02 | 2013-05-06 | 1900-01-02 | 2013-05-10 23:10 | 23.4097 | 2013-06-03 09:00 | 1900-01-02 | 1900-01-02 | 2013-06-14 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-03 | 3
CMS-RE4-2-CERN-015 |  | 2013-05-02 | 1900-02-01 | 2013-05-07 | 1900-01-02 | 2013-05-07 | 1900-01-02 | 2013-05-06 | 1900-01-02 | 2013-05-06 18:40 | 30.8521 | 2013-06-06 15:07 | 1900-01-02 | 1900-01-02 | 2013-06-13 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-17 | 6
CMS-RE4-2-CERN-016 |  | 2013-04-13 | 1900-02-01 | 2013-05-07 | 1900-01-02 | 2013-05-07 | 1900-01-02 | 2013-04-17 | 1900-01-02 | 2013-05-06 18:40 | 30.0972 | 2013-06-05 21:00 | 1900-01-02 | 1900-01-02 | 2013-06-17 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-17 | 7
CMS-RE4-2-CERN-018 |  | 2013-05-02 | 1900-02-01 | 2013-05-07 | 1900-02-01 | 2013-05-07 | 1900-02-01 | 2013-05-06 | 1900-01-02 | 2013-05-06 18:40 | 30.0972 | 2013-06-05 21:00 | 1900-01-02 | 1900-01-02 | 2013-06-13 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-06 | 4
CMS-RE4-2-CERN-014 |  | 2013-05-02 | 1900-02-01 | 2013-05-07 | 1900-02-01 | 2013-05-07 | 1900-02-01 | 2013-05-06 | 1900-02-01 | 2013-05-10 23:10 | 26.6646 | 2013-06-06 15:07 | 1900-01-02 | 1900-01-02 | 2013-06-14 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-07 | 5
CMS-RE4-2-BARC-023 |  | 2013-05-24 | 1900-02-01 | 2013-06-28 | 1900-02-01 | 2013-06-28 | 1900-02-01 | 2013-07-01 | 1900-02-01 | 2013-07-01 17:30 | 56 | 2013-08-26 17:30 | 1900-01-02 | 1900-01-02 | 2013-06-28 | 1900-02-01 | 1900-01-02 | 2013-05-28 | 2013-06-28 | 2013-08-26 | 19
CMS-RE4-2-BARC-019 |  | 2013-05-24 | 1900-02-01 | 2013-06-21 | 1900-02-01 | 2013-06-20 | 1900-02-01 | 2013-06-21 | 1900-02-01 | 2013-06-24 13:14 | 7 | 2013-07-01 13:14 | 1900-01-02 | 1900-01-02 | 2013-07-04 | 1900-02-01 | 1900-02-01 | 2013-05-28 | 2013-06-20 | 2013-07-01 | 9
CMS-RE4-2-BARC-021 |  | 2013-05-24 | 1900-02-01 | 2013-06-21 | 1900-02-01 | 2013-06-19 | 1900-02-01 | 2013-06-21 | 1900-02-01 | 2013-06-21 18:14 | 19.67 | 2013-07-11 10:19 | 1900-01-02 | 1900-01-02 | 2013-06-19 | 1900-02-01 | 1900-01-02 | 2013-05-28 | 2013-06-19 | 2013-07-11 | 11
CMS-RE4-2-BARC-024 |  | 2013-05-24 | 1900-02-01 | 2013-06-28 | 1900-02-01 | 2013-06-28 | 1900-02-01 | 2013-10-01 | 1900-01-02 | 2013-10-01 16:48 | 31 | 2013-11-01 16:48 | 1900-01-02 | 1900-01-02 | 2013-11-04 | 1900-02-01 | 1900-01-02 | 28/05/2013, 20/08/2013 | 2013-06-28 | 2013-11-05 | 34
CMS-RE4-2-BARC-009 |  | 2013-05-24 | 1900-02-01 | 2013-06-28 | 1900-02-01 | 2013-06-28 | 1900-02-01 | 2013-07-01 | 1900-02-01 | 2013-07-01 17:30 | 14.83 | 2013-07-16 13:25 | 1900-01-02 | 1900-01-02 | 2013-06-28 | 1900-02-01 | 1900-01-02 | 2013-05-28 | 2013-06-28 | 2013-07-16 | 13
CMS-RE4-2-BARC-022 |  | 2013-05-24 | 1900-02-01 | 2013-06-28 | 1900-02-01 | 2013-06-28 | 1900-01-02 | 2013-07-01 | 1900-02-01 | 2013-07-01 17:30 | 13.7 | 2013-07-15 10:18 | 1900-01-02 | 1900-01-02 | 2013-06-28 | 1900-02-01 | 1900-01-02 | 2013-05-28 | 2013-06-28 | 2013-07-15 | 12
CMS-RE4-2-BARC-005 |  | 2013-05-24 | 1900-02-01 | 2013-06-21 | 1900-02-01 | 2013-06-20 | 1900-02-01 | 2013-10-01 | 1900-01-02 | 2013-10-01 16:48 | 31 | 2013-11-01 16:48 | 1900-01-02 | 1900-01-02 | 2013-11-04 | 1900-02-01 | 1900-01-02 | 28/05/2013, 20/08/2013 | 2013-06-20 | 2013-11-04 | 33
CMS-RE4-2-BARC-007 |  | 2013-05-24 | 1900-02-01 | 2013-06-21 | 1900-02-01 | 2013-06-19 | 1900-02-01 | 2013-06-21 | 1900-02-01 | 2013-06-24 13:14 | 7 | 2013-07-01 13:14 | 1900-01-02 | 1900-01-02 | 2013-06-19 | 1900-02-01 | 1900-01-02 | 2013-05-28 | 2013-06-19 | 2013-07-01 | 10
CMS-RE4-2-CERN-050 |  | 2013-07-16 | 1900-02-01 | 2013-07-17 | 1900-02-01 | 2013-07-16 | 1900-01-02 | 2013-07-17 | 1900-02-01 | 2013-07-17 19:41 | 11.75 | 2013-07-29 13:41 | 1900-01-02 | 1900-01-02 | 2013-07-04 | 1900-02-01 | 1900-01-02 |  |  | 2013-07-29 | 14
CMS-RE4-2-CERN-056 |  | 2013-07-16 | 1900-02-01 | 2013-07-17 | 1900-02-01 | 2013-07-16 | 1900-01-02 | 2013-07-18 | 1900-02-01 | 2013-07-19 11:17 | 12.95 | 2013-08-01 10:05 | 1900-01-02 | 1900-01-02 | 2013-07-16 | 1900-02-01 | 1900-01-02 | 2013-07-17 | 2013-07-17 | 2013-08-01 | 16
CMS-RE4-2-CERN-055 |  | 2013-07-16 | 1900-02-01 | 2013-07-17 | 1900-02-01 | 2013-07-16 | 1900-02-01 | 2013-07-17 | 1900-02-01 | 2013-07-17 19:41 | 12.8 | 2013-07-30 14:53 | 1900-01-02 | 1900-01-02 | 2013-07-16 | 1900-02-01 | 1900-01-02 |  |  | 2013-07-30 | 15
CMS-RE4-2-CERN-059 |  | 2013-08-12 | 1900-02-01 | 2013-08-22 | 1900-02-01 | 2013-08-12 | 1900-02-01 | 2013-08-15 | 1900-02-01 | 2013-08-15 11:00 | 7 | 2013-08-22 11:00 | 1900-01-02 | 1900-01-02 | 2013-08-12 | 1900-02-01 | 1900-01-02 |  |  | 2013-08-22 | 17
CMS-RE4-2-CERN-060 |  | 2013-08-12 | 1900-02-01 | 2013-08-22 | 1900-02-01 | 2013-08-12 | 1900-02-01 | 2013-09-03 | 1900-02-01 | 2013-08-23 13:18 | 11 | 2013-09-03 13:18 | 1900-01-02 | 1900-01-02 | 2013-08-12 | 1900-02-01 | 1900-01-02 |  |  | 2013-09-03 | 22
CMS-RE4-2-CERN-057 |  | 2013-08-12 | 1900-01-02 | 2013-08-22 | 1900-02-01 | 2013-08-12 | 1900-01-02 | 2013-08-28 | 1900-02-01 | 2013-08-23 14:38 | 5 | 2013-08-28 14:38 | 1900-01-02 | 1900-01-02 | 2013-08-12 | 1900-02-01 | 1900-01-02 |  |  | 2013-08-26 | 21
CMS-RE4-2-CERN-065 |  | 2013-08-12 | 1900-02-01 | 2013-08-22 | 1900-02-01 | 2013-08-12 | 1900-02-01 | 2013-08-15 | 1900-02-01 | 2013-08-15 11:00 | 8 | 2013-08-23 11:00 | 1900-01-02 | 1900-01-02 | 2013-08-12 | 1900-02-01 | 1900-01-02 |  |  | 2013-08-23 | 18
CMS-RE4-2-CERN-062 |  | 2013-08-12 | 1900-02-01 | 2013-08-22 | 1900-02-01 | 2013-08-12 | 1900-02-01 | 2013-08-27 | 1900-02-01 | 2013-08-14 16:00 | 12 | 2013-08-26 16:00 | 1900-01-02 | 1900-01-02 | 2013-08-27 | 1900-02-01 | 1900-01-02 |  |  | 2013-08-26 | 20
CMS-RE4-2-CERN-063 |  | 2013-08-29 | 1900-02-01 | 2013-08-29 | 1900-02-01 | 2013-09-02 | 1900-01-02 | 2013-09-02 | 1900-02-01 | 2013-09-02 17:55 | 18 | 2013-09-20 17:55 | 1900-01-02 | 1900-01-02 | 2013-08-30 | 1900-02-01 | 1900-01-02 |  |  | 2013-09-20 | 26
CMS-RE4-2-CERN-064 |  | 2013-08-29 | 1900-02-01 | 2013-08-29 | 1900-02-01 | 2013-09-02 | 1900-01-02 | 2013-09-02 | 1900-02-01 | 2013-09-02 17:55 | 15 | 2013-09-17 17:55 | 1900-01-02 | 1900-01-02 | 2013-08-30 | 1900-02-01 | 1900-01-02 |  |  | 2013-09-17 | 24
CMS-RE4-2-CERN-066 |  | 2013-08-29 | 1900-02-01 | 2013-08-29 | 1900-02-01 | 2013-09-02 | 1900-01-02 | 2013-09-02 | 1900-02-01 | 2013-09-02 17:55 | 42 | 2013-10-14 17:55 | 3 | 1900-01-02 | 2013-08-30 | 1900-02-01 | 1900-01-02 |  |  | 2013-10-16 | 2
CMS-RE4-2-CERN-067 |  | 2013-08-29 | 1900-02-01 | 2013-08-29 | 1900-02-01 | 2013-09-02 | 1900-02-01 | 2013-09-02 | 1900-02-01 | 2013-09-02 17:55 | 14 | 2013-09-16 17:55 | 1900-01-02 | 1900-01-02 | 2013-08-30 | 1900-02-01 | 1900-01-02 |  |  | 2013-09-17 | 23
CMS-RE4-2-CERN-068 |  | 2013-08-29 | 1900-02-01 | 2013-08-29 | 1900-02-01 | 2013-09-02 | 1900-02-01 | 2013-10-01 | 1900-01-02 | 2013-10-01 16:48 | 31 | 2013-11-01 16:48 | 1900-01-02 | 1900-01-02 | 2013-08-30 | 1900-02-01 | 1900-01-02 | 2013-09-17 | 2013-10-01 | 2013-11-06 | 35
CMS-RE4-2-CERN-053 |  | 2013-08-29 | 1900-02-01 | 2013-08-29 | 1900-02-01 | 2013-09-02 | 1900-01-02 | 2013-09-02 | 1900-02-01 | 2013-09-02 17:55 | 17 | 2013-09-19 17:55 | 1900-01-02 | 1900-01-02 | 2013-08-30 | 1900-02-01 | 1900-01-02 |  |  | 2013-09-19 | 25
CMS-RE4-2-CERN-061 |  | 2013-08-29 | 1900-02-01 | 2013-08-29 | 1900-02-01 | 2013-09-02 | 1900-01-02 | 2013-09-02 | 1900-02-01 | 2013-09-02 17:55 | 21 | 2013-09-23 17:55 | 1900-01-02 | 1900-01-02 | 2013-08-30 | 1900-02-01 | 1900-02-01 |  |  | 2013-09-23 | 27
CMS-RE4-2-CERN-051 |  | 2013-09-09 | 1900-02-01 | 2013-09-14 | 1900-02-01 | 2013-09-26 | 1900-01-02 | 2013-09-26 | 1900-01-02 | 2013-09-16 09:15 | 10 | 2013-09-26 09:15 | 3 | 3 | 2013-09-26 | 1900-01-02 | 1900-01-02 |  |  | 2013-09-26 | 30
CMS-RE4-2-CERN-069 |  | 2013-09-09 | 1900-02-01 | 2013-09-14 | 1900-02-01 | 2013-10-21 | 1900-01-02 | 2013-10-21 | 1900-01-02 | 2013-09-16 09:15 | 35.3 | 2013-10-21 16:27 | 3 | 3 | 2013-11-05 | 1900-01-02 | 1900-01-02 |  |  | 2013-10-21 | 32
CMS-RE4-2-CERN-073 |  | 2013-09-09 | 1900-02-01 | 2013-09-14 | 1900-02-01 | 2013-09-25 | 1900-01-02 | 2013-09-24 | 1900-01-02 | 2013-09-16 09:15 | 8 | 2013-09-24 09:15 | 3 | 3 | 2013-09-24 | 1900-02-01 | 1900-02-01 |  |  | 2013-09-25 | 28
CMS-RE4-2-CERN-079 |  | 2013-09-09 | 1900-02-01 | 2013-09-14 | 1900-02-01 | 2013-10-21 | 1900-01-02 | 2013-10-21 | 1900-01-02 | 2013-09-16 09:15 | 35.3 | 2013-10-21 16:27 | 3 | 3 | 2013-11-06 | 1900-01-02 | 1900-01-02 |  |  | 2013-10-21 | 31
CMS-RE4-2-CERN-020 |  | 2013-09-11 | 1900-02-01 | 2013-09-14 | 1900-02-01 | 2013-09-25 | 1900-01-02 | 2013-09-24 | 1900-01-02 | 2013-09-16 09:15 | 8 | 2013-09-24 09:15 | 3 | 3 | 2013-09-24 | 1900-02-01 | 1900-02-01 |  |  | 2013-09-25 | 29
CMS-RE4-2-CERN-078 |  | 2013-09-26 | 1900-02-01 | 2013-09-26 | 1900-02-01 | 2013-09-27 | 1900-01-02 | 2013-10-01 | 1900-01-02 | 2013-10-01 16:48 | 31 | 2013-11-01 16:48 | 3 | 1900-01-02 | 2013-09-26 | 1900-02-01 | 1900-02-01 |  |  | 2013-11-13 | 36
CMS-RE4-2-CERN-080 |  | 2013-10-07 | 1900-01-02 | 2013-10-07 | 1900-01-02 | 2013-10-08 | 1900-01-02 | 2013-10-10 | 1900-01-02 | 2013-10-11 00:43 | 26.7 | 2013-11-06 17:31 | 3 | 3 | 2013-10-07 | 1900-02-01 | 1900-02-01 |  |  | 2013-11-13 | 37
2nd ENDCAP
| Scheduled | Expected Arrival | [9 empty] | Expected Delivery
DELAY RESPECT TO THE CALENDAR | 30 | DAYS
Formulas:
Stability end = [Stability start]+[Stability test time [days]]
Stability start = [QC4 arrival]+1.82

## Chamber RE4-3
DISK RE+4
Chamber ID | Expected arrival | QC4 arrival | Electric test | Status | HV scan | Status | Stability start | Stability test time [days] | Stability end | Status | Removed | Leak test | Status | DB updated | Back to QC3 | Back to QC4 | SM delivery | SM ID
CMS-RE4-3-Ghent-003 |  | 2013-04-08 | 2013-04-24 | 1900-01-02 | 2013-04-25 | 1900-01-02 | 07/24/2013 |  | 08/20/2013 15:30 | 1900-01-02 | 1900-01-02 | 2013-06-13 | 1900-01-02 | 1900-01-02 |  |  | 2013-04-08 | 2
CMS-RE4-3-Ghent-006 |  | 2013-04-11 | 2013-04-22 | 1900-01-02 | 2013-04-15 | 1900-02-01 | 2013-04-27 | 30.2917 | 2013-05-27 07:00 | 1900-01-02 | 1900-01-02 | 2013-06-14 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-03 | 3
CMS-RE4-3-CERN-010 |  | 2013-05-02 | 2013-05-07 | 1900-01-02 | 2013-05-03 | 1900-01-02 | 2013-05-06 18:40 | 30.0972 | 2013-06-05 21:00 | 1900-01-02 | 1900-01-02 | 2013-06-13 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-06 | 4
CMS-RE4-3-CERN-011 |  | 2013-05-02 | 2013-05-07 | 1900-01-02 | 2013-05-03 | 1900-01-02 | 2013-05-06 18:40 | 30.0972 | 2013-06-05 21:00 | 1900-01-02 | 1900-01-02 | 2013-06-14 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-14 | 5
CMS-RE4-3-CERN-031 |  | 2013-05-29 | 2013-05-30 | 1900-01-02 | 2013-05-31 | 1900-01-02 | 2013-05-31 13:50 | 16.9097 | 2013-06-17 11:40 | 1900-01-02 | 1900-01-02 | 2013-06-17 | 1900-01-02 | 1900-01-02 | 2013-05-30 | 2013-05-30 | 2013-06-14 | 7
CMS-RE4-3-CERN-027 |  | 2013-05-29 | 2013-05-30 | 1900-01-02 | 2013-05-31 | 1900-01-02 | 2013-05-31 13:50 | 16.9097 | 2013-06-17 11:40 | 1900-01-02 | 1900-01-02 | 2013-06-19 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-14 | 8
CMS-RE4-3-CERN-028 |  | 2013-05-29 | 2013-05-30 | 1900-01-02 | 2013-05-31 | 1900-01-02 | 2013-05-31 13:50 | 16.9097 | 2013-06-17 11:40 | 1900-01-02 | 1900-01-02 | 2013-06-18 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-14 | 9
CMS-RE4-3-CERN-034 |  | 2013-05-29 | 2013-05-30 | 1900-01-02 | 2013-05-31 | 1900-01-02 | 2013-05-31 13:50 | 16.9097 | 2013-06-17 11:40 | 1900-01-02 | 1900-01-02 | 2013-06-18 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-14 | 10
CMS-RE4-3-CERN-029 |  | 2013-05-29 | 2013-05-30 | 1900-01-02 | 2013-05-31 | 1900-01-02 | 2013-05-31 13:50 | 16.9097 | 2013-06-17 11:40 | 1900-01-02 | 1900-01-02 | 2013-06-17 | 1900-01-02 | 1900-01-02 |  |  | 2013-06-14 | 6
CMS-RE4-3-CERN-032 |  | 2013-06-04 | 2013-06-05 | 1900-01-02 | 2013-06-07 | 1900-01-02 | 2013-06-07 11:00 | 28 | 2013-07-05 11:00 | 1900-01-02 | 1900-01-02 | 2013-07-09 | 1900-01-02 | 1900-01-02 |  |  | 2013-07-05 | 11
CMS-RE4-3-CERN-033 |  | 2013-06-04 | 2013-06-05 | 1900-01-02 | 2013-06-07 | 1900-01-02 | 2013-06-07 11:00 | 87 | 2013-09-02 11:00 | 1900-01-02 | 1900-01-02 | 2013-09-02 | 1900-01-02 | 1900-01-02 | 2013-06-05 |  | 2013-09-03 | 22
CMS-RE4-3-CERN-035 |  | 2013-06-04 | 2013-06-05 | 1900-01-02 | 2013-06-07 | 1900-01-02 | 2013-06-07 11:00 | 28 | 2013-07-05 11:00 | 1900-01-02 | 1900-01-02 | 2013-07-09 | 1900-01-02 | 1900-01-02 |  |  | 2013-07-05 | 12
CMS-RE4-3-CERN-036 |  | 2013-06-19 | 2013-06-20 | 1900-01-02 | 2013-06-21 | 1900-01-02 | 2013-06-21 18:14 | 27.9 | 2013-07-19 15:50 | 1900-01-02 | 1900-01-02 | 2013-07-22 | 1900-01-02 | 1900-01-02 |  |  | 2013-07-19 | 14
CMS-RE4-3-CERN-037 |  | 2013-06-19 | 2013-06-20 | 1900-01-02 | 2013-06-21 | 1900-01-02 | 2013-06-21 18:14 | 68 | 2013-08-28 18:14 | 1900-01-02 | 1900-01-02 | 2013-08-28 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-28 | 21
CMS-RE4-3-CERN-039 |  | 2013-06-19 | 2013-06-20 | 1900-01-02 | 2013-06-21 | 1900-01-02 | 2013-06-21 18:14 | 24.8 | 2013-07-16 13:26 | 1900-01-02 | 1900-01-02 | 2013-07-17 | 1900-01-02 | 1900-01-02 |  |  | 2013-07-16 | 13
CMS-RE4-3-CERN-038 |  | 2013-06-19 | 2013-06-20 | 1900-01-02 | 2013-06-21 | 1900-01-02 | 2013-06-24 13:14 | 35 | 2013-07-29 13:14 | 1900-01-02 | 1900-01-02 | 2013-07-29 | 1900-01-02 | 1900-01-02 |  |  | 2013-07-30 | 15
CMS-RE4-3-CERN-040 |  | 2013-06-27 | 2013-06-28 | 1900-01-02 | 2013-07-02 | 1900-02-01 | 2013-07-02 18:00 | 29.666 | 2013-08-01 09:59 | 1900-01-02 | 1900-01-02 | 2013-06-28 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-01 | 16
CMS-RE4-3-CERN-025 |  | 2013-06-27 | 2013-06-28 | 1900-01-02 | 2013-07-02 | 1900-02-01 | 2013-07-02 18:00 | 29.666 | 2013-08-01 09:59 | 1900-01-02 | 1900-01-02 | 2013-06-28 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-01 | 17
CMS-RE4-3-CERN-041 |  | 2013-06-27 | 2013-06-28 | 1900-01-02 | 2013-07-02 | 1900-02-01 | 2013-07-02 18:00 | 29.666 | 2013-08-01 09:59 | 1900-01-02 | 1900-01-02 | 2013-06-28 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-01 | 18
CMS-RE4-3-CERN-043 |  | 2013-06-27 | 2013-06-28 | 1900-01-02 | 2013-07-02 | 1900-02-01 | 2013-07-02 18:00 | 29.666 | 2013-08-01 09:59 | 1900-01-02 | 1900-01-02 | 2013-06-28 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-01 | 20
CMS-RE4-3-CERN-042 |  | 2013-06-27 | 2013-06-28 | 1900-01-02 | 2013-07-02 | 1900-02-01 | 2013-07-02 18:00 | 29.666 | 2013-08-01 09:59 | 1900-01-02 | 1900-01-02 | 2013-06-28 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-01 | 20
CMS-RE4-3-GENT-026 |  | 2013-07-05 | 2013-07-08 | 1900-01-02 | 2013-07-09 | 1900-02-01 | 2013-07-09 16:05 | 30 | 2013-08-08 16:05 | 1900-01-02 | 1900-01-02 | 2013-08-27 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-28 | 23
CMS-RE4-3-GENT-008 |  | 2013-07-05 | 2013-07-09 | 1900-01-02 | 2013-07-09 | 1900-02-01 | 2013-07-09 16:05 | 30 | 2013-08-08 16:05 | 1900-01-02 | 1900-01-02 | 2013-08-28 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-28 | 24
CMS-RE4-3-GENT-044 |  | 2013-07-05 | 2013-07-08 | 1900-01-02 | 2013-07-09 | 1900-02-01 | 2013-07-19 15:36 | 34 | 2013-08-22 15:36 | 1900-01-02 | 1900-01-02 | 2013-08-28 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-28 | 27
CMS-RE4-3-GENT-030 |  | 2013-07-05 | 2013-07-08 | 1900-01-02 | 2013-07-09 | 1900-02-01 | 2013-07-19 15:36 | 40 | 2013-08-28 15:36 | 1899-12-31 |  | 2013-08-26 | 1900-01-02
CMS-RE4-3-GENT-046 |  | 2013-07-05 | 2013-07-08 | 1900-01-02 | 2013-07-09 | 1900-02-01 | 2013-07-19 15:36 | 32 | 2013-08-20 15:36 | 1900-01-02 | 1900-01-02 | 2013-08-28 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-28 | 25
CMS-RE4-3-GENT-047 |  | 2013-07-05 | 2013-07-08 | 1900-01-02 | 2013-07-09 | 1900-02-01 | 2013-07-09 16:05 | 30 | 2013-08-08 16:05 | 1900-01-02 | 1900-01-02 | 2013-08-28 | 1900-01-02 | 1900-01-02 |  |  | 2013-08-28 | 26
CMS-RE4-3-GENT-052 |  | 2013-08-19 | 2013-08-21 | 1900-01-02 | 2013-08-21 | 1900-02-01 | 2013-08-20 20:53 | 35 | 2013-09-24 20:53 | 1900-01-02 | 1900-01-02 | 2013-09-24 | 1900-01-02 | 1900-01-02 |  |  | 2013-09-24 | 28
CMS-RE4-3-GENT-048 |  | 2013-08-19 | 2013-08-21 | 1900-01-02 | 2013-08-21 | 1900-02-01 | 2013-08-20 20:53 | 35 | 2013-09-24 20:53 | 1900-01-02 | 1900-01-02 | 2013-09-24 | 1900-01-02 | 1900-01-02 |  |  | 2013-09-26 | 29
CMS-RE4-3-GENT-054 |  | 2013-08-19 | 2013-08-21 | 1900-01-02 | 2013-08-21 | 1900-02-01 | 2013-08-20 20:53 | 35 | 2013-09-24 20:53 | 1900-01-02 | 1900-01-02 | 2013-09-24 | 1900-01-02 | 1900-01-02 |  |  | 2013-09-26 | 30
CMS-RE4-3-GENT-049 |  | 2013-08-19 | 2013-08-21 | 1900-01-02 | 2013-08-21 | 1900-02-01 | 2013-08-20 20:53 | 77.6 | 2013-11-06 11:17 | 1900-01-02 | 1900-01-02 | 2013-11-06 | 1900-01-02 | 1900-01-02 |  |  | 2013-11-06 | 35
CMS-RE4-3-GENT-045 |  | 2013-08-19 | 2013-08-21 | 1900-01-02 | 2013-08-21 | 1900-02-01 | 2013-08-20 20:53 | 35 | 2013-09-24 20:53 | 1900-01-02 | 1900-01-02 | 2013-09-24 | 1900-01-02 | 1900-01-02 |  |  | 2013-09-27 | 31
CMS-RE4-3-GENT-058 |  | 2013-09-09 | 2013-08-22 | 1900-01-02 | 2013-10-17 | 1900-02-01 | 2013-09-19 14:38 | 25 | 2013-10-14 14:38 | 1900-01-02 | 1900-01-02 | 2013-11-05 | 1900-01-02 | 1900-01-02 |  |  | 2013-10-24 | 32
CMS-RE4-3-CERN-076 |  | 2013-09-09 | 2013-10-08 | 1900-01-02 | 2013-10-08 | 1900-02-01 | 2013-09-16 02:24 | 51.6 | 2013-11-06 16:48 | 1900-01-02 | 1900-01-02 | 2013-11-11 | 1900-01-02 | 1900-01-02 |  |  | 2013-11-13 | 36
CMS-RE4-3-CERN-072 |  | 2013-09-09 | 2013-10-08 | 1900-01-02 | 2013-10-08 | 1900-02-01 | 2013-09-19 14:38 | 48.1 | 2013-11-06 17:02 | 1900-01-02 | 1900-01-02 | 2013-11-11 | 1900-01-02 | 1900-01-02 |  |  | 2013-11-13 | 37
CMS-RE4-3-CERN-071 |  | 2013-09-26 | 2013-09-27 | 1900-01-02 | 2013-10-01 | 1900-02-01 | 2013-10-02 16:48 | 30 | 2013-11-01 16:48 | 1900-01-02 | 1900-01-02 | 9/26/13 | 1900-01-02 | 1900-01-02 |  |  | 2013-11-04 | 33
CMS-RE4-3-CERN-074 |  | 2013-09-26 | 2013-09-27 | 1899-12-31 | 2013-10-01 | 1900-02-01 | 2013-10-02 16:48 | 42 | 2013-11-13 16:48 | 1899-12-31 |  | 9/26/13 | 1900-01-02 |  | 2013-11-13
CMS-RE4-3-CERN-077 |  | 2013-09-26 | 2013-09-27 | 1900-01-02 | 2013-10-01 | 1900-02-01 | 2013-10-02 19:12 | 33.9 | 2013-11-05 16:48 | 1900-01-02 | 1900-01-02 | 9/26/13 | 1900-01-02 | 1900-01-02 |  |  | 2013-11-05 | 34
CMS-RE4-3-CERN-070 |  | 2013-09-26 | 2013-09-27 | 1900-01-02 | 2013-10-01 | 1900-02-01 | 2013-10-02 19:12 | 40 | 2013-11-11 19:12 | 1899-12-31 |  | 9/26/13 | 1900-01-02 |  | 2013-11-28
| Scheduled | Expected Arrival | [6 empty] | Expected Delivery
DELAY RESPECT TO THE CALENDAR | 18 | DAYS
Formulas:
Stability end = [Stability start]+[Stability test time [days]]
Stability start = [QC4 arrival]+4.67

## SMs
SM ID | chambers | Reception date | SM assembled | Status | Gas leak test | Status | Cooling test | Status | DB Updated | Stored to the rack for P5 | Shipment Date to P5
2 | CMS-RE4-2-CERN-066 | 2013-10-16 | 2013-10-25 | 3 | 2013-11-08 | 1 | 2013-11-21 | 3 | 3 | 2013-12-04 | NEAR side 04/12/2013
| CMS-RE4-3-Ghent-003 | 2013-04-13
3 | CMS-RE4-2-CERN-013 | 2013-06-03 | 2013-06-06 | 3 | 2013-06-14 | 3 | 2013-10-13 | 1 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-Ghent-006 | 2013-06-03
4 | CMS-RE4-2-CERN-018 | 2013-06-06 | 2013-06-12 | 3 | 2013-06-13 | 3 | 2013-10-03 | 3 | 3 | 2013-10-10 | trial 25/10/2013, NEAR side 04/12/2013
| CMS-RE4-3-CERN-010 | 2013-06-06
5 | CMS-RE4-2-CERN-014 | 2013-06-07 | 2013-06-12 | 3 | 2013-06-14 | 3 | 2013-11-12 | 1 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-CERN-011 | 2013-06-07
6 | CMS-RE4-2-CERN-015 | 2013-06-17 | 2013-06-18 | 3 | 2013-06-20 | 3 | 2013-11-08 | 3 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-CERN-029 | 2013-06-14
7 | CMS-RE4-2-CERN-016 | 2013-06-17 | 2013-06-19 | 3 | 2013-06-21 | 3 | 2013-10-12 | 1 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-CERN-031 | 2013-06-14 | [9 empty] | #REF!
8 | CMS-RE4-2-CERN-012 | 2013-06-19 | 2013-06-21 | 3 | 2013-07-04 | 3 | 2013-10-04 | 3 | 3 | 2013-10-10 | trial 25/10/2013, NEAR side 04/12/2013
| CMS-RE4-3-CERN-027 | 2013-06-14
9 | CMS-RE4-2-BARC-019 | 2013-07-01 | 2013-07-03 | 3 | 2013-07-04 | 3 | 2013-10-11 | 1 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-CERN-028 | 2013-06-14
10 | CMS-RE4-2-BARC-007 | 2013-07-01 | 2013-07-04 | 3 | 2013-07-04 | 3 | 2013-10-04 | 3 | 3 | 2013-10-10 | trial 25/10/2013, NEAR side 04/12/2013
| CMS-RE4-3-CERN-034 | 2013-06-14
11 | CMS-RE4-2-BARC-021 | 2013-07-11 | 2013-07-11 | 3 | 2013-07-22 | 3 | 2013-10-03 | 3 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-CERN-032 | 2013-07-05
12 | CMS-RE4-2-BARC-022 | 15-juil | 2013-07-15 | 3 | 2013-07-22 | 3 | 2013-10-25 | 3 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-CERN-035 | 2013-07-05
13 | CMS-RE4-2-BARC-009 | 16-juil | 2013-07-16 | 3 | 2013-07-22 | 3 | 2013-11-13 | 3 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-CERN-039 | 16-juil
14 | CMS-RE4-2-CERN-050 | 29-juil | 2013-07-29 | 3 | 2013-11-19 | 3 | 2013-11-12 | 3 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-CERN-036 | 19-juil
15 | CMS-RE4-2-CERN-055 | 30-juil | 2013-07-30 | 3 | 2013-10-07 | 1 | 2013-10-03 | 3 | 3 | 2013-10-10 | trial 25/10/2013, NEAR side 04/12/2013
| CMS-RE4-3-CERN-038 | 30-juil
16 | CMS-RE4-2-CERN-056 | 2013-08-01 | 2013-08-01 | 3 | 2013-10-07 | 1 | 2013-10-04 | 3 | 3 | 2013-10-10 | trial 25/10/2013, NEAR side 04/12/2013
| CMS-RE4-3-CERN-040 | 2013-08-01
17 | CMS-RE4-2-CERN-059 | 2013-08-22 | 2013-08-23 | 3 | 2013-11-13 | 1 | 2013-11-27 | 3 | 3 | 2013-12-02 | NEAR side 04/12/2013/11/2013
| CMS-RE4-3-CERN-025 | 2013-08-01
18 | CMS-RE4-2-CERN-065 | 2013-08-22 | 2013-08-23 | 3 | 2013-11-13 | 1 | 2013-11-26 | 3 | 3 | 2013-12-02 | NEAR side 04/12/2013/11/2013
| CMS-RE4-3-CERN-041 | 2013-08-23
19 | CMS-RE4-2-BARC-023 | 2013-08-26 | 2013-08-26 | 3 | 2013-11-13 | 1 | 2013-11-26 | 3 | 3 | 2013-12-02 | NEAR side 04/12/2013/11/2013
| CMS-RE4-3-CERN-042 | 2013-08-01
20 | CMS-RE4-2-CERN-062 | 2013-08-26 | 2013-08-27 | 3 | 2013-11-13 | 1 | 2013-11-25 | 3 | 3 | 2013-12-02 | NEAR side 04/12/2013/11/2013
| CMS-RE4-3-CERN-043 | 2013-08-01
21 | CMS-RE4-2-CERN-057 | 2013-08-28 | 2013-08-28 | 3 | 2013-11-13 | 1 | 2013-11-26 | 3 | 3 | 2013-12-02 | NEAR side 04/12/2013/11/2013
| CMS-RE4-3-CERN-037 | 2013-08-28
22 | CMS-RE4-2-CERN-060 | 2013-09-03 | 2013-09-08 | 3 | 2013-10-07 | 3 | 2013-11-14 | 3 | 3 | 2013-11-18 | FAR side 22/11/2013 | 22/09/2014 SM return to 904 Overpressure of 5 bars
| CMS-RE4-3-CERN-033 | 2013-09-03
23 | CMS-RE4-2-CERN-067 | 2013-09-17 | 2013-09-18 | 3 | 2013-11-08 | 3 | 2013-11-14 | 3 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-Ghent-026 | 2013-08-28
24 | CMS-RE4-2-CERN-064 | 2013-09-17 | 2013-09-19 | 3 | 2013-11-08 | 3 | 2013-10-09 | 1 | 3 | 2013-11-18 | FAR side 22/11/2013 | 22/09/2014 SM return to 904 Overpressure of 5 bars
| CMS-RE4-3-Ghent-008 | 2013-08-28
25 | CMS-RE4-2-CERN-053 | 2013-09-19 | 2013-09-19 | 3 | 2013-11-08 | 1 | 2013-10-08 | 1 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-Ghent-046 | 2013-08-28
26 | CMS-RE4-2-CERN-063 | 2013-09-20 | 2013-09-20 | 3 | 2013-09-27 | 3 | 2013-10-11 | 1 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-Ghent-047 | 2013-08-28
27 | CMS-RE4-2-CERN-061 | 2013-09-23 | 2013-09-23 | 3 | 2013-11-08 | 3 | 2013-10-09 | 1 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-Ghent-044 | 2013-08-28
28 | CMS-RE4-2-CERN-073 | 2013-09-25 | 2013-09-25 | 3 | 2013-10-07 | 1 | 2013-10-07 | 3 |  | 2013-10-10 | trial 25/10/2013, NEAR side 04/12/2013
| CMS-RE4-3-Ghent-052 | 2013-09-24
29 | CMS-RE4-2-CERN-020 | 2013-09-25 | 2013-09-26 | 3 | 2013-10-07 | 1 | 2013-11-12 | 3 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-Ghent-048 | 2013-09-26
30 | CMS-RE4-2-CERN-051 | 2013-09-26 | 2013-10-18 | 3 | 2013-11-08 | 3 | 2013-11-15 | 3 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-Ghent-054 | 2013-09-26
31 | CMS-RE4-2-CERN-079 | 2013-10-21 | 2013-10-24 | 3 | 2013-10-05 | 1 | 2013-11-19 | 3 | 3 | 2013-12-04 | NEAR side 04/12/2013
| CMS-RE4-3-Ghent-045 | 2013-09-27
32 | CMS-RE4-2-CERN-069 | 2013-10-21 | 2013-10-26 | 3 | 2013-11-08 | 1 | 2013-11-19 | 3 | 3 | 2013-12-04 | NEAR side 04/12/2013
| CMS-RE4-3-Ghent-058 | 2013-10-24
33 | CMS-RE4-2-BARC-005 | 2013-11-04 | 2013-11-04 | 3 | 2013-11-08 | 3 | 2013-11-18 | 3 | 3 | 2013-11-18 | FAR side 22/11/2013
| CMS-RE4-3-CERN-071 | 2013-11-04
34 | CMS-RE4-2-BARC-024 | 2013-11-05 | 2013-11-05 | 3 | 2013-11-08 | 1 | 2013-11-19 | 3 | 3 | 2013-12-04 | NEAR side 04/12/2013
| CMS-RE4-3-CERN-077 | 2013-11-05
35 | CMS-RE4-2-CERN-068 | 2013-11-06 | 2013-11-07 | 3 | 2013-11-13 | 1 | 2013-11-25 | 3 | 3 | 2013-12-04 | NEAR side 04/12/2013
| CMS-RE4-3-Ghent-049 | 2013-11-06
36 | CMS-RE4-2-CERN-078 | 2013-11-13 | 2013-11-15 | 3 | 2013-11-28 | 1 | 2013-11-21 | 3 | 3 | 2013-12-04 | NEAR side 04/12/2013
| CMS-RE4-3-CERN-076 | 2013-11-13
37 | CMS-RE4-2-CERN-080 | 2013-11-13 | 2013-11-18 | 3 | 2013-11-18 | 1 | 2013-11-21 | 3 | 3 | 2013-12-04 | NEAR side 04/12/2013
| CMS-RE4-3-CERN-072 | 2013-11-13
51 | CMS-RE4-2-CERN-098 | 2014-03-10 | 2014-03-10 | 3 | 2014-03-14 | 3 | 2014-03-11 | 3 | 3 | 2014-03-14 | 10/04/2014 -trolley #4, 22/09/2014 - trolley # 1 | Chamber GHENT-108 TW High currents Chamber replaced by RE4_3_ CERN-154
| CMS-RE4-3-CERN-154 | 2014-03-10
75 | CMS-RE4-2-CERN-017 | 2014-04-25 | 2014-04-25 | 3 | 2014-05-16 | 3 | 2014-09-21 | 3 |  | 2014-09-22 | 22/09/2014 - trolley #1
| CMS-RE4-3-GHENT-114 | 2014-04-25
2nd Endcap
38 | CMS-RE4-2-CERN-075 | 2013-11-29 | 2014-01-31 | 3
| CMS-RE4-3-CERN-088 | 2014-01-30

## COMMENTS-RE4-3
Chamber ID | COMMENTS | CHECKS DONE
CMS-RE4-3-Ghent-003
CMS-RE4-3-Ghent-006
CMS-RE4-3-CERN-010 | I forgot to upload the files for the leak test
CMS-RE4-3-CERN-011
CMS-RE4-3-CERN-031 | Hardware thresholds board two too low ~200 -> Values Adjusted on 31/05 -- there is no excel file for the leak test!! | We fixed it ourselves (Guillaume)
CMS-RE4-3-CERN-027
CMS-RE4-3-CERN-028
CMS-RE4-3-CERN-034
CMS-RE4-3-CERN-029 | there is no excel file for the leak test!!
CMS-RE4-3-CERN-032
CMS-RE4-3-CERN-033 | Hardware thresholds board one too low ~161.Vth adjusted 03/09 Information for the HV scan is in the database, but it does not look to be there. Restarted monitoring on 05/07/2013
CMS-RE4-3-CERN-035 | Informationfor the HV scan is in the database, but it does not look to be there
CMS-RE4-3-CERN-036
CMS-RE4-3-CERN-037
CMS-RE4-3-CERN-039
CMS-RE4-3-CERN-038
CMS-RE4-3-CERN-040
CMS-RE4-3-CERN-025
CMS-RE4-3-CERN-041 | Hardware thresholds board one too low ~188
CMS-RE4-3-CERN-043
CMS-RE4-3-CERN-042
CMS-RE4-3-GENT-026
CMS-RE4-3-GENT-008 | adjust thresholds board2 ~200 done 19/09 now ok
CMS-RE4-3-GENT-044 | adjust thresholds board2 ~200, done 23/09 now ok
CMS-RE4-3-GENT-030 | Bottom current 0 confirmed ( swap cables, change module, cable -->Ibot=0)
CMS-RE4-3-GENT-046 | adjust thresholds board2 ~200, done 19/09 now ok
CMS-RE4-3-GENT-047 | adjust thresholds board2 ~200 :done
CMS-RE4-3-GENT-052 | All Hardware thresholds for all boards are too low ~205-210, 24/09 done
CMS-RE4-3-GENT-048 | adjust threshold VTH1 board1 ~259:DONE
CMS-RE4-3-GENT-054 | All Hardware thresholds for all boards are too low ~205-210:DONE : Brd2 There is a difference of +10 when comparing the thresholds from the voltimeter and the LabView interface. We set up the thresholds so the LabView interface give us 212.
CMS-RE4-3-GENT-049 | All Hardware thresholds for all boards are too low ~205-210, adjusted on 7 november 2013
CMS-RE4-3-GENT-045 | All Hardware thresholds for all boards are too low ~205-210:DONE : Brd2 There is a difference of +10 when comparing the thresholds from the voltimeter and the LabView interface. We set up the thresholds so the LabView interface give us 212.
CMS-RE4-3-GENT-058 | adjust thresholds board2 ~208, the digital value is a low DONE : Brd2 There is a difference of +7 when comparing the thresholds from the voltimeter and the LabView interface. We set up the thresholds so the LabView interface give us 208.
CMS-RE4-3-CERN-076
CMS-RE4-3-CERN-072
CMS-RE4-3-CERN-071
CMS-RE4-3-CERN-074 | Brd0:VTHall ~ 208, both gaps to be changed, current increase
CMS-RE4-3-CERN-077 | Brd2:VTH1:322, adjusted 05/11/2013
CMS-RE4-3-CERN-070 | Back to QC3 because of the Increasing current behaviour of the top layer
CMS-RE4-3-CERN-076 | All threshold have to be checked
CMS-RE4-3-CERN-072 | All threshold have to be checked, done 13/11

## COMMENTS-RE4-2
CHAMBER | COMMENTS | ACTIONS
CMS-RE4-2-CERN-017 | 08/20/2013 : Removed to QC3, tripolar problem, frequent trips , after change the 3 polar we get again one trip/4-5 days on the top gap--> 7/10/2013 ch goes back to QC3
CMS-RE4-2-CERN-012 | The current behavior was increasing, but we validated | Cahnge the HV channel, Pressure/Humidity/Temperture values
CMS-RE4-2-CERN-013
CMS-RE4-2-CERN-015 | there is no excel file for the leak test!!
CMS-RE4-2-CERN-016 | The HV test was not uploaded : The HV test does not have a value for 1000V, so it is not possible to submit the file to the database
CMS-RE4-2-CERN-018
CMS-RE4-2-CERN-014 | The data is in two files, so it has been downloaded to the database twice
CMS-RE4-2-BARC-023
CMS-RE4-2-BARC-019 | Sabino performed the leak test, and Guillaume got the excel files and uploaded the database. Checked.
CMS-RE4-2-BARC-021 | I forgot to upload the files in the leak test
CMS-RE4-2-BARC-024 | Bottom gap behaviour bad ,08/20/2013 : chamber moved to QC3 to change the bottom gap
CMS-RE4-2-BARC-009
CMS-RE4-2-BARC-022 | Hardware thresholds board one FEB 4 high ~227, fixed n 15/07/2013 in QC4
CMS-RE4-2-BARC-005 | 08/20/2013 :Removed to QC3 to change the HV connector
CMS-RE4-2-BARC-007 | I forgot to upload the files in the leak test
CMS-RE4-2-CERN-050 | Wrong PLW uploaded for the bottom gap
CMS-RE4-2-CERN-056 | LV test 1st try was not passed. Digital current to high above 930. Steffano is fixing it in QC4
CMS-RE4-2-CERN-055 | Wrong XLS uploaded for the bottom gap
CMS-RE4-2-CERN-059
CMS-RE4-2-CERN-060 | Hardware thresholds board two all FEB ~200 -- have been adjusted 03/09
CMS-RE4-2-CERN-057 | The connector for the electrical test is broken.Nevertheles, It is still possible to connect; Hardware thresholds board two all FEB =200 , Thresholds adjusted 28/08
CMS-RE4-2-CERN-065
CMS-RE4-2-CERN-062 | leak rate > 150% of the sum of bot TOPthe leak rates ) : new leak done no leak, loose connector behind the PP, now OK
#VALUE! | chamber leak > 150% of the Sum of the bot leak rate and Top leak rate
CMS-RE4-2-CERN-066 | Hardware thresholds board two all FEB ~200 --, thr adjusted again 21/10.2013
CMS-RE4-2-CERN-053 | VTH1 Board 0 = 220 to be adjusted done on the 19/9
CMS-RE4-2-CERN-061 | VTH4 Board 0 = 222 to be adjusted , 23/09 done
CMS-RE4-2-CERN-063 | VTH2 VTH4 of Board 1 =220 :done
CMS-RE4-2-CERN-064 | VTH2,VTH4 of Board 2 =220, VTH3,VTH4 of Board 0=220,VTH2 of Board 0=225 :DONE
CMS-RE4-2-CERN-068 | Stability test failed for the bottom Gap, I increase >> 50% -->17/09/2013:QC3 to replace the bottom gap :1/10 gap replaced
CMS-RE4-2-CERN-080 | Brd2-VTH1 : 259, Bdr2-VTH4:210 to be adjusted, 13//11 done
CMS-RE4-2-CERN-078 | Brd0-VTH1 : 225, Bdr2-VTH1:220 done 13/11
#VALUE! | Brd0-VTH1 : 308, VTH2:220, VTH3:220, VTH4:227, adjusted 29/11/2013

## COMMENTS SM
SM ID | Comments | Actions
2
3
4
5
6
7 | leakage was in the test system not in the chamber
8 | leakage was in the test system not in the chamber
9
10
11
12
13
14
15
16

## FINAL REPORT
| Week starting | RE4-2 ready | RE4-3 ready | Fridays | Column2 | Chambers RE4-2 ready per week | Chambers RE4-3 ready per week | Column3 | SM | Actual Assembly | SM tests | Modules Total | remaining RE4-2 | remaining RE4-3
|  | 0 | 0 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
2013-04-01 | Mon 01-Apr | 0 | 0 | 2013-04-05 | Fri 05-Apr | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2013-04-08 | Mon 08-Apr | 0 | 0 | 2013-04-12 | Fri 12-Apr | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2013-04-15 | Mon 15-Apr | 0 | 0 | 2013-04-19 | Fri 19-Apr | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2013-04-22 | Mon 22-Apr | 0 | 0 | 2013-04-26 | Fri 26-Apr | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2013-04-29 | Mon 29-Apr | 0 | 0 | 2013-05-03 | Fri 03-May | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2013-05-06 | Mon 06-May | 0 | 0 | 2013-05-10 | Fri 10-May | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2013-05-13 | Mon 13-May | 0 | 0 | 2013-05-17 | Fri 17-May | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2013-05-20 | Mon 20-May | 0 | 0 | 2013-05-24 | Fri 24-May | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2013-05-27 | Mon 27-May | 0 | 1 | 2013-05-31 | Fri 31-May | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 1
2013-06-03 | Mon 03-Jun | 6 | 2 | 2013-06-07 | Fri 07-Jun | 6 | 2 |  | 3 | 1 | 0 | 3 | 3 | 0
2013-06-10 | Mon 10-Jun | 0 | 0 | 2013-06-14 | Fri 14-Jun | 0 | 0 |  | 0 | 2 | 0 | 3 | 3 | 0
2013-06-17 | Mon 17-Jun | 0 | 5 | 2013-06-21 | Fri 21-Jun | 0 | 5 |  | 3 | 3 | 0 | 6 | 0 | 2
2013-06-24 | Mon 24-Jun | 0 | 0 | 2013-06-28 | Fri 28-Jun | 0 | 0 |  | 0 | 0 | 0 | 6 | 0 | 2
2013-07-01 | Mon 01-Jul | 2 | 2 | 2013-07-05 | Fri 05-Jul | 2 | 0 |  | 2 | 2 | 0 | 8 | 0 | 0
2013-07-08 | Mon 08-Jul | 1 | 0 | 2013-07-12 | Fri 12-Jul | 1 | 2 |  | 1 | 1 | 0 | 9 | 0 | 1
2013-07-15 | Mon 15-Jul | 2 | 2 | 2013-07-19 | Fri 19-Jul | 2 | 1 |  | 2 | 2 | 0 | 11 | 0 | 0
2013-07-22 | Mon 22-Jul | 0 | 0 | 2013-07-26 | Fri 26-Jul | 0 | 1 |  | 0 | 0 | 0 | 11 | 0 | 1
2013-07-29 | Mon 29-Jul | 3 | 6 | 2013-08-02 | Fri 02-Aug | 3 | 6 |  | 3 | 3 | 0 | 14 | 0 | 4
2013-08-05 | Mon 05-Aug | 0 | 3 | 2013-08-09 | Fri 09-Aug | 0 | 3 |  | 0 | 0 | 0 | 14 | 0 | 7
2013-08-12 | Mon 12-Aug | 0 | 0 | 2013-08-16 | Fri 16-Aug | 0 | 0 |  | 0 | 0 | 0 | 14 | 0 | 7
2013-08-19 | Mon 19-Aug | 2 | 2 | 2013-08-23 | Fri 23-Aug | 1 | 2 |  | 1 | 2 | 0 | 15 | 0 | 8
2013-08-26 | Mon 26-Aug | 3 | 2 | 2013-08-30 | Fri 30-Aug | 4 | 2 |  | 4 | 3 | 0 | 19 | 0 | 6
2013-09-02 | Mon 02-Sep | 1 | 1 | 2013-09-06 | Fri 06-Sep | 1 | 1 |  | 1 | 1 | 0 | 20 | 0 | 6
2013-09-09 | Mon 09-Sep | 0 | 0 | 2013-09-13 | Fri 13-Sep | 0 | 0 |  | 0 | 0 | 0 | 20 | 0 | 6
2013-09-16 | Mon 16-Sep | 4 | 0 | 2013-09-20 | Fri 20-Sep | 3 | 0 |  | 3 | 4 | 0 | 23 | 0 | 3
2013-09-23 | Mon 23-Sep | 4 | 4 | 2013-09-27 | Fri 27-Sep | 5 | 4 |  | 5 | 3 | 0 | 28 | 0 | 2
2013-09-30 | Mon 30-Sep | 0 | 0 | 2013-10-04 | Fri 04-Oct | 0 | 0 |  | 0 | 0 | 6 | 28 | 0 | 2
2013-10-07 | Mon 07-Oct | 0 | 0 | 2013-10-11 | Fri 11-Oct | 0 | 0 |  | 0 | 0 | 8 | 28 | 0 | 2
2013-10-14 | Mon 14-Oct | 1 | 1 | 2013-10-18 | Fri 18-Oct | 1 | 1 |  | 1 | 1 | 0 | 29 | 0 | 2
2013-10-21 | Mon 21-Oct | 2 | 0 | 2013-10-25 | Fri 25-Oct | 2 | 0 |  | 2 | 3 | 1 | 31 | 0 | 0
2013-10-28 | Mon 28-Oct | 4 | 1 | 2013-11-01 | Fri 01-Nov | 0 | 0 |  | 0 | 0 | 0 | 31 | 0 | 0
2013-11-04 | Mon 04-Nov | 1 | 4 | 2013-11-08 | Fri 08-Nov | 5 | 5 |  | 5 | 3 | 1 | 36 | 0 | 0
2013-11-11 | Mon 11-Nov | 0 | 2 | 2013-11-15 | Fri 15-Nov | 0 | 2 |  | 0 | 1 | 7 | 36 | 0 | 2
2013-11-18 | Mon 18-Nov | 0 | 0 | 2013-11-22 | Fri 22-Nov | 0 | 0 |  | 0 | 36 | 7 | 36 | 0 | 2
2013-11-25 | Mon 18-Nov | 0 | 0 | 2013-11-22 | Fri 22-Nov | 0 | 0 |  | 0 | -35 | 6 | 36 | 0 | 2
2013-12-02 | Mon 25-Nov | 0 | 0 | 2013-11-29 | Fri 29-Nov | 0 | 0 |  | 0 | 0 | -36 | 36 | 0 | 2
Formulas:
Fridays = [Fridays, row above]+7

## REPORT
| Week starting | RE4-2 ready | RE4-3 ready | Fridays | Column2 | Chambers RE4-2 ready per week | Chambers RE4-3 ready per week | Column3 | SM | Modules Total | remaining RE4-2 | remaining RE4-3 | TEAM
|  | 36 | 38 | [5 empty] | 0 | 0 | 0 | 0
2026-07-27 | Mon 27-Jul | 0 | 0 | 2026-07-31 | Fri 31-Jul | 36 | 38 |  | 36 | 36 | 0 | 2
2026-08-03 | Mon 03-Aug | 0 | 0 | 2026-08-07 | Fri 07-Aug | 0 | 0 |  | 0 | 36 | 0 | 2
2026-08-10 | Mon 10-Aug | 0 | 0 | 2026-08-14 | Fri 14-Aug | 0 | 0 |  | 0 | 36 | 0 | 2 | Plamen-Alexander
2026-08-17 | Mon 17-Aug | 0 | 0 | 2026-08-21 | Fri 21-Aug | 0 | 0 |  | 0 | 36 | 0 | 2 | Plamen-Alexander
2026-08-24 | Mon 24-Aug | 0 | 0 | 2026-08-28 | Fri 28-Aug | 0 | 0 |  | 0 | 36 | 0 | 2 | Plamen-Alexander
2026-08-31 | Mon 31-Aug | 0 | 0 | 2026-09-04 | Fri 04-Sep | 0 | 0 |  | 0 | 36 | 0 | 2 | Plamen-Iury
2026-09-07 | Mon 07-Sep | 0 | 0 | 2026-09-11 | Fri 11-Sep | 0 | 0 |  | 0 | 36 | 0 | 2 | Iury
2026-09-14 | Mon 14-Sep | 0 | 0 | 2026-09-18 | Fri 18-Sep | 0 | 0 |  | 0 | 36 | 0 | 2 | Iury
2026-09-21 | Mon 21-Sep | 0 | 0 | 2026-09-25 | Fri 25-Sep | 0 | 0 |  | 0 | 36 | 0 | 2 | Iury
2026-09-28 | Mon 28-Sep | 0 | 0 | 2026-10-02 | Fri 02-Oct | 0 | 0 |  | 0 | 36 | 0 | 2 | Iury
2026-10-05 | Mon 05-Oct | 0 | 0 | 2026-10-09 | Fri 09-Oct | 0 | 0 |  | 0 | 36 | 0 | 2
2026-10-12 | Mon 12-Oct | 0 | 0 | 2026-10-16 | Fri 16-Oct | 0 | 0 |  | 0 | 36 | 0 | 2
2026-10-19 | Mon 19-Oct | 0 | 0 | 2026-10-23 | Fri 23-Oct | 0 | 0 |  | 0 | 36 | 0 | 2
2026-10-26 | Mon 26-Oct | 0 | 0 | 2026-10-30 | Fri 30-Oct | 0 | 0 |  | 0 | 36 | 0 | 2
2026-11-02 | Mon 02-Nov | 0 | 0 | 2026-11-06 | Fri 06-Nov | 0 | 0 |  | 0 | 36 | 0 | 2
2026-11-09 | Mon 09-Nov | 0 | 0 | 2026-11-13 | Fri 13-Nov | 0 | 0 |  | 0 | 36 | 0 | 2
2026-11-16 | Mon 16-Nov | 0 | 0 | 2026-11-20 | Fri 20-Nov | 0 | 0 |  | 0 | 36 | 0 | 2
2026-11-23 | Mon 23-Nov | 0 | 0 | 2026-11-27 | Fri 27-Nov | 0 | 0 |  | 0 | 36 | 0 | 2
2026-11-30 | Mon 30-Nov | 0 | 0 | 2026-12-04 | Fri 04-Dec | 0 | 0 |  | 0 | 36 | 0 | 2
2026-12-07 | Mon 07-Dec | -36 | -38 | 2026-12-11 | Fri 11-Dec | 0 | 0 |  | 0 | 36 | 0 | 2
| Mon 02-Nov | 36 | 38 | 2026-11-06 | Fri 06-Nov | 0 | 0 |  | 0 |  | 0 | 2
| Mon 09-Nov | 0 | 0 | 2026-11-13 | Fri 13-Nov | 0 | 0 |  | 0 |  | 0 | 2
| Mon 16-Nov | 0 | 0 | 2026-11-20 | Fri 20-Nov | 0 | 0 |  | 0 |  | 0 | 2
| Mon 23-Nov | 0 | 0 | 2026-11-27 | Fri 27-Nov | 0 | 0 |  | 0 |  | 0 | 2
| Mon 30-Nov | 0 | 0 | 2026-12-04 | Fri 04-Dec | 0 | 0 |  | 0 |  | 0 | 2
| Mon 07-Dec |  |  | 2026-12-11 | Fri 11-Dec | 0 | 0 |  | 0 |  | 0 | 2
Formulas:
Fridays = [Fridays, row above]+7

## REPORT-GRAPHS
| Expected RE4-2 | Received RE4-2 | Expecting | Under Test | Delivered
| 38 | 37 | 1 | 1 | 36
| Expected RE4-3 | Received | Expecting | Under Test | Delivered
| 38 | 39 | -1 | 1 | 38
| Expected SM | Delivered | To be delivered
| 38 | 36 | 2
RECEIVED | DELIVERED | UNDER TEST | EXPECTING |  | RECEIVED | DELIVERED | UNDER TEST | EXPECTING | DELIVERED | TO BE DELIVERED
37 | 36 | 1 | 1 |  | 39 | 38 | 1 | -1 | 36 | 2

## BackFromPoint5
SM | Chamber ID | QC4 arrival | Status | Coonectivity | commentss | Status | Electric test | AC PS | DC PS | FEBs | Status | Gas CH | Starting | HV scan | Status | Stability start | Stability test time [days] | Stability end | Status
8 | CMS-RE4-2-CERN-012 | 2013-11-14 |  | 2013-11-15 | ok |  | 2013-11-15 | 0.357 | 0.704 | 0.350/0.704 All Brds higher than 230==>adjusted |  | 12 | 2013-11-19 12:37 |  | 3/18, 12-4,21 Imon bot =0 !! | 2013-11-20 15:05
|  | 2013-11-14 |  | 2013-11-15 | ok |  | 2013-11-15 | 0.357 | 0.795 | [5 empty] | pino-4,4-2,8 | 2013-11-20 15:05
10 | CMS-RE4-2-BARC-007 | 2013-11-14 |  | 2013-11-15 | ok |  | 2013-11-15 | 0.358 | 0.802 |  |  | CAN2 | 2013-11-19 12:37 |  | 26/25,2-4,6 | 2013-11-20 15:05
| CMS-RE4-3-CERN-034 | 2013-11-14 |  | 2013-11-15 | ok |  | 2013-11-15 | 0.354 | 0.796 | Brd2: VTH3 220==>adjusted |  |  |  |  | pino-13,2-2,5 | 2013-11-20 15:05
28 | CMS-RE4-2-CERN-073 | 2013-11-14 |  | 2013-11-15 | C1 -15&16, repaired |  | 2013-11-19 | 0.357 | 0.801 |  |  | 14 | 2013-11-19 12:37 |  | 2/18,14-0,22 | 2013-11-20 15:05
| CMS-RE4-3-Ghent-052 | 2013-11-14 |  | 2013-11-15 | ok |  | 2013-11-19 | 0.362 | 0.811 | [5 empty] | pino-3, 4-4,9 | 2013-11-20 15:05
4 | CMS-RE4-2-CERN-018 | 2013-11-14 |  | 2013-11-19 | conector C2-1 dead, cable to be changed?, repareid |  | 2013-11-15 | 0.358 | 0.795 | Brd2: VTH2 210,VTH2 210, VTH 3 210==>adjusted |  | CAN1 | 2013-11-19 12:37 |  | pino-8, 12-0,19, Imon bot =0 !! | 2013-11-20 15:05
| CMS-RE4-3-CERN-010 | 2013-11-14 |  | 2013-11-19 | ok |  | 2013-11-15 | 0.364 | 0.808 | [5 empty] | 43/14, 10-4,18 | 2013-11-20 15:05
15 | CMS-RE4-2-CERN-055 | 2013-11-14 |  | 2013-11-15 | ok |  | 2013-11-15 | 0.36 | 0.802 |  |  | 15 | 2013-11-19 12:37 |  | 25/25, 4-0, 7 | 2013-11-20 15:05
| CMS-RE4-3-CERN-038 | 2013-11-14 |  | 2013-11-15 | ok |  | 2013-11-15 | 0.361 | 0.81 | Brd1 : VTH2 220==>adjusted |  |  |  |  | pino-1,0-4,3 | 2013-11-20 15:05
16 | CMS-RE4-2-CERN-056 | 2013-11-14 |  | 2013-11-15 | ok |  | 2013-11-19 | 0.361 | 0.804 |  |  | CAN3 | 2013-11-19 12:37 |  | pino-7,12-2,20 | 2013-11-20 15:05
| CMS-RE4-3-CERN-040 | 2013-11-14 |  | 2013-11-15 | ok |  | 2013-11-19 | 0.356 | 0.813 | Brd1: VTH3 225==>adjusted |  |  |  |  | 29/15,10-2,17 | 2013-11-20 15:05
3 x new feb = 0.8
3 x old feb = 0.7
11 | CMS-RE4-3-CERN-032 |  |  | 2013-11-21 | ok |  | 2013-11-21 | 0.399 | 0.848
| CMS-RE4-2-BARC-021 |  |  | 2013-11-21 | OK |  | 2013-11-21 | 0.397 | 0.839
3 | CMS-RE4-3-GHENT-006 |  |  | 2013-11-21 | ok |  | 2013-11-21 | 0.395 | 0.703
| CMS-RE4-2-CERN-013 |  |  | 2013-11-21 | OK |  | 2013-11-21 | 0.401 | 0.712
12 | CMS-RE4-3-CERN-035 |  |  | 2013-11-21 | OK |  | 2013-11-21 | 0.399 | 0.851
| CMS-RE4-2-BARC-022 |  |  | 2013-11-21 | OK |  | 2013-11-21 | 0.403 | 0.857
13 | CMS-RE4-3-CERN-039 |  |  | 2013-11-21 | OK |  | 2013-11-21 | 0.4 | 0.855
CMS-RE4-2-CERN-0
CMS-RE4-2-CERN-0
CMS-RE4-3-CERN-0
CMS-RE4-2-CERN-0
CMS-RE4-3-CERN-0