## Chamber RE4-2
| Chamber ID | Expected arrival | QC4 arrival | Status | Coonectivity | Status | Electric test | Status | HV scan | Status | Stability start | Stability test time [days] |  | Stability end | Status | Removed | Leak test | Status | DB updated | Back to QC3 | Back to QC4 | SM delivery | SM ID
SPARES TYPE 2
1 | CMS-RE4-2-CERN-098 |  | 2014-02-18 | 3 | 2014-02-18 | 3 | 2014-02-18 | 3 | 2014-02-24 | 3 | 2014-02-24 14:24 | 13.79 | 436.4 | 2014-03-10 09:22 | 1900-01-02 |  | 2014-02-20 | 3 | 1900-01-02 |  |  | 2014-03-11 | 51
2 | CMS-RE4-2-CERN-017 | 2014-04-14 | 2014-04-15 | 1900-02-01 | 2014-04-15 | 1900-02-01 | 2014-04-15 | 3 | 2013-04-29 | 1900-01-02 | 2014-04-19 | 10 |  | 2014-04-29 | 1900-01-02 |  | 2014-04-15 | 1900-01-02 | 1900-01-02 |  | 2014-04-15 | 2014-04-25 | 75
3 | CMS-RE4-2-BARC-155 |  | 2014-05-26 | 1900-02-01 | 2014-10-27 | 3 | 2014-09-23 | 3 | 2014-09-26 | 3 | 2014-10-28 | 13 |  | 2014-11-10 | 3 |  | 2014-05-28 | 1900-01-02 | 1900-01-02 |  |  | 2015-01-25 | 24
4 | CMS-RE4-2-BARC-156 |  | 2014-05-26 | 1900-02-01 | 2014-09-30 | 1900-02-01 | 2014-09-23 | 3 | 2014-09-25 | 1900-01-02 | 2014-10-28 | 13 |  | 2014-11-10 | 1900-01-02 |  | 2014-05-28 | 1900-01-02 | 1900-01-02 |  |  | 2015-01-25 | 76
5 | CMS-RE4-2-BARC-157 |  | 2014-05-26 | 1900-02-01 | 2014-10-27 | 3 | 2014-09-23 | 3 | 2014-09-25 | 3 | 2014-10-28 | 13 |  | 2014-11-10 | 3 |  | 2014-05-27 | 1900-01-02 | 1900-01-02 |  |  | 2015-01-25 | 79
6 | CMS-RE4-2-BARC-158 |  | 2014-05-26 | 1900-02-01 | 2014-09-30 | 3 | 2014-09-23 | 3 | 2014-09-25 | 1900-01-02 | 2014-10-28 | 13 |  | 2014-11-10 | 1900-01-02 |  | 2014-05-28 | 1900-01-02 | 1900-01-02 |  |  | 2015-01-25 | 22
7 | CMS-RE4-2-BARC-159 |  | 2014-05-26 | 1900-02-01 | 2014-09-30 | 1900-02-01 | 2014-09-23 | 3 | 2014-09-25 | 1900-01-02 | 2014-10-28 | 13 |  | 2014-11-10 | 1900-01-02 |  | 2014-05-28 | 1900-01-02 | 1900-01-02 |  |  | 2015-01-25 | 78
8 | CMS-RE4-2-BARC-161 |  | 2014-05-26 | [13 empty] | 2014-05-27 | 1900-01-02 | [5 empty] | GIF(old)
9 | CMS-RE4-2-PANJAB-BARC-162 |  | 2014-06-02 | 1900-02-01 | 2014-10-27 | 3 | 2014-09-23 | 2 | 2014-09-26 | 3 | 2014-10-28 | 13 |  | 2014-11-10 | 3 |  | 2014-06-03 | 1900-01-02 | 1900-01-02 |  |  | 2015-01-25 | 77
10 | CMS-RE4-2-PANJAB-BARC-163 |  | 2014-06-02 | 1900-02-01 | 2014-10-27 | 3 | 2014-09-23 | 3 | 2014-09-26 | 1900-01-02 | 2014-10-28 | 13 |  | 2014-11-10 | 1900-01-02 |  | 2014-06-03 | 1900-01-02 | 1900-01-02 |  |  | SPARE
11 | CMS-RE4-2-PANJAB-BARC-164 |  | 2014-06-02 | 1900-02-01 | 2014-10-27 | 1900-02-01 | 2014-09-23 | 3 | 2014-09-25 | 1900-01-02 | 2014-10-28 | 13 |  | 2014-11-10 | 1900-01-02 |  | 2014-06-03 | 1900-01-02 | 1900-01-02 |  |  | SPARE
12 | CMS-RE4-2-CERN-165 |  | 2014-11-30 | 1900-02-01 | 2014-11-09 | 1900-02-01 | 2014-11-09 | 1900-02-01 | 2014-01-20 | 1900-01-02 | 2015-01-20 |  |  | 2015-02-11 | 1900-01-02 |  | 2014-12-08 | 1900-01-02 | 1900-01-02 |  |  |  |  | GIF++ ( ghent)
13 | CMS-RE4-2-CERN-170 |  | 2014-11-30 | 1900-02-01 | 2014-11-09 | 1900-02-01 | 2014-11-09 | 1900-02-01 | 2014-01-20 | 1900-01-02 | 2015-02-07 |  |  | 2015-02-27 | 1900-01-02 |  | 2014-12-08 | 1900-01-02 | 1900-01-02 |  |  | SPARE
14 | CMS-RE4-2-CERN-168 |  | 2014-11-30 | 1900-02-01 | 2014-11-09 | 1900-02-01 | 2014-11-09 | 1900-02-01 | 2014-01-20 | 1900-01-02 | 2015-01-20 |  |  | 2015-02-11 | 1900-01-02 |  | 2014-12-09 | 1900-01-02 | 1900-01-02 |  |  | SPARE
15 | CMS-RE4-2-CERN-166 |  | 2014-11-30 | 1900-02-01 | 2014-11-09 | 1900-02-01 | 2014-11-09 | 1900-02-01 | 2014-01-20 | 1900-01-02 | 2015-01-20 |  |  | 2015-02-11 | 1900-01-02 |  | 2014-12-09 | 1900-01-02 | 1900-01-02 |  |  |  |  | GIF++(ghent)
16 | CMS-RE4-2-CERN-167 |  | 2014-02-10 |  | 2015-02-06 | 1900-02-01 | 2015-02-06 | 1900-02-01 | 2015-02-16 | 1900-01-02 | 2015-02-17 |  |  | 2015-02-27 | 1900-01-02 |  | 2015-02-14 | 1900-01-02 | 1900-01-02 |  |  | SPARE
17 | CMS-RE4-2-CERN-169 |  | 2014-02-10 |  | 2015-02-06 | 1900-02-01 | 2015-02-06 | 1900-02-01 | 2015-02-16 | 1900-01-02 | 2015-02-17 |  |  | 2015-02-27 | 1900-01-02 |  | 2015-02-14 | 1900-01-02 | 1900-01-02 |  |  | SPARE
CERN
INDIA
Formulas:
Stability start = [QC4 arrival]+6.6
Stability end = [Stability start]+[Stability test time [days]]

## Chamber RE4-3
| Chamber ID | Expected arrival | QC4 arrival | Back From Retrofitted/Connector | Connectivity | Status | Electric test | Status | HV scan | Status | Stability start | Stability test time [days] |  | Stability end | Status | Removed | Leak test | Status | DB updated | Back to QC3 | Back to QC4 | SM delivery | SM ID
SPARES TYPE 3
1 | CMS-RE4-3-GENT-108 |  | 2014-01-27 |  | 2014-02-13 | 1900-01-02 | 2014-02-13 | 1900-01-02 | 2015-02-04 | 1900-01-02 | 2015-02-18 16:00 | 19.95 | -77.3333 | 2015-02-27 | 3 |  | 2014-02-14 | 1900-01-02 | 3 | 2014-06-02 |  | SPARE | 51
2 | CMS-RE4-3-GENT-114 | 2014-02-24 | 2014-02-20 |  | 2014-02-24 | 1900-01-02 | 2014-02-24 | 1900-01-02 | 2014-02-27 | 1900-01-02 | 2014-03-03 | 50 | -430 | 2014-04-24 | 3 |  | 2014-02-24 | 1900-01-02 | 3 |  |  | 2014-04-25 | 75
3 | CMS-RE4-3-CERN-154 | 2014-04-18 | 2014-04-18 |  | 2014-04-18 | 1900-01-02 | 2014-04-18 | 1900-01-02 | 2014-04-24 | 1900-01-02 | 25/04/2014 11;15 | 19 |  | 2014-05-14 | 3 |  | 2014-04-18 | 1900-01-02 | 3 |  |  | 2014-09-22 | 51
4 | CMS-RE4-3-CERN-160 | 2014-04-18 | 2014-04-18 |  | 2014-04-18 | 1900-01-02 | 2014-04-18 | 1900-01-02 | 2014-10-30 | 1900-01-02 | 2014-04-22 | 10 |  | 2014-05-02 | 3 |  | 2014-04-22 | 1900-01-02 | 3 |  |  | 2015-01-30 | 76
5 | CMS-RE4-3-CERN-153 | 2014-04-18 | 2014-04-18 |  | 2014-04-18 | 1900-01-02 | 2014-04-18 | 1900-01-02 | 2014-04-24 | 1900-01-02 | 25/04/2014 11;15 | 19 |  | 2014-05-14 | 3 |  | 2014-04-18 | 1900-01-02 | 3 |  |  | 2015-01-30 | 77
6 | CMS-RE4-3-CERN-004 | 2014-04-18 | 2014-04-18 |  | 2014-04-18 | 1900-01-02 | 2014-04-18 | 1900-01-02 | [8 empty] | 2014-04-18 | 1900-01-02 |  | 2014-09-10 |  | 2014-04-18 | GIF | HOSPITAL
7 | CMS-RE4-3-CERN-174 |  | 2014-12-02 |  | 2014-12-03 | 1900-01-02 | 2014-12-03 | 1900-01-02 | 2015-02-04 | 1900-01-02 | 2015-02-02 |  |  | 2015-02-26 | 3 |  | 2014-12-03 | 1900-01-02 | 3 |  |  | SPARE
8 | CMS-RE4-3-CERN-175 |  | 2014-12-02 |  | 2014-12-03 | 1900-01-02 | 2014-12-03 | 1900-01-02 | 2014-01-20 | 1900-01-02 | 2015-01-28 |  |  | 2015-02-05 | 3 |  | 2014-12-03 | 1900-01-02 | 3 |  |  | 2015-01-30 | 24
9 | CMS-RE4-3-CERN-176 |  | 2014-12-02 |  | 2014-12-03 | 1900-01-02 | 2014-12-03 | 1900-01-02 | 2015-02-04 | 1900-01-02 | 2015-02-04 16:00 |  |  | 20/20/2015 | 3 |  | 2014-12-03 | 1900-01-02 | 3 |  |  | SPARE
10 | CMS-RE4-3-CERN-178 |  | 2014-12-02 |  | 2014-12-03 | 1900-01-02 | 2014-12-03 | 1900-01-02 | 2014-01-20 | 1900-01-02 | 2015-01-20 15:45 | 11 |  | 2015-02-04 | 3 |  | 2014-12-03 | 1900-01-02 | 3 |  |  | 2015-01-30 | 78
11 | CMS-RE4-3-GENT-171 |  | 2014-12-02 |  | 2014-12-03 | 1900-01-02 | 2014-12-03 | 1900-01-02 | 2014-12-15 | 1900-01-02 | 2015-01-20 15:45 |  |  | 2015-02-11 | 3 |  | 2014-12-13 | 1900-01-02 | 3 |  |  | SPARE
12 | CMS-RE4-3-GENT-172 |  | 2014-12-02 |  | 2014-12-03 | 1900-01-02 | 2014-12-03 | 1900-01-02 | 2014-12-15 | 1900-01-02 | 2015-02-09 21:15 |  |  | 2015-02-27 | 3 |  | 2014-12-13 | 1900-01-02 | 3 |  |  | SPARE
13 | CMS-RE4-3-GENT-173 |  | 2014-12-02 |  | 2014-12-03 | 1900-01-02 | 2014-12-03 | 1900-01-02 | 2014-12-15 | 1900-01-02 | 2015-01-20 15:45 |  |  | 2015-02-20 | 3 |  | 2014-12-13 | 1900-01-02 | 3 |  |  | SPARE
14 | CMS-RE4-3-GENT-177 |  | 2014-12-02 |  | 2014-12-03 | 1900-01-02 | 2014-12-03 | 1900-01-02 | 2014-12-15 | 1900-01-02 | 2015-01-20 15:45 | 16 |  | 2015-02-05 15:45 | 3 |  | 2014-12-13 | 1900-01-02 | 3 |  |  | 2015-01-30 | 79
15 | CMS-RE4-3-GENT-150 |  | 2014-12-02 |  | 2014-12-03 | 1900-01-02 | 2014-12-03 | 1900-01-02 | 2014-12-15 | 1900-01-02 | 2015-01-20 15:45 | 13 |  | 2015-02-02 15:45 | 3 |  | 2014-12-13 | 1900-01-02 | 3 |  |  | 2015-01-30 | 22
16 | CMS-RE4-3-GENT-183 |  | 2015-02-27 |  | 2015-03-18 | 1900-01-02 | 2015-03-18 | 1900-01-02 | 2015-03-13 | 1900-01-02 | 2015-03-19 |  |  | 2015-04-03 |  |  | 2015-03-18 | 1900-01-02 | 3 |  |  | SPARE
17 | CMS-RE4-3-GENT-179 |  | 2015-02-27
18 | CMS-RE4-3-GENT-180 |  | 2015-02-27
19 | CMS-RE4-3-GENT-184 |  | 2015-02-27
GENT
CERN
|  |  | Expected Arrival | [10 empty] | Expected Delivery
| DELAY RESPECT TO THE CALENDAR |  | DAYS
Formulas:
Stability start = [QC4 arrival]+11
Stability end = [Stability start]+[Stability test time [days]]

## SMs
SM ID | chambers | HV cable offset (mm +-1) | Reception date | SM assembled | Status | Gas leak test | Status | Cooling test | Status | DB Updated | Stored to the rack for P5 | Shipment Date to P5 | Shipment Date to 904 | Comment
2nd Endcap
51 | CMS-RE4-2-CERN-098 | 5 | 2014-03-10 | 2014-03-10 | 3 | 2014-03-14 | 3 | 2014-03-11 | 3 | 3 | 2014-03-14 | 10/04/2014 -trolley #4, 22/09/2014 - trolley # 1 | 2014-05-20 | Chamber GHENT-108 TW High currents Chamber replaced by RE4_3_ CERN-154
| CMS-RE4-3-GENT-108 | 7 | 2014-03-10
22 | CMS-RE4-2-BARC-158 |  | 2015-01-30 | 2015-02-04 | 3 | 2015-02-12 | 3 | 2015-02-04 | 3 | 3 |  |  | 22/09/2014 : Returned from P5 overpressure 5 bars both chambers have been replaced
| CMS-RE4-3-GHENT-150 |  | 2015-01-30
24 | CMS-RE4-2-BARC-155 |  | 2015-01-30 | 2015-02-05 | 3 | 2015-02-11 | 3 | 2015-02-05 | 3 | 3 |  |  | 22/09/2014 : Returned from P5 overpressure 5 bars both chambers have been replaced
| CMS-RE4-3-CERN-175 |  | 2015-01-30
75 | CMS-RE4-2-CERN-017 |  | 2015-04-25 | 2015-04-25 | 3 | 2014-05-16 | 3 | 2014-09-21 | 3 | 3 |  | 22/09/2014 - trolley #1
| CMS-RE4-3-GHENT-114 |  | 25-avr.
76 | CMS-RE4-2-BARC-156 |  | 2015-01-30 | 2015-01-30 | 3 | 2015-02-11 | 3 | 2015-02-17 | 3 | 3
| CMS-RE4-3-CERN-160 |  | 2015-01-30
77 | CMS-RE4-2-BARC-162 |  | 2015-01-30 | 2015-02-02 | 3 | 2015-02-12 | 3 | 2015-02-02 | 3 | 3
| CMS-RE4-3-CERN-153 |  | 2015-01-30
78 | CMS-RE4-2-BARC-159 |  | 2015-01-30 | 2015-02-03 | 3 | 2015-02-12 | 3 | 2015-02-03 | 3 | 3
| CMS-RE4-3-CERN-178 |  | 2015-01-30
79 | CMS-RE4-2-BARC-157 |  | 2015-01-30 | 2015-02-06 | 3 | 2015-02-12 | 3 | 2015-02-06 | 3 | 3
| CMS-RE4-3-GHENT-177 |  | 2015-01-30

## COMMENTS-RE4-3
Chamber ID | COMMENTS | CHECKS DONE
CMS-RE4-3-GENT-108 | During Commissionning TW gap trip, 2 holes on insulation plastic foil located on top of the HV pad of TW, see report TC meeting of 2/06/14, Cu foil changed, TW gap also changed oold : KODEL-CMS-RE4-3-TW069 replaced by : KODEL-CMS-RE4-3-TW087
CMS-RE4-3-CERN-004 | Chamber run in the GIF without gas but with HV at 9.5 KV with source ON for two weeks, increase of the currents

## COMMENTS-RE4-2
CHAMBER | COMMENTS | ACTIONS
CMS-RE4-2-CERN-098
CMS-RE4-2-CERN-017
CMS-RE4-2-BARC-155
CMS-RE4-2-BARC-156
CMS-RE4-2-BARC-157
CMS-RE4-2-BARC-158
CMS-RE4-2-BARC-159
CMS-RE4-2-BARC-161
CMS-RE4-2-PANJAB-BARC-162 | check Brd1, VHT4 high 227
CMS-RE4-2-PANJAB-BARC-163
CMS-RE4-2-PANJAB-BARC-164

## COMMENTS SM
SM ID | Comments | Actions

## REPORT
| Week starting | RE4-2 ready | RE4-3 ready | Fridays | Friday day | Chambers RE4-2 ready per week | Chambers RE4-3 ready per week | Under Test RE4-3 | Under Test RE4-2 | Under Test | SM | Modules Total | remaining RE4-2 | remaining RE4-3 | SM TEAM | QC4 TEAM
|  | 16 | 14 | [6 empty] | 0 | 0
2015-04-27 | Mon 27-Apr | 0 | 0 | 2015-05-01 | Fri 01-May | 16 | 14 | 5 | 1 | 6 | 14 | 14 | 2 | 0
2015-05-04 | Mon 04-May | 0 | 0 | 2015-05-08 | Fri 08-May | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-05-11 | Mon 11-May | 0 | 0 | 2015-05-15 | Fri 15-May | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-05-18 | Mon 18-May | 0 | 0 | 2015-05-22 | Fri 22-May | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-05-25 | Mon 25-May | 0 | 0 | 2015-05-29 | Fri 29-May | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-06-01 | Mon 01-Jun | 0 | 0 | 2015-06-05 | Fri 05-Jun | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-06-08 | Mon 08-Jun | 0 | 0 | 2015-06-12 | Fri 12-Jun | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-06-15 | Mon 15-Jun | 0 | 0 | 2015-06-19 | Fri 19-Jun | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-06-22 | Mon 22-Jun | 0 | 0 | 2015-06-26 | Fri 26-Jun | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-06-29 | Mon 29-Jun | 0 | 0 | 2015-07-03 | Fri 03-Jul | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-07-06 | Mon 06-Jul | 0 | 0 | 2015-07-10 | Fri 10-Jul | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-07-13 | Mon 13-Jul | 0 | 0 | 2015-07-17 | Fri 17-Jul | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-07-20 | Mon 20-Jul | 0 | 0 | 2015-07-24 | Fri 24-Jul | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-07-27 | Mon 27-Jul | 0 | 0 | 2015-07-31 | Fri 31-Jul | 0 | 0 | 5 | 1 | 6 | 0 | 14 | 2 | 0 | #N/A | #N/A
2015-08-03 | Mon 03-Aug | 0 | 0 | 2015-08-07 | Fri 07-Aug | 0 | 0 | 17 | 1 | 18 | 0 | 14 | 2 | 0 | #N/A
2015-08-10 | Mon 10-Aug | 0 | 0 | 2015-08-14 | Fri 14-Aug | 0 | 0 | 17 | 1 | 18 | 0 | 14 | 2 | 0 | #N/A
2015-08-17 | Mon 17-Aug | 0 | 0 | 2015-08-21 | Fri 21-Aug | 0 | 0 | 17 | 1 | 18 | 0 | 14 | 2 | 0 | #N/A
2015-08-24 | Mon 24-Aug | 0 | 0 | 2015-08-28 | Fri 28-Aug | 0 | 0 | 17 | 1 | 18 | 0 | 14 | 2 | 0 | #N/A
2015-08-31 | Mon 31-Aug | 0 | 0 | 2015-09-04 | Fri 04-Sep | 0 | 0 | 17 | 1 | 18 | 0 | 14 | 2 | 0 | #N/A
2015-09-07 | Mon 07-Sep | -16 | -14 | 2015-09-11 | Fri 11-Sep | 0 | 0 | 17 | 1 | 18 | 0 | 14 | 2 | 0 | #N/A
| Mon 03-Aug | 16 | 14 | 2015-08-07 | Fri 07-Aug | 0 | 0 |  |  |  | 0 |  | 2 | 0
| Mon 10-Aug | 0 | 0 | 2015-08-14 | Fri 14-Aug | 0 | 0 |  |  |  | 0 |  | 2 | 0
| Mon 17-Aug | 0 | 0 | 2015-08-21 | Fri 21-Aug | 0 | 0 |  |  |  | 0 |  | 2 | 0
| Mon 24-Aug | 0 | 0 | 2015-08-28 | Fri 28-Aug | 0 | 0 |  |  |  | 0 |  | 2 | 0
| Mon 31-Aug | 0 | 0 | 2015-09-04 | Fri 04-Sep | 0 | 0 |  |  |  | 0 |  | 2 | 0
| Mon 07-Sep |  |  | 2015-09-11 | Fri 11-Sep | 0 | 0 |  |  |  | 0 |  | 2 | 0
Formulas:
Fridays = [Fridays, row above]+7

## REPORT-GRAPHS
| Expected RE4-2 | Received RE4-2 | Expecting | Under Test | Delivered
| 38 | 17 | 21 | 1 | 16
| Expected RE4-3 | Received | Expecting | Under Test | Delivered
| 38 | 19 | 19 | 5 | 14
| Expected SM | Delivered | To be delivered
| 38 | 14 | 24
RECEIVED | DELIVERED | UNDER TEST | EXPECTING |  | RECEIVED | DELIVERED | UNDER TEST | EXPECTING | DELIVERED | TO BE DELIVERED
17 | 16 | 1 | 21 |  | 19 | 14 | 5 | 19 | 14 | 24

## SM Team
Column1 | Column2 | Column3 | Column4
Week |  | SM Team | QC4 Team
Starting | Ending
2014-02-10 | 2014-02-16 | Vlado-Alexander | Isabel-Nicolas-Francesco
2014-02-17 | 2014-02-23 | Vlado-Alexander | Isabel-Nicolas-Francesco
2014-02-24 | 2014-03-02 | Vlado-Alexander -Iury | Isabel-Nicolas-Francesco
2014-03-03 | 2014-03-09 | Vlado-Alexander-Iury | Isabel-Nicolas
2014-03-10 | 2014-03-16 | Alexander-Iury | Isabel-Severiano
2014-03-17 | 2014-03-23 | Alexander-Iury | Isabel-Nicolas-Severiano
2014-03-24 | 2014-03-30 | Alexander-Iury | Isabel-Nicolas-Severiano
2014-03-31 | 2014-04-06 | Alexander-Iury | Isabel-Nicolas-Severiano
2014-04-07 | 2014-04-13 | Alexander-Iury | Nicolas-Severiano
2014-04-14 | 2014-04-20 | Alexander-Iury | Nicolas-Severiano
2014-04-21 | 2014-04-27 | Alexander-Iury | Nicolas-Severiano
2014-04-28 | 2014-05-04 | Alexander-Iury | Severiano
2014-05-05 | 2014-05-11 | Alexander-Iury | Severiano
2014-05-12 | 2014-05-18 | Alexander-Iury | Nicolas-Severiano
2014-05-19 | 2014-05-25 | Alexander-Iury | Nicolas-Severiano
2014-05-26 | 2014-06-01 | Alexander | Nicolas-Severiano
2014-06-02 | 2014-06-08 | Alexander | Nicolas-Severiano
2014-06-09 | 2014-06-15 | Alexander | Isabel-Nicolas
2014-06-16 | 2014-06-22 | Alexander | Isabel-Nicolas
2014-06-23 | 2014-06-29 | Alexander | Isabel-Nicolas
2014-06-30 | 2014-07-06 | Alexander | Isabel-Nicolas
2014-07-07 | 2014-07-13 | Alexander | Isabel-Nicolas
2014-07-14 | 2014-07-20 | Alexander | Isabel-Nicolas
2014-07-21 | 2014-07-27 | Alexander | Nicolas
2014-07-28 | 2014-08-03 | Alexander | Isabel-Nicolas
2014-08-04 | 2014-08-10 | Alexander | Isabel-Nicolas
Formulas:
Column2 = [Column1]+6
Column1 = [Column2, row above]+1

## Electrical Test RE42
Chamber | Date | Analog | Digital | FEBS | Comments
CMS-RE4-2-CERN-098 | 2014-02-18
CMS-RE4-2-CERN-017 | 2014-04-15
CMS-RE4-2-BARC-155 | 2014-09-23 | 0.361 | 0.81 | OK
CMS-RE4-2-BARC-156 | 2014-09-23 | 0.361 | 0.81 | OK
CMS-RE4-2-BARC-157 | 2014-09-23 | 0.361 | 0.81 | OK
CMS-RE4-2-BARC-158 | 2014-09-23 | 0.361 | 0.81 | OK
CMS-RE4-2-BARC-159 | 2014-09-23 | 0.359 | 0.819 | OK
CMS-RE4-2-BARC-161 | 0
CMS-RE4-2-PANJAB-BARC-162 | 2014-09-23 | 0.357 | 0.805 | check Brd1, VHT4 high 227
CMS-RE4-2-PANJAB-BARC-163 | 2014-09-23 | 0.368 | 0.818 | OK
CMS-RE4-2-PANJAB-BARC-164 | 2014-09-23 | 0.363 | 0.82 | OK

## Electrical Test RE43
Chamber | Date | Analog | Digital | FEBS | Comments
CMS-RE4-3-GENT-108 | 2014-02-13
CMS-RE4-3-GENT-114 | 2014-02-24
CMS-RE4-3-CERN-154 | 2014-04-18
CMS-RE4-3-CERN-160 | 2014-04-18
CMS-RE4-3-CERN-153 | 2014-04-18
CMS-RE4-3-CERN-004 | 2014-04-18

## GAS-CABLES-INFO-RE42
| GAS LINE | CONEXION ORDER | MODE | GAS START | GAS STOP | HV scan CABLE | SLOT | CHANNEL | HV stability CABLE | SLOT | CHANNEL
CMS-RE4-2-CERN-098
CMS-RE4-2-CERN-017 |  | "1/1" - supply : top | OPEN | 2014-09-22 13:30
CMS-RE4-2-BARC-155 | 12 | "2/2" - supply : top | OPEN | 2014-09-22 13:30 |  |  |  |  | pino-2 | 6 | 4-5
CMS-RE4-2-BARC-156 | 8 | "1/2" - supply : top | OPEN | 2014-09-22 13:30 |  |  |  |  | pino-3 | 4 | 4-5
CMS-RE4-2-BARC-157 | 13 | "2/2" - supply : top | OPEN | 2014-09-22 13:30 |  |  |  |  | 26 | 2 | 4-5
CMS-RE4-2-BARC-158 | 8 | "2/2" - supply : top | OPEN | 2014-09-22 13:30 |  |  |  |  | pino-4 | 4 | 2-3
CMS-RE4-2-BARC-159 | can1 | "1/2" - supply : top | OPEN | 2014-09-22 13:30 |  |  |  |  | 6 | 2 | 2-3
CMS-RE4-2-BARC-161
CMS-RE4-2-PANJAB-BARC-162 | 13 | "1/2" - supply : top | OPEN | 2014-09-22 13:30 |  |  |  |  | 25 | 4 | 0-1
CMS-RE4-2-PANJAB-BARC-163 | 12 | "1/2" - supply : top | OPEN | 2014-09-22 13:30 |  |  |  |  | pino-1 | 6 | 2-3
CMS-RE4-2-PANJAB-BARC-164 | can1 | "2/2" - supply : top | OPEN | 2014-09-22 13:30 |  |  |  |  | 2 | 2 | 0-1

## GAS-CABLES-INFO-RE43
| GAS LINE | CONEXION ORDER | MODE | GAS START | GAS STOP | HV scan CABLE | SLOT | CHANNEL | HV stability CABLE | SLOT | CHANNEL | CHANGED TO | CHANGED ON
CMS-RE4-3-GENT-108
CMS-RE4-3-GENT-114
CMS-RE4-3-CERN-154
CMS-RE4-3-CERN-160
CMS-RE4-3-CERN-153 |  |  | OPEN
CMS-RE4-3-CERN-004 |  |  | OPEN

## BackFromPoint5
SM | Chamber ID | QC4 arrival | Status | Coonectivity | commentss | Status | Electric test | AC PS | DC PS | FEBs | Status | Gas CH | Starting | HV scan | Status | Stability start | Stability test time [days] | Stability end | Status

## Sheet1
| cable number | slot | ch-1 | QC4.2-station | length | USED red=yes | gas channel | USED red=yes
line 1 | red001/pino-16 | disconnected | disconnected |  | 12m | FALSE | 1 : attached to the tank
| 39 | 2 | 0 | 4 | 14m | FALSE | 2
| 43 | 10 | 4 | 18 | 14m | FALSE | 3
| 29 | 10 | 2 (top?) | 17 | 15m | FALSE
| 31 | bad cable (Top) | bad cable (Top) |  | 15m | FALSE
| 005red/pino-13 | 2 | 2 | 5 | 14m | FALSE
| 41 | 10 | 0 | 16 | 14m | FALSE
FALSE
lin2 | 14/pino-8 | 12 | 0 | 19 | 22m | FALSE | 5
| 3 | 12 | 4 | 21 | 18m | FALSE | 6
| 4/pino-7 | 12 | 2 | 20 | 18m | FALSE
FALSE
line 3 | 32/pino-10 | 6 | 2 | 11 | 15m | FALSE | 7
| 30/pino-12 | 6 | 4 | 12 | 15m | FALSE | 8
| 33/pino-11 | 8 | 2 | 14 | 15m | FALSE | 9
| 28/pino-9 | 8 | 0 | 13 | 15m | FALSE
FALSE
line 4 | 5white/pino-5 | 14 | 4 | 24 | 18m | FALSE | 10
| white001/pino-6 | 6 | 0 | 10 | 18m | FALSE | 11
[6 empty] | FALSE | (new gas rack 1)
[6 empty] | FALSE | (new gas rack 2)
[6 empty] | FALSE | (new gas rack 3)
FALSE
line 5 | pino-4 | 4 | 2 | 8 |  | FALSE | 12
| pino-3 | 4 | 4 | 9 |  | FALSE | 13
| 6 | 0 | 2 | 2 | 18m | FALSE | 14
| 2 | 14 | 0 | 22 | 18m | FALSE
FALSE
line 6 | 25 | 4 | 0 | 7 | 25m | FALSE | 15
| 26 | 2 | 4 | 6 | 25m | FALSE | 4
| pino-1 | 0 | 4 | 3 |  | FALSE
| pino-2 | 8 | 4 | 15 |  | FALSE
| 13 | 14 | 2 | 23 | 22m | FALSE

## Sheet2
Chamber 1 | 0.401 | 0.855 | 1
Chamber 2 | 0.402 | 0.845 | 2
Chamber 3 | 0.401 | 0.852 | 3
Chamber 4 | 0.394 | 0.848 | 4
Chamber 5 | 0.402 | 0.854 | 5
Chamber 6 | 0.4 | 0.844 | 6
Chamber 7 | 0.405 | 0.858 | 7
Chamber 8 | 0.403 | 0.854 | 8
Chamber 9 | 0.41 | 0.861 | 9
Chamber 10 | 0.394 | 0.845 | 10
Chamber 11 | 0.402 | 0.854 | 11
Chamber 12 | 0.398 | 0.844 | 12
Chamber 13 | 0.403 | 0.853 | 13
Chamber 14 | 0.402 | 0.863 | 14
Chamber 15 | 0.398 | 0.829 | 15