## Slide 1: CMS Cable & Connectorization Workshop
15/03/2023 – Speaker I. Crotty – Project CMS RPC
Contributions Anton and Ian

## Slide 2: CMS RPC Contact Person: A. DIMITROV
Service Type: RPC HV 3-polar CPR connector (CMS cable type 1_HV)
  Technical Specifications available: Yes:1x(2x0.22 + 2x 0.22mm2) H2M1 15kV CC IEC 60332-1
  Procurement Path: CERN/EDH External purchase
  Supplier known: Yes: Novacavi (IT)
  CPR (Fire) and R.I. (Radiation) certification available: No: requires verification with supplier
  Connectorization strategy: At the supplier premises & re-checked at CERN
  Routing path defined: defined, as before but new lengths to be calculated to reduce slack storage
  Cables quantities: 144 pieces, avg. 18m, tot. length 2.6km. Dia.<10mm, red.
  Space request: Storage (m3), Test Area with equipped HV system (30 m2)
  Timeline: Material arrival / Tests at CERN (904) and labels

## Slide 3: CMS RPC Contact Person: A. DIMITROV
Service Type: RPC HV Jupiter connector (CMS cable type 1_HV)
  Technical Specifications available: Yes: Prev 3864L LSZH sheath (see CPE spec sheet)
  Procurement Path: CERN/EDH External purchase
  Supplier known: Yes: CPE (IT)
  CPR (Fire) and R.I. (Radiation) certification available: No: requires verification with supplier
  Connectorization strategy: At the supplier premises & re-checked at CERN
  Routing path defined: defined, as before but new lengths to be calculated to reduce slack storage
  Cables quantities: 288 pieces, avg. 18m, tot. length 5.2km. Dia. 5mm, red.
  Space request: Storage (m3), Test Area with equipped HV system (30 m2)
  Timeline: Material arrival / Tests at CERN (904) and labels

## Slide 4: CMS RPC Contact Person: A. DIMITROV
Service Type: RPC LV Molex / Powerpole connector (CMS cable type 1_LV1)
  Technical Specifications available: Yes: 8 x 0.75mm2 screened FMUH2M4 300V LSOH IEC 60332-3-25
  Procurement Path: CERN/EDH External purchase
  Supplier known: Yes: Novacavi (IT)
  CPR (Fire) and R.I. (Radiation) certification available: No: requires verification with supplier
  Connectorization strategy: Cavitech (CH) or at CERN
  Routing path defined: defined, as before but new lengths to be calculated to reduce slack storage
  Cables quantities: 72 Y-pieces, avg. 18m, tot. length 1.3km. Dia 10mm, Blue.
  Space request: Storage (m3), Test Area with equipped LV system (30 m2)
  Timeline: Material arrival / Tests at CERN (904) and labels

## Slide 5: CMS RPC Contact Person: A. DIMITROV
Service Type: RPC Signal 3M IDC flat cable connector 40c (CMS cable type 1_CA1)
  Technical Specifications available: Yes: TWISTED PAIR ROUND CABLE FE[5x(4*2*AWG28)N]N/SN/ST/M, CERN 04.71.06.400.0 LSZH IEC 60332-1-11
  Procurement Path: CERN/EDH External purchase
  Supplier known: Yes: Tecni Kabel (IT), Plasticavi Italia S.p.A (IT)
  CPR (Fire) and R.I. (Radiation) certification available: No: requires verification with supplier
  Connectorization strategy: Cavitech (CH), quote obtained 2022, re-checked at CERN
  Routing path defined: defined, as before but new lengths to be calculated to reduce slack storage
  Cables quantities: 864 pieces, avg. 11m, tot. length 10km. Dia 10mm, Blue.
  Space request: Storage (40 m3), Test Area for skew test (30 m2)
  Timeline: Material arrival / Cables assembly 2-3 weeks. Skew tests at CERN BEFORE procurement amongst (5) suppliers and retested at CERN

## Slide 6: CMS RPC Contact Person: A. DIMITROV
Service Type: RPC DCS 3M IDC flat cable connector 10c (CMS cable type 1_CA3)
  Technical Specifications available: Yes: Cat. 5 Ethernet ( or better)
  Procurement Path: CERN/EDH External purchase
  Supplier known: No: wide choice ( eg. 04.21.70.104.6 Kerpen mega Line 727 Flex 4P LSFROH 3503789)
  CPR (Fire) and R.I. (Radiation) certification available: No: requires verification with supplier
  Connectorization strategy: Cavitech (CH), quote obtained 2022, re-checked at CERN
  Routing path defined: defined, as before but new lengths to be calculated to reduce slack storage.
  Cables quantities: 144 pieces, avg. 12m, tot. length 1.8km. Dia. 5mm, grey.
  Space request: Storage (m3), Test Area (30 m2)
  Timeline: Material arrival / Cables assembly 2-3 weeks.

## Slide 7: CMS RPC Contact Person: A. DIMITROV
Service Type: RPC Temperature sensor (Pt100) connector 2c (CMS cable type 1_CA4)
  Technical Specifications available: Yes: 2x0.22mm2 Screened,
  Procurement Path: CERN Technikabel 08WH CERN Type MCA2 IEC 60332-1 ZH OR EDH External purchase
  Supplier known: No: wide choice
  CPR (Fire) and R.I. (Radiation) certification available: No: requires verification with supplier
  Connectorization strategy: At CERN & checked at CERN
  Routing path defined: defined, as before but new lengths to be calculated to reduce slack storage.
  Cables quantities: 24 (or 144) pieces, avg. 15m, tot. length 360m (or 2.2km).
  Space request: Storage (m3), Test Area (m2)
  Timeline: Material arrival / Cables assembly

## Slide 8: CMS RPC Contact Person: A. DIMITROV
Service Type: RPC Fibre Optic for Link System Upgrade
  Technical Specifications available: YES: OM4 (or OM3)
  Procurement Path: CERN/EDH External purchase
  Supplier known: No: wide choice
  CPR (Fire) and R.I. (Radiation) certification available: No: requires verification with supplier
  Connectorization strategy: At the supplier premises & re-checked at CERN
  Routing path defined: defined, as before but new lengths to be calculated to reduce slack storage.
  Cables quantities: Barrel: 2x10x144OF, avg.18m+75m, tot. length 1km. Endcap: 2x8x96OF, avg.33m+80m, tot. length 0.9km.
  Space request: Storage (?m3), Test Area (30 m2)
  Timeline: Material arrival: Most urgent is YE1-YE3mCC OF at start of LS3 / Cables assembly

## Slide 9: CMS RPC
Conclusions
Total cable lengths (longest case) 22.4km
Total quantity of cables (optimised case) 1752 pieces
Basic info available on dfs project web site.
Skew test jig has to be rebuilt from scratch
Increase number of temp sensors to one per chamber
Requires up dating to meet CARE and new prices/delay
Do the cables this year so that everybody is on the starting line in 2027 (?) If RPC need assistance now to be sure that there are no last minute mess-ups.

## Slide 10: CMS RPC Contact Person: A. DIMITROV
Summary
Service (cables) PRR: Date (estimated) None
Specific open questions / pending items
Eventual requests for support:
Storage needs: volume~100m³ & timeline: from purchase to installation
Assembly/tests space: surface ~30m² & timeline: before LS3
Manpower Assembly/tests: 3 setups (HV/LV, skew, OTDR), tests in series

## Slide 11: Links to cable types
HV cable
https://project-cms-rpc-endcap.web.cern.ch/rpc/Services/Services2000/Hv/HVcable/H2M115KVCCIEC332-1.doc
https://project-cms-rpc-endcap.web.cern.ch/rpc/Services/Services2000/Hv/RB.HV.pdf
Coaxial cable and connectors
https://www.cpeitalia.it/cpe-italia-catalogs/#
Signal cable
https://project-cms-rpc-endcap.web.cern.ch/rpc/Services/HiLumiPhase3/Cables/Signal/Cable/Novacavi/18R3191%209X2XAWG%2028%20FE2XOH2M-150V.doc.pdf