## Sheet1
CMS RPC Endcap Cable Connectorising
Request for quote
Christian Dechelette tel 74337/160043 (WS Tel; 74771)
· First stage
This action is to cover the initial installation to be done before ‘Offyoke’ ME1/2 & RE1/2 chambers are installed
RE1/1 ONE Endcap
Copper Cables
Type | Calc. Quantity | Quantity | Approx | Number of Pins per Connector | Connector Ref. | Status | Cable Ref. | Status | Remarks | Status | Requested Delivery Date.
Length Range
|  | Nos | [m]
CSC Com. | 6 x 6 | 36 | 15m max | 40 | AMP 1376245-1 | 12 weeks | 04.12.22.740.1 | 1.8km in ISR | USA funds
[5 empty] | 09.55.03.340.4, | 1800328
[5 empty] | 09.55.03.440.1 | 90%del.
LV LBB | 6 x 6 | 36 |  | 4 | undefined |  | 04.08.61.564.5 | 1.9km in ISR
Power
LV LBX Sense | 6 x 6 | 36 |  | 4 | undefined |  | 04.21.70.104.6 | 2km in ISR
HV RPC | 6 x 6 | 36 |  | 3 x 0.22 | CPE | In ISR | Novacavi | In ISR
|  |  |  | [Cable 4x0.22] | 28.002.512_020 |  | P0825_03
Signal Cables | 6 x 6 x 8 | 288 | 6 | x40 AWG 28 | 09.55.03.340.4, |  | 04.71.06.400.0 | Tender in Process | Not Laminated
09.55.03.440.1
LV RPC | 36 | 18 |  | 8 x 0.75 | Molex | In ISR | Novacavi | In ISR | 1 cable for 2 chambers
[5 empty] | 43025 |  | FMOH2M1
Temp Sensor | 36 |  |  | 2 |  |  | 04.21.51.055.4 | 2km in ISR
Optical fibres
Type | Calc. Quantity | Quantity | Approx | Number of Pins per Connector | Connector Ref. | Status | Cable Ref. | Status | Remarks | Status | Requested Delivery Date.
Length Range
|  | Nos | [m]
Trigger | [8 empty] | Warsaw
Spares
DCS | [8 empty] | Warsaw
Spares
TTC | [8 empty] | Warsaw
Spares
RE1/2 ONE Endcap
Copper Cables
Type | Calc. Quantity | Quantity | Approx | Number of Pins per Connector | Connector Ref. | Status | Cable Ref. | Status | Remarks | Status | Requested Delivery Date.
Length Range
|  | Nos | [m]
CSC Com. | 6 x 6 | 36 | 15m max | 40 | AMP 1376245-1 | 12 weeks | 04.12.22.740.1 | 800m in CERN | USA funds
[5 empty] | 09.55.03.340.4, | >400
[5 empty] | 09.55.03.440.1 | >400 in CERN
LV LBB | 6 x 6 | 36 |  | 4 | undefined |  | 04.08.61.564.5 | 2km del 1 week |  |  | 2005-01-05
Power
LV LBX Sense | 6 x 6 | 36 |  | 4 | undefined |  | 04.21.70.104.6 | 2km in ISR
HV RPC | 6 x 6 | 36 |  | 3 x 0.22 | CPE | In ISR | Novacavi | In ISR |  |  | 2005-01-05
|  |  |  | [Cable 4x0.22] | 28.002.512_020 |  | P0825_03
Signal Cables | 6 x 6 x 8 | 288 | 6 | x40 AWG 28 | 09.55.03.340.4, |  | 04.71.06.400.0 | Tender in Process | Not Laminated |  | 2008-01-05
09.55.03.440.1
LV RPC | 36 | 18 |  | 8 x 0.75 | Molex | In ISR | Novacavi | In ISR | 1 cable for 2 chambers |  | 2005-01-05
[5 empty] | 43025 |  | FMOH2M1
Temp Sensor | 36 |  |  | 2 |  |  | 04.21.70.104.6 | 2km in ISR
Optical fibres
Type | Calc. Quantity | Quantity | Approx | Number of Pins per Connector | Connector Ref. | Status | Cable Ref. | Status | Remarks | Status | Requested Delivery Date.
Length Range
|  | Nos | [m]
Trigger | [8 empty] | Warsaw
Spares
DCS | [8 empty] | Warsaw
Spares
TTC | [8 empty] | Warsaw
Spares
RE1/3 ONE Endcap
Copper Cables
Type | Calc. Quantity | Quantity | Approx | Number of Pins per Connector | Connector Ref. | Status | Cable Ref. | Status | Remarks | Status | Requested Delivery Date.
Length Range
|  | Nos | [m]
CSC Com. | 6 x 6 | 36 | 15m max | 40 | AMP 1376245-1 | 12 weeks | 04.12.22.740.1 | 800m in CERN | USA funds
[5 empty] | 09.55.03.340.4, | >400
[5 empty] | 09.55.03.440.1 | >400 in CERN
LV LBB | 6 x 6 | 36 |  | 4 | undefined |  | 04.08.61.564.5 | 2km del 1 week |  |  | 2005-01-05
Power
LV LBX Sense | 6 x 6 | 36 |  | 4 | undefined |  | 04.21.70.104.6 | 2km in ISR
HV RPC | 6 x 6 | 36 |  | 3 x 0.22 | CPE | In ISR | Novacavi | In ISR |  |  | 2005-01-05
|  |  |  | [Cable 4x0.22] | 28.002.512_020 |  | P0825_03
Signal Cables | 6 x 6 x 8 | 288 | 6 | x40 AWG 28 | 09.55.03.340.4, |  | 04.71.06.400.0 | Tender in Process | Not Laminated |  | 2008-01-05
09.55.03.440.1
LV RPC | 36 | 18 |  | 8 x 0.75 | Molex | In ISR | Novacavi | In ISR | 1 cable for 2 chambers |  | 2005-01-05
[5 empty] | 43025 |  | FMOH2M1
Temp Sensor | 36 |  |  | 2 |  |  | 04.21.70.104.6 | 2km in ISR
Optical fibres
Type | Calc. Quantity | Quantity | Approx | Number of Pins per Connector | Connector Ref. | Status | Cable Ref. | Status | Remarks | Status | Requested Delivery Date.
Length Range
|  | Nos | [m]
Trigger | [8 empty] | Warsaw
Spares
DCS | [8 empty] | Warsaw
Spares
TTC | [8 empty] | Warsaw
Spares
Ian Crotty 10.02.05