## Sheet1
Cable Status in UXC55
Both endcaps
RE1/1
Function | Name/Label | EDMS Code | Connector | Status | Cable | Status | Length Definition | Connectorised | Installed
CSc Com. | RE.1/1_CA | CMS-G-RR-0096 | US Spec. | changed | 04.21.51.550.4 | Supplied | yes | done | done
HV RPC | RE.1/1_HV | CMS-G-RR-0101 | CPE 28.002.512-020 | Supplied | Novacavi CA 134 3738 | Supplied | yes | done | done
LV RPC | RE.1/1_LV1 | CMS-G-RR-0102 | Molex 43025 Powerpole | Supplied Not ordered | Novacavi 8R3141 | Supplied | yes | done | done
Signal RPC | RE.1/1_CA1 | CMS-G-RR-0097 | Tender |  | 04.71.06.400.0 |  |  |  | 2007
Temp Sensor | RE1/1_CA4 | CMS-G-RR-0145 | Flat "3M" AD592 | Not ordered | 04.21.51.055.4 | Supplied | yes | done | done
DCS RPC | RE.1/1_CA3 |  | 09.55.03.310.0 09.55.03.410.7 | Supplied | 04.21.70.104.6 | Supplied |  |  | 2007
LV LBB Power | RE.1/1_LV2 | CMS-G-RR-0103 | ? | Not ordered | 04.08.61.564.5 | Supplied | yes |  | done
LV LBB Sense | RE1/1_LV3 | CMS-G-RR-0144 | ? | Not ordered | 04.21.70.104.6 | Supplied | yes |  | done
DCS LBB Ring | RE.1/1_CA2 | CMS-G-RR-0098 | RJ 45 | Not ordered | Ethernet 04.21.70.104.6 | Not ordered |  |  | 2007
LBB TTC | RE.1/1_OF2 | CMS-G-RR-0100 | ST-MM | Supplied | Patch Cord | Supplied | yes | done | done
LBB Trig | RE.1/1_OF | CMS-G-RR-0104 | LC-MM | Supplied | Patch Cord | Supplied | yes | done | done
LBB DCS | RE1/1_OF3 | CMS-G-RR-0143 | MFS | Supplied | Ribbon | Supplied | yes | done | done
RE1/2
Function | Name/Label | EDMS Code | Connector | Status | Cable | Status | Length Definition | Connectorised | Installed
CSc Com. | RE.1_CA | CMS-G-RR-0171 | US Spec. | changed | 04.21.51.550.4 | Supplied | yes, to be checked | yes
HV RPC | RE.1_HV |  | CPE 28.002.512-020 | Supplied | Novacavi CA 134 3738 | Supplied | yes, to be checked
LV RPC | RE.1_LV1 |  | Molex 43025 Powerpole | Supplied Not ordered | Novacavi 8R3141 | Supplied | yes, to be checked
Signal RPC | RE.1_CA1 | CMS-G-RR-0172 | Tender |  | 04.71.06.400.0 | 2+2km - 1.7km | yes, to be checked
Temp Sensor | RE1_CA4 |  | Flat "3M" AD592 |  | 04.21.51.055.4 | Supplied | No
DCS RPC | RE.1_CA3 |  | 09.55.03.310.0 09.55.03.410.7 | Supplied | 04.21.70.104.6 | Supplied | yes, to be checked
LV LBB Power | RE.1_LV2 |  | ? |  | 04.08.61.564.5 | NEW cable Novacavi Order ready | No
LV LBB Sense | RE1_LV3 |  | ? |  | 04.21.70.104.6 |  | No
DCS LBB Ring | RE.1_CA2 | CMS-G-RR-0173 | RJ 45 |  | Ethernet 04.21.70.104.6 |  | No
LBB TTC | RE.1_OF2 |  | ST-MM |  | Patch Cord |  | No
LBB Trig | RE.1_OF |  | LC-MM |  | Patch Cord |  | No
LBB DCS | RE1_OF3 |  | MFS |  | Ribbon |  | No
RE1/3
Function | Name/Label | EDMS Code | Connector | Status | Cable | Status | Length Definition | Connectorised | Installed
CSc Com. | RE.1_CA |  | US Spec. | changed | 04.21.51.550.4 | Supplied | yes, to be checked | yes
HV RPC | RE.1_HV |  | CPE 28.002.512-020 | Ordered | Novacavi CA 134 3738 | Supplied | yes, to be checked
LV RPC | RE.1_LV1 |  | Molex 43025 Powerpole | Supplied Not ordered | Novacavi 8R3141 | Supplied | yes, to be checked
Signal RPC | RE.1_CA1 |  | Tender | Tender | 04.71.06.400.0 | 2+2-1.7-1.2 | yes, to be checked
Temp Sensor | RE1_CA4 |  | Flat "3M" AD592 |  | 04.21.51.055.4 | Supplied | No
DCS RPC | RE.1_CA3 |  | 09.55.03.310.0 09.55.03.410.7 | Supplied | 04.21.70.104.6 | Supplied | yes, to be checked
LV LBB Power | RE.1_LV2 |  | ? |  | 04.08.61.564.5 | NEW cable Novacavi Order ready | No
LV LBB Sense | RE1_LV3 |  | ? |  | 04.21.70.104.6 |  | No
DCS LBB Ring | RE.1_CA2 |  | RJ 45 |  | Ethernet 04.21.70.104.6 |  | No
LBB TTC | RE.1_OF2 |  | ST-MM | Supplied | Patch Cord | Supplied | No
LBB Trig | RE.1_OF |  | LC-MM | Supplied | Patch Cord | Supplied | No
LBB DCS | RE1_OF3 |  | MFS | Supplied | Ribbon | Supplied | No
RE2
Function | Name/Label | EDMS Code | Connector | Status | Cable | Status | Length Definition | Connectorised | Installed
CSc Com. | N/A
HV RPC | RE.2_HV |  | CPE 28.002.512-020 | Ordered | Novacavi CA 134 3738 | Supplied | No
LV RPC | RE.2_LV1 |  | Molex 43025 Powerpole | Supplied Not ordered | Novacavi 8R3141 | Supplied | No
Signal RPC | RE.2_CA1 |  | Tender |  | 04.71.06.400.0 | 2+2-RE1 =1.1 | No | Tender
Temp Sensor | RE2_CA4 |  | Flat "3M" AD592 |  | 04.21.51.055.4 | Supplied | No
DCS RPC | RE.2_CA3 |  | 09.55.03.310.0 09.55.03.410.7 | Supplied | 04.21.70.104.6 | Supplied | No
LV LBB Power | RE.2_LV2 |  | ? |  | 04.08.61.564.5 | NEW cable Novacavi Order ready | No
LV LBB Sense | RE2_LV3 |  | ? |  | 04.21.70.104.6 |  | No
DCS LBB Ring | RE.2_CA2 |  | RJ 45 |  | Ethernet 04.21.70.104.6 |  | No
LBB TTC | RE.2_OF2 |  | ST-MM | Supplied | Patch Cord | Supplied | No
LBB Trig | RE.2_OF |  | LC-MM | Supplied | Patch Cord | Supplied | No
LBB DCS | RE2_OF3 |  | MFS | Supplied | Ribbon | Supplied | No
RE3
Function | Name/Label | EDMS Code | Connector | Status | Cable | Status | Length Definition | Connectorised | Installed
CSc Com. | N/A
HV RPC | RE.3_HV |  | CPE 28.002.512-020 | Ordered | Novacavi CA 134 3738 | Supplied | No
LV RPC | RE.3_LV1 |  | Molex 43025 Powerpole | Supplied Not ordered | Novacavi 8R3141 | Supplied | No
Signal RPC | RE.3_CA1 |  | Tender |  | 04.71.06.400.0 | Tender | No | Tender
Temp Sensor | RE3_CA4 |  | Flat "3M" AD592 |  | 04.21.51.055.4 | Supplied | No
DCS RPC | RE.3_CA3 |  | 09.55.03.310.0 09.55.03.410.7 | Supplied | 04.21.70.104.6 | Supplied | No
LV LBB Power | RE.3_LV2 |  | ? |  | 04.08.61.564.5 | NEW cable Novacavi Order ready | no
LV LBB Sense | RE3_LV3 |  | ? |  | 04.21.70.104.6
DCS LBB Ring | RE.3_CA2 |  | RJ 45 |  | Ethernet 04.21.70.104.6 |  | No
LBB TTC | RE.3_OF2 |  | ST-MM | Supplied | Patch Cord | Supplied | No
LBB Trig | RE.3_OF |  | LC-MM | Supplied | Patch Cord | Supplied | No
LBB DCS | RE3_OF3 |  | MFS | Supplied | Ribbon | Supplied | No
Ian Crotty
2005-07-05