Cables to be installed on detector and towers for RPC trigger.

(for Warsaw part the detailed cable list is  available on http://pccms9.igf.fuw.edu.pl/users/tb/CMS/Cables)

- Trigger fibers   (LBBoxes_sgn_trg_  .xls) -from LBBox to patch panel (tower)

-first batch (about 90 fibers for RE11) already delivered

-awaiting decision on eventual change of cable laying technique*

-persons responsible: Krzysztof Doroba, Ian Crotty/Fabio Montecassiano

- LV cable for LBBox (LBBoxex_ttc_lv_ .xls) from PS to LBBox (tower)

-total length of the cable (encap and barrel) already bought from CERN store (thanks to Ian Crotty).

-connector defined only on LBBox end

-next batch needed: for endcap – late Fall 2005

barrel – Fall 2005

-no cables length defined yet (but RE11)

-persons responsible: Krzysztof Doroba, Ian Crotty/Fabio Montecassiano

- TTCOC fibers (LBBoxex_ttc_lv_ .xls) from TTC box to LBB0x (tower)

-first batch (12 fibers for RE11) already delivered

-awaiting decision on eventual change of cable laying technique*

-persons involved: Krzysztof Doroba, Ian Crotty/Fabio Montecassiano

- dcs cables (LBBox_dcs_ .xls) run between LBBoxes (copper) and one per disc fiber  cable from LBBox to patch panel (tower)

-total length of copper cable (encap and barrel) already bought from CERN store (thanks to Ian Crotty).

-connectors: 2 x RJ45

-next batch needed: for endcap – Fall 2005

barrel – Fall 2005

-no cables length defined yet

-persons responsible: Krzysztof Doroba, Ian Crotty/Fabio Montecassiano

- i2c cables (LBBox_i2c_ .xls) run from FEB to LBBox (detector to tower)

-no cable length defined yet

-person responsible:

- ors cables (LBBoxes_ors_ .xls) run from LBBox to RAT crates (tower)

-no cable length/routing defined yet

-cable for endcaps already purchased

-person responsible:

- RPC signal cables,  run from FEB to LBBox (detector to tower)

- connectorized cables needed June 2005 (RE12)

- person responsible:            /Ian Crotty/Fabio Montecassiano

- High voltage cables for RPC  (detector to tower)

- connectorized cables needed June 2005 (RE12)

- person responsible:

- Low voltage cables for RPC   (detector to tower)

- connectorized cables needed June 2005 (RE12)

  - person responsible:

- Technical trigger fiber cables (from …. to patch panel)  (tower)

General priorities for cabling: detector, detector to tower, tower, tower to counting room.

Detailed list of cables is should be available

PRR approval for cables is seldom

-------------------------------------------------------------------------------------------

* The cost estimate for fiber blowing technique is  CHF 125-150 K  + 30 K

patch cords and multifiber cable            CHF          57 K  + 10 K labor