## RPC RE34-COST ESTIMATE
1/30/2017
Item Number | Item name | KCHF (2014) | Standard Component ID | Unit Defiinition | Unit Cost | Currency of Unit Cost | Unit Basis of Estimate | Unit Cost Quality Flag | Quantity of Units in CMS | Quantity of Units for Production Test Stands | Quantity of Production spares | Quantity of Units | Item Cost | comments on number of unit for test stand
2.4.1 | TOTAL | 2355.6259
BAKELITE
2.4.1.1 | CHAMBER COMPONENTS | 722.0855
2.4.1.1.1 | Bakelite | 105.9355 | see 'RPC Chamber components BoE' tab | Sheets (5 m2) | 1030 | EUR | Riva company quotation 1st of March 2017 | 2 | 72 | 4 | 9 | 85 | 87550 | Two for RE4-1 and RE3-1 for validation of quality control procedure
2.4.1.1.2 | Chamber Mechanics & Strip | 205.7 | see 'RPC Chamber components BoE' tab | Mechanical structure | 2000 | EUR | Extrapolation from the recent RE4 experience (installed in LS1) | 2 | 72 | 4 | 9 | 85 | 170000 | Two for RE4-1 and RE3-1 for validation of quality control procedure
2.4.1.1.3 | Gap Production | 276.25 | see 'RPC Chamber components BoE' tab | Bakelite gap (double gap chamber) | 3250 | CHF | RE4 production done in Korea in 2012 | 2 | 72 | 4 | 9 | 85 | 276250 | Two for RE4-1 and RE3-1 for validation of quality control procedure
2.4.1.1.4 | Chamber Cooling Circuit | 85 | see 'RPC Chamber components BoE' tab | Copper pipes with unions and T joints | 1000 | CHF | Scaled from 2012 from the RE4 production done in India | 2 | 72 | 4 | 9 | 85 | 85000 | Two for RE4-1 and RE3-1 for validation of quality control procedure
2.4.1.1.5 | Chamber Assembly Components | 49.2 | see 'RPC Chamber components BoE' tab | Connectors, Al foils, screws, Adhesive copper tape | 600 | CHF | Extrapolation from the recent RE4 experience (installed in LS1) | 2 | 72 | 1 | 9 | 82 | 49200 | Two for RE4-1 and RE3-1 for validation of quality control procedure
2.4.1.2 | FE ELECTRONICS | 646.7986
2.4.1.2.1 | ASICs | 13.8386 | see 'RPC Electronics BoE' tab | 192x2 = 384 channels per chamber and 4$ per channel | 138 | USD | quotation from TSMC company | 3 | 72 | 4 | 33 | 109 | 15042
2.4.1.2.2 | PCB | 300.84 | see 'RPC Electronics BoE' tab | 1 board per chamber | 3000 | USD | quotation from TSMC company | 3 | 72 | 4 | 33 | 109 | 327000
2.4.1.2.3 | RUN Production | 131.56 | see 'RPC Electronics BoE' tab | In order to produce the ASICs | 143000 | USD | quotation from TSMC company | 3 | 1 | 0 | 0 | 1 | 143000
2.4.1.2.4 | TDC | 100.28 | see 'RPC Electronics BoE' tab |  | 1000 | USD | company quotation | 3 | 72 | 4 | 33 | 109 | 109000
2.4.1.2.5 | FPGA | 100.28 | see 'RPC Electronics BoE' tab |  | 1000 | USD | company quotation | 3 | 72 | 4 | 33 | 109 | 109000
2.4.1.3 | Back End Electronics | 128.1382
2.4.1.3.2 | Concentrator | 84.7 | see 'RPC back-end electronics BoE' tab | Readout for DAQ | 5000 | EUR | approximative cost based on estimated price of fpgas and pcb in fall 016: design phase | 4 | 12 | 1 | 1 | 14 | 70000
2.4.1.3.4 | Micro TCA crates and processing boards | 43.4382 | see 'RPC back-end electronics BoE' tab | Readout for DAQ | 14479.4 | CHF | approximative cost based on estimated price of fpgas and pcb in fall 016 | 2 | 1 | 1 | 1 | 3 | 43438.2
2.4.1.4 | Signal and DAQ Cables | 36.52
2.4.1.4.1 | Signal Cables | 34.1 |  | Flat Cables & connectors | 110 | CHF | Extrapolation from the RE4 | 2 | 288 | 15 | 7 | 310 | 34100 | Two for RE4-1 and RE3-1 for validation of quality control procedure
2.4.1.4.2 | Optical Fibers | 2.42 |  | from DAQ to Trigger | 110 | CHF | Extrapolation from the RE4 | 2 | 20 | 1 | 1 | 22 | 2420 | Two for RE4-1 and RE3-1 for validation of quality control procedure
2.4.1.5 | Power Sytem | 352.7696
| Power system HV | 188.6293 |  | 1 chnannel per chamber
2.4.1.5.1 | HV crates | 16.9521 | see 'RPC Power system BoE' tab | CAEN EASY3000 | 2802 | EUR | CAEN catalogue in the CERN epool, spring 2017 | 1 | 4 | 1 | 0 | 5 | 14010
2.4.1.5.2 | 48V Service Cable | 0.10648 | see 'RPC Power system BoE' tab | 48V 4m | 8 | EUR | CAEN catalogue in the CERN epool, spring 2017 | 1 | 8 | 1 | 2 | 11 | 88
2.4.1.5.3 | Anderson Connectors | 0.242 | see 'RPC Power system BoE' tab | for Service Power | 10 | EUR | CAEN catalogue in the CERN epool, spring 2017 | 1 | 16 | 1 | 3 | 20 | 200
2.4.1.5.4 | HV board | 132.8241 | see 'RPC Power system BoE' tab | CAEN A3512N HV | 8444 | EUR | CAEN catalogue in the CERN epool, spring 2017 | 1 | 12 | 1 | 0 | 13 | 109772
2.4.1.5.5 | HV distribution board | 0.3025 | see 'RPC Power system BoE' tab | Custom made, material aluminium | 50 | EUR | CAEN catalogue in the CERN epool, spring 2017 | 1 | 4 | 1 | 0 | 5 | 250
2.4.1.5.6 | Jupiter connectors male | 3.2489 | see 'RPC Power system BoE' tab |  | 15 | EUR | Company quotation | 1 | 144 | 8 | 27 | 179 | 2685
2.4.1.5.7 | Jupiter connectors female | 3.2489 | see 'RPC Power system BoE' tab |  | 15 | EUR | Company quotation | 1 | 144 | 8 | 27 | 179 | 2685
2.4.1.5.8 | Umbilical cables | 29.9475 | see 'RPC Power system BoE' tab | One cable will be left from GE1/1 slice test, so we need 7 | 2250 | EUR | Company quotation | 1 | 8 | 1 | 2 | 11 | 24750
2.4.1.5.9 | HV CPE connectors male | 2.178 | see 'RPC Power system BoE' tab | 72 connectors for 8 umbilical cables | 20 | EUR | CPE company quotation | 1 | 72 | 4 | 14 | 90 | 1800
2.4.1.5.10 | HV CPE connectors female | 2.178 | see 'RPC Power system BoE' tab | 72 connectors for 8 umbilical cables | 20 | EUR | CPE company quotation | 1 | 72 | 4 | 14 | 90 | 1800
2.4.1.5.11 | HV cables | 12.5235 | see 'RPC Power system BoE' tab | Asumming 25m of cable per connector. Cost 4 EUR per metter | 115 | EUR | Company quotation | 1 | 72 | 4 | 14 | 90 | 10350
2.4.1.5.12 | HV CPE connectors CH-side | 2.178 | see 'RPC Power system BoE' tab | Assuming that the on-detector HV connector is already taken into account in the chamber construction cost | 20 | EUR | Company quotation | 1 | 72 | 4 | 14 | 90 | 1800
| Power System LV - ASIC TDC | 164.1402 |  | 60º per channel (3 chambers)
2.4.1.5.13 | LV board | 75.533 | see 'RPC Power system BoE' tab | CAEN A3016 boards | 6936 | EUR | CAEN catalogue in the CERN epool, spring 2017 | 1 | 8 | 1 | 0 | 9 | 62424
2.4.1.5.14 | LV crates | 16.9521 | see 'RPC Power system BoE' tab | CAEN EASY3000S | 2802 | EUR | CAEN catalogue in the CERN epool, spring 2017 | 1 | 4 | 1 | 0 | 5 | 14010
2.4.1.5.15 | LV branch | 5.3361 | see 'RPC Power system BoE' tab | CAEN A1676A branch controller | 1470 | EUR | CAEN catalogue in the CERN epool, spring 2017 | 1 | 2 | 1 | 0 | 3 | 4410
2.4.1.5.16 | LV power cables | 21.78 | see 'RPC Power system BoE' tab |  | 200 | EUR | Company quotation | 1 | 72 | 4 | 14 | 90 | 18000
2.4.1.5.17 | DCS Control Optical Fiber | 3.267 | see 'RPC Power system BoE' tab |  | 30 | EUR | Company quotation | 1 | 72 | 4 | 14 | 90 | 2700
2.4.1.5.18 | Cable Connectorization | 13.684 | see 'RPC Power system BoE' tab | HV-LV-Signal | 22 | CHF | Extrapolation from the RE4 | 2 | 592 | 30 | 0 | 622 | 13684
2.4.1.5.19 | LV mainframes | 27.588 | see 'RPC Power system BoE' tab | SY1527 | 5700 | EUR | CAEN catalogue in the CERN epool, spring 2017 | 1 | 3 | 1 | 0 | 4 | 22800
2.4.1.6 | Services | 128.314
2.4.1.6.1 | Cooling System | 50 |  | Cost and installation the cooling pipes from the chambers to the patch panel | 50000 | CHF | CERN quotation from DT-PH-CERN group | 2 | 1 | 0 | 0 | 1 | 50000
2.4.1.6.2 | Gas System: Infrastructure on disks | 50 |  | connectors, plastic, flow cells, distribution mainfolds, copper pipes € 200 per 100 m. We need 1000 m per disk. Man Power : 64 CHF per hour per person | 50000 | CHF | CERN quotation from DT-PH-CERN group | 2 | 1 | 0 | 0 | 1 | 50000
2.4.1.6.3 | Temperature Sensor (DCS) | 28.314 |  | One sensors per chamber and installation of the fiber from the chamber to the periferic | 300 | EUR | CERN quotation from DT-PH-CERN group | 2 | 72 | 4 | 2 | 78 | 23400
2.4.1.7 | Chamber Assembly and QC | 190
2.4.1.7.1 | Component for assembling | 35 |  | Tables and tools at 904 | 35000 | CHF | Extrapolation from the recent RE4 experience (installed in LS1) | 2 | 1 |  |  | 1 | 35000
2.4.1.7.2 | Components for Testing | 50 |  | Material needed at 904 test [Electronics Pool, Gas] | 50000 | CHF | Extrapolation from the recent RE4 experience (installed in LS1) | 2 | 1 |  |  | 1 | 50000
2.4.1.7.3 | Testing consumables | 50 |  | Test at the sites | 50000 | CHF | Extrapolation from the recent RE4 experience (installed in LS1) | 2 | 1 |  |  | 1 | 50000
2.4.1.7.4 | Shipment to CERN/COMPANY/Production sites | 55 |  | Bakelite and Gap and chambers | 55000 | CHF | Extrapolation from the recent RE4 experience (installed in LS1) | 2 | 1 |  |  | 1 | 55000
2.4.1.8 | LOGISTIC & INSTALLATION | 151
2.4.1.8.1 | Consumables for Installations | 66 | see 'RPC logistics-installation BoE' tab | Mounting posts, frames to install the RE4-1 table | 66000 | CHF | design phase based on the recent experience with installation of RE4 chambers | 4 | 1 |  |  | 1 | 66000
2.4.1.8.2 | Mechanics for Logistics | 40 | see 'RPC logistics-installation BoE' tab | Troleys and installation AG (dinamic components) | 40000 | CHF | design phase based on the recent experience with installation of RE4 chambers | 4 | 1 |  |  | 1 | 40000
2.4.1.8.3 | Mechanics for Installation | 45 | see 'RPC logistics-installation BoE' tab | Material for mounting (static components) | 45000 | CHF | design phase based on the recent experience with installation of RE4 chambers | 4 | 1 |  |  | 1 | 45000

## Number of Chambers
All RPCs | station | End caps | chamber per station ring | Eta Partitions | total chambers per station
| RE4-1 | 2 | 18 | 1 | 36
| RE3-1 | 2 | 18 | 1 | 36
| TOTAL |  |  |  | 72

## RPC Chamber components BoE
| Item | Per Chamber | Total | Unit Price | Currency | Source
2.4.1.1 | CHAMBER COMPONENTS
2.4.1.1.1 | Bakelite | 1 | 72 | 1030 | EUR | Riva company quotation 1st of March 2017
2.4.1.1.2 | Chamber Mechanics & Strip | 1 | 72 | 2000 | EUR | Extrapolation from the recent RE4 experience (installed in LS1)
2.4.1.1.3 | Gap Production | 1 | 72 | 3250 | CHF | RE4 production done in Korea in 2012
2.4.1.1.4 | Chamber Cooling Circuit | 1 | 72 | 1000 | CHF | Scaled from 2012 from the RE4 production done in India
2.4.1.1.5 | Chamber Assembly Components | 1 | 72 | 600 | CHF | Extrapolation from the recent RE4 experience (installed in LS1)
Equipment | Gaps | Electrodes per chamber | Cost per unit | currency | Cost per chamber | currency
Bakelite | 2 | 4 | 257.5 | EUR | 1030 | EUR
Chamber Mechanics & strips |  | 1 |  | EUR | 2000 | EUR
Gap Production |  |  |  | CHF | 3250 | CHF
Cahmber Cooling Circuit |  |  |  | CHF | 1000 | CHF
Chanber Assembly Components |  |  |  | CHF | 600 | CHF

## RPC back end electronis BoE
| Item | Per Chamber | Total | Unit Price | Currency | Source
2.4.1.3 | Back End Electronics
2.4.1.3.2 | Concentrator | 0.16667 | 12 | 5000 | EUR
2.4.1.3.4 | Micro TCA crates and processing card |  | 1 | 14479.4 | CHF | Magnu's table

## RPC Electronics BoE
| Item | Per Chamber | Total | Unit Price | Currency | Source
2.4.1.2 | ELECTRONICS
2.4.1.2.1 | ASICs [petiroc] | 1 | 72 | 138 | USD | quotation from TSMC company
2.4.1.2.2 | PCB | 1 | 72 | 3000 | USD | quotation from TSMC company
2.4.1.2.2 | RUN Production [petiroc] |  | 1 | 143000 | USD | quotation from TSMC company
2.4.1.2.3 | TDC | 1 | 72 | 1000 | USD | company quotation
2.4.1.2.4 | FPGA | 1 | 72 | 1000 | USD | company quotation
Petiroc Equipment | Strips | pitch [mm] | strip width [mm] | read both ends | Number of chanels
FE Boards | 192 | 4 | 3 | Yes | 384
PCB
Strip Connections to FE |  |  |  |  | 128
| channels | both ends | number of boards | chambers | total number | unit cost | currency | total | production yield applied
ASIC [Petiroc] | 192 | 2 | 6 | 72 | 432 | 3 | USD | 1296 | 2160
Paking of ASICs | 192 | 2 | 6 | 72 | 432 | 20 | USD | 8640 | 14400
TOTAL ASIC | [6 empty] | USD | 9936 | 16560
PCB |  |  |  | 72 | 72 | 3000 | USD | 216000 | 240000
FE Board |  |  |  | 72 | 72 | 1000 | USD | 72000 | 80000
TDC |  |  |  | 72 | 72 | 1000 | USD | 72000 | 80000
336560

## RPC power system BoE
| Item | Per Chamber | Total | Unit Price | Currency | Source
2.4.1.5 | Power Sytem
Power system HV
2.4.1.5.1 | HV crates | 0.055556 | 4 | 2802 | EUR | CAEN catalogue in the CERN epool, spring 2017
2.4.1.5.2 | 48V Service Cable | 0.11111 | 8 | 8 | EUR | CAEN catalogue in the CERN epool, spring 2017
2.4.1.5.3 | Anderson Connectors | 0.22222 | 16 | 10 | EUR | CAEN catalogue in the CERN epool, spring 2017
2.4.1.5.4 | HV board | 0.16667 | 12 | 8444 | EUR | CAEN catalogue in the CERN epool, spring 2017
2.4.1.5.5 | HV distribution board | 0.055556 | 4 | 50 | EUR | CAEN catalogue in the CERN epool, spring 2017
2.4.1.5.6 | Jupiter connectors male | 2 | 144 | 15 | EUR | Company quotation
2.4.1.5.7 | Jupiter connectors female | 2 | 144 | 15 | EUR | Company quotation
2.4.1.5.8 | Umbilical cables | 0.11111 | 8 | 2250 | EUR | Company quotation
2.4.1.5.9 | HV CPE connectors male | 1 | 72 | 20 | EUR | CPE company quotation
2.4.1.5.10 | HV CPE connectors female | 1 | 72 | 20 | EUR | CPE company quotation
2.4.1.5.11 | HV cables | 1 | 72 | 115 | EUR | Company quotation
2.4.1.5.12 | HV CPE connectors CH-side | 1 | 72 | 20 | EUR | Company quotation
Power System LV
2.4.1.5.13 | LV board | 0.11111 | 8 | 6936 | EUR | CAEN catalogue in the CERN epool, spring 2017
2.4.1.5.14 | LV crates | 0.055556 | 4 | 2802 | EUR | CAEN catalogue in the CERN epool, spring 2017
2.4.1.5.15 | LV branch | 0.027778 | 2 | 1470 | EUR | CAEN catalogue in the CERN epool, spring 2017
2.4.1.5.16 | LV power cables | 1 | 72 | 200 | EUR | Company quotation
2.4.1.5.17 | DCS Control Optical Fiber | 1 | 72 | 30 | EUR | Company quotation
2.4.1.5.18 | Cable Connectorization | 576 | 41472 | 22 | CHF | Extrapolation from the RE4
2.4.1.5.19 | LV mainframes | 3 | 216 | 5700 | EUR | CAEN catalogue in the CERN epool, spring 2017
HV
Equipment | Pcs | Meters | Unit Price [Eur] | Total Price [EUR] | Comments
EASY3000 crate | 4 |  | 2802 | 11208
48V Service cable | 8 | 4 | 15 | 60
Anderson Connectors for Service Power | 16 |  | 10 | 160
A3512N HV Board | 12 |  | 8444 | 101328
HVDistribution Board | 4 |  | 50 | 200 | Custom made, material aluminium
Jupiter Connectors male | 144 |  | 15 | 2160
Jupiter Connectors female | 144 |  | 15 | 2160
Umbilical cables | 8 | 900 | 20 | 18000 | One cable will be left from GE1/1 slice test, so we need 7
HV CPE connectors male | 72 |  | 20 | 1440 | 80 connectors for 8 umbilical cables with 15% contingeny
HV CPE connectors female | 72 |  | 20 | 1440 | 80 connectors for 8 umbilical cables with 15% contingency
HV cables | 72 | 2070 | 4 | 8280 | Assuming 20-25m of cable with 15% contingency
HV CPE connectors CH-side | 72 |  | 20 | 1440 | 72 cables with 15% contingency. Assuming that the on-detector HV connector is already taken into account in the chamber construction cost
SY1527 Mainframe | 1 |  | 0 | 0 | Not needed, using existing
A1676A Branch Controller | 1 |  | 0 | 0 | Not needed, using existing ones
A3485S 48V DC Power Supply | 1 |  | 0 | 0 | Not needed, assuming that in EYETS16/17 we will install a second one
YE1 HV Patch Panel | 4 |  | 0 | 0 | Not needed, using existing
HV TOTAL |  |  |  | 147876
Variant IV - LV
Equipment | Pcs | Meters | Unit Price [Eur] | Total Price [EUR] | Comments
CAEN A3016 boards | 8 |  | 6936 | 55488
CAEN EASY3000S crates | 4 |  | 2802 | 11208
CAEN A1676A branch controller | 2 |  | 1470 | 2940
LV power cables | 72 |  | 200 | 14400
DCS control Optical Fibre | 72 |  | 30 | 2160
LV TOTAL |  |  |  | 86196

## RPC Logistics-installation BoE
2.4.1.8 | LOGISTIC & INSTALLATION
2.4.1.8.1 | Consumables for Installations | Mounting posts, frames to install the RE4-1 table
2.4.1.8.2 | Mechanics for Logistics | Troleys and installation AG (dinamic components)
2.4.1.8.3 | Mechanics for Installation | Material for mounting (static components)
| Item | Per Chamber | RE3/1 | RE4/1 | Total | Unit Price | Currency | Source
2.4.1.8.1 | Consumable for installion
Frames to install RE4 table
| Table? |  |  |  |  | 0 | 0
[6 empty] | 0 | 0
| Item | Per Chamber |  |  | Total | Unit Price | Currency | Source
2.4.1.8.2 | Mechanics for logistics
troleys
[6 empty] | 0 | 0
| ? |  |  |  |  | 0 | 0
| Item | Per Chamber |  |  | Total | Unit Price | Currency | Source
2.4.1.8.3 | Mechanics for installations
Mounting arcs
| Brackets? |  |  |  |  | 0 | 0
| ? |  |  |  |  | 0 | 0

## RPC LINK COST ESTIMATE
1/30/2017
Item Number | Item name | KCHF (2014) | Standard Component ID | Unit Defiinition | Unit Cost | Currency of Unit Cost | Unit Basis of Estimate | Unit Cost Quality Flag | Quantity of Units in CMS | Quantity of Units for Production Test Stands | Quantity of Production spares | Quantity of Units | Item Cost
2.4.2 | TOTAL
2.4.2 | Link System for the Current System | 1268.7092
2.4.2.1 | Control Board | 189.728 |  |  | 700 | EUR | Extrapolation from the RE4 | 3 | 216 | 3 | 5 | 224 | 156800
2.4.2.2 | Link Board | 1030.194 |  |  | 600 | EUR | Extrapolation from the RE4 | 3 | 1376 | 14 | 29 | 1419 | 851400
2.4.2.3 | FrontPlane | 48.7872 |  |  | 180 | EUR | Extrapolation from the RE4 | 3 | 216 | 3 | 5 | 224 | 40320
2.4.2.4 | uTCA | 14.52 |  |  | 6000 | EUR | Extrapolation from the RE4 | 2 | 1 | 0 | 0 | 2 | 12000
2.4.2.5 | AMC board | 24.2 |  |  | 10000 | EUR | Extrapolation from the RE4 | 2 | 1 | 0 | 0 | 2 | 20000

## Rates
='COST ESTIMATE TEMPLATE'!A1
Exchange rate vs CHF | Currency | rate
| CHF | 1
| EUR | 1.21 | http://www.x-rates.com/average/?from=EUR&to=CHF&amount=1.00&year=2014
| USD | 0.92 | http://www.x-rates.com/average/?from=USD&to=CHF&amount=1.00&year=2014
| YEN | 0.0087 | http://www.x-rates.com/average/?from=JPY&to=CHF&amount=1.00&year=2014
| Future Currency | 0
| Future Currency | 0
| Future Currency | 0
| Future Currency | 0
| Future Currency | 0
| Future Currency | 0
Production yield (Guideline figures) | item | rate
| PYA | 0.6 | Production yield for a complex analogue packaged FE ASIC
| PYD | 0.9 | Production yield for a digital packaged ASIC
| PYSemod | 0.9 | Production yield for a standard (back end or front end) electronics module
| PYCemod | 0.8 | Production yield for a complex (front end hybrid) electronics module
| PYproject defined1 | 0.95 | Production yield based on recent production and experience
| PYproject defined2 | 0.98 | Production yield based on recent production and experience
| PYproject defined3 | 1 | Production yield based on recent production and experience - RPC Power System
| PYproject defined4 | 0.85 | Production yield based on recent production and experience - RPC Connectors
| PYRPC_bakELITE | 0.9
| PY_Linksystem | 0.98 | Modules Link system
| PY_PCBProduction | 0.9
| PY_RPCElectronics | 0.7 | Production yield from previous production for FE ASIC, done in 2012

## Plots
|  | November cost | Current cost | Technical Proposal | Increment w.r. TP
#REF! | FE ELECTRONICS | 525 | #REF! | 320.22 | #REF!
#REF! | Back End Electronics | 193.81 | #REF!
-2.42 | Signal and DAQ Cables | 38.94 | 36.52 | 408.34 | -4.665%
10.7396 | Power system HV | 342.03 | 188.6293
| Power System LV - ASIC TDC |  | 164.1402
-56.686 | Services | 185 | 128.314 | 150 | -14.46%
-158 | Chamber Assembly and QC | 348 | 190 | 348 | -45.4%
-25 | LOGISTIC & INSTALLATION | 176 | 151 | 176 | -14.2%
| TOTAL w/o Chambers | 1808.78 | #REF! | 1402.56 | #REF!
2.0855 | CHAMBER COMPONENTS Bakelite | 720 | 722.0855 | 900 | -19.77%
112.425 | CHAMBER COMPONENTS GLASS | 912 | 1024.425
#REF! | TOTAL with Bakelite | 2528.78 | #REF! | 2302.56 | #REF!
#REF! | TOTAL with Glass | 2720.78 | #REF! |  | #REF!
Now HV and LV includes the cables
[6 empty] | Project/task | TP Cost | November Cost | Current Cost | November - TP | Current-November | Current - TP | Current Cost 2016
|  | Current cost | November cost | Technical Proposal |  | RPC | 2302.56 | 3797.48 | #REF! | 1494.92 | #REF! | #REF! | 3415.0719
| TOTAL with Bakelite | #REF! | 2528.78 | 2302.56 |  | TOTAL with Bakelite | 2302.56 | 2528.78 | #REF! | 226.22 | #REF! | #REF! | 2272.1851
| CHAMBER COMPONENTS Bakelite | 722.0855 | 720 | 900 |  | Chamber components | 900 | 720 | 722.0855 | -180 | 2.0855 | -177.9145 | 691.1795
| Electronics & DAQ | #REF! | 718.81 | 320.22 |  | Electronics & DAQ | 320.22 | 718.81 | #REF! | 398.59 | #REF! | #REF! | 751.68
| Power Sytem | 389.2896 | 380.97 | 408.34 |  | Power Sytem | 408.34 | 380.97 | 389.2896 | -27.37 | 8.3196 | -19.0504 | 337.8196
| Services | 128.314 | 185 | 150 |  | Services | 150 | 185 | 128.314 | 35 | -56.686 | -21.686 | 125.506
| Chamber Assembly and QC | 190 | 348 | 348 |  | Chamber Assembly and QC | 348 | 348 | 190 | 0 | -158 | -158 | 190
| LOGISTIC & INSTALLATION | 151 | 176 | 176 |  | Logistics and installation | 176 | 176 | 151 | 0 | -25 | -25 | 176
[6 empty] | RPC Link System |  | 1268.7 | 1268.7092 | 1268.7 | 0.0092 | 1268.7092 | 1142.8868
|  | November-TP | Current-TP
| TOTAL with Bakelite | 226.22 | #REF!
| CHAMBER COMPONENTS Bakelite | -180 | -177.9145
| Electronics & DAQ | 398.59 | #REF!
| Power Sytem | -27.37 | -19.0504
| Services | 35 | -21.686
| Chamber Assembly and QC | 0 | -158
| LOGISTIC & INSTALLATION | 0 | -25
|  | Current-TP | November-TP | Current-November
| TOTAL with Bakelite | #REF! | 226.22 | #REF!
| CHAMBER COMPONENTS Bakelite | -177.9145 | -180 | 2.0855
| Electronics & DAQ | #REF! | 398.59 | #REF!
| Power Sytem | -19.0504 | -27.37 | 8.3196
| Services | -21.686 | 35 | -56.686
| Chamber Assembly and QC | -158 | 0 | -158
| LOGISTIC & INSTALLATION | -25 | 0 | -25

## Modules
20170209
| Standard Component ID | Short Description | Unit Cost | Currency of Unit Cost | Unit Basis of Estimate | Unit Cost Quality Flag | Standard Component ID | Documentation (URL)
| AODBRD | ATCA OD Board | 200 | CHF | Engineering estimate | 4 | AODBRD | ATCA off detector FED; cost per front end link receiver; intended for comparison only. It is understood that for many systems the cost estimate will be different. The cost will be compared to this value and the difference should be explained.
| AFEDBRD | ATCA FED | 16993.64 | CHF |  | 4 | AFEDBRD | ATCA example FED with output to DAQ and L1 trigger; 3 FPGAs, 96 input channels, 50% bw to L1 trigger
| MB | Main board | 1600 | EURO | Engineering estimate | 4 |  | Main PCB with mounting and testing
| COMP | Aux components | 1000 | USD | Engineering estimate | 4 |  | Auxiliary components (power, brd control, etc.)
| FPGA | XC-KU115 | 3629 | USD | Engineering estimate | 4 |  | Main FPGA(s), assumes MOQ 300
| DTH | ATCA DAQ interface | 20000 | CHF | Engineering guess | 4 | DTH | At lease one DTH per ATCA shelf, provides 800Gbps link to cDAQ and TCDS function for the crate
| MP7V1 | uTCA Processing card V1 | 14479.4 | CHF | Engineering estimate based on earlier project | 2 | MP7V1 | 72 fiber receiver and 72 fiber transmitter processor board 7 series generation; fully populated with 72 Rx 72 Tx
| MB | Main board | 4500 | EURO | Vendor quote | 2 |  | Main board with power and other supporting circuits, including testing
| FPGA | XC7V690 | 5500 | USD | Vendor quote | 2 |  | Main FPGA
| FC7V2 | uTCA Processing card V2 | 3915 | CHF | Engineering estimate based on earlier project | 2 | FC7V2 | Fully populated with two example FMCs
| MB | Main board | 1500 | EURO | Vendor quote | 2 |  | Main board with power and other supporting circuits, mech
| FPGA | XC7K420 | 1500 | USD | Vendor quote | 2 |  | Main FPGA
| fmc | Mezzanine | 360 | CHF | Engineering estimate | 4 |  | 4 SFP FMC connectivity adapter for e.g. FC7V1
| uODINFR | uTCA Crate etc. | 11000 | CHF | Vendor quote | 2 | uODINFR | Off Detector Infrastructure; 12 slot uTCA crate + AMC13 + MCH + PM + bulk supply
| AODINFR | ATCA Crate etc. | 12000 | CHF | Vendor quote | 2 | AODINFR | Off Detector Infrastructure; ATCA crate + bulk supply

## chip_technology
20170209
| Standard Component ID | Short Description | Unit Cost | Currency of Unit Cost | Unit Basis of Estimate | Unit Cost Quality Flag | Standard Component ID | Documentation (URL)
| S65nm10M | Submission 65nm 10 metal layers | 1017017 | USD | IMEC contract B1379/PH/LHC: 12" wafers, 10 metal layer process, all options engineering run NRE (maskset build) | 1 | S65nm10M | TSMC mask set using 10 metal layers plus six 12" wafers with die size up to 24x32mm.
| S65nm8M | Submission 65nm 8 metal layers | 865000 | USD | IMEC contract B1379/PH/LHC: 12" wafers, 8 metal layer process, all options engineering run NRE (maskset build) | 1 | S65nm8M | TSMC mask set using 8 metal layers plus six 12" wafers with die size up to 24x32mm.
| waf65nm10M | Cost per wafer in lots of 25 wafers | 4107 | USD | IMEC contract B1379/PH/LHC: 12" wafers, 10 metal layer process, all options | 1 | waf65nm10M | TSMC 12" 10 metal layer full maskset wafer, MOQ25
| waf65nm8M | Cost per wafer in lots of 25 wafers | 3700 | USD | IMEC contract B1379/PH/LHC: 12" wafers, 8 metal layer process, all options | 1 | waf65nm8M | TSMC 12" 8 metal layer full maskset wafer, MOQ25
| S65nm10MMLM | Submission 65nm 10 metal layers | 680000 | USD | IMEC contract B1379/PH/LHC: 12" wafers, 10 metal layer process, all options engineering run NRE (maskset build) | 1 | S65nm10MMLM | TSMC MLM (Multi Layer Maskset) plus six 12" wafers for die size up to 12x15mm. Combine with MLM wafer cost.
| S65nm8MMLM | Submission 65nm 8 metal layers | 580000 | USD | IMEC contract B1379/PH/LHC: 12" wafers, 8 metal layer process, all options engineering run NRE (maskset build) | 1 | S65nm8MMLM | TSMC mask set using 8 metal layers plus six 12" wafers with die size up to 12x15mm. Combine with MLM wafer cost.
| waf65nm10MMLM | Cost per wafer in lots of 25 wafers | 7143 | USD | IMEC contract B1379/PH/LHC: 12" wafers, 10 metal layer process, all options | 1 | waf65nm10MMLM | TSMC 12" 10 metal layer MLM wafer, MOQ25
| waf65nm8MMLM | Cost per wafer in lots of 25 wafers | 6411 | USD | IMEC contract B1379/PH/LHC: 12" wafers, 8 metal layer process, all options | 1 | waf65nm8MMLM | TSMC S12" 8 metal layerMLM wafer, MOQ25
| IS130nm8M | Submission 130nm 8 metal layers | 350000 | USD | MOSIS contract B1123/PH: 8" wafers, 8 metal layer process, GF CMOS8RF, engineering run NRE (maskset build) + two 8" wafers | 1 | IS130nm8M | IBM mask set plus two 8" wafers.
| Iwaf130nm8M | Cost per wafer in lots of 25 wafers | 2700 | USD | MOSIS contract B1123/PH: 8" wafers, 8 metal layer process, GF CMOS8RF | 1 | Iwaf130nm8M | IBM production wafer, MOQ 25.
| TS130nm | Submission 130nm | 302000 | USD | IMEC contract B1379/PH/LHC: 8" wafers, 8 metal layer process, common options | 1 | TS130nm | TSMC mask set plus six 8" (or 12") wafers depending on foundry
| Twaf130nm8 | production wafer cost | 1618 | USD | IMEC contract B1379/PH/LHC: 8" wafers, 8 metal layer process, common options | 1 | Twaf130nm8 | TSMC 8" production wafer, MOQ 25.
| Twaf130nm12 | production wafer cost | 1250 | USD | quote from Kostas Kloukinas through CERN PH | 1 | Twaf130nm12 | TSMC 12" production wafer, MOQ 25. Depreciated waiting for further radiation tolerance test results.
| TS130nmMLM | Submission 130nm | 166400 | USD | IMEC contract B1379/PH/LHC: 8" wafers, 8 metal layer process, common options | 1 | TS130nmMLM | TSMC MLM plus six 8" (or 12") wafers depending on foundry; ASIC smaller than 15x12mm. Combine with MLM wafer cost.
| Twaf130nm8MLM | Cost per wafer in lots of 25 wafers | 1975 | USD | IMEC contract B1379/PH/LHC: 8" wafers, 8 metal layer process, common options | 1 | Twaf130nm8MLM | TSMC MLM 8" production wafer, MOQ 25.
| S250nm6 | Submission 250nm | 100000 | USD | MOSIS contract B1123/PH: 8" wafers, 6 metal layer process,engineering run NRE (maskset build) + two 8" wafers | 2 | S250nm6 | IBM 6 metal layer mask set plus two 8" wafers
| S250nm3 | Submission 250nm | 60000 | USD | MOSIS contract B1123/PH: 8" wafers, 3 metal layer process,engineering run NRE (maskset build) + two 8" wafers | 2 | S250nm3 | IBM 3 metal layer mask set plus two 8" wafers
| waf250nm | production wafer cost, MOQ25 | 3000 | USD | IMEC contract B1379/PH/LHC: 8" wafers, 6 metal layer process, common options | 2 | waf250nm | IBM 8" wafer; depending onprocess parameters, MOQ 25

## ASICs
20161216
| Standard Component ID | Short Description | Unit Cost | Currency of Unit Cost | Unit Basis of Estimate | Unit Cost Quality Flag | Standard Component ID | Documentation (URL)
| GBTxHF | 4.8Gb High Feature GBTx | 35 | CHF | quote from CERN PH | 1 | GBTxHF | Chip existing. Price for one packaged and tested chip. Production ends 2017.
| LPGBT | 5.12/10.24Gb Low Power GBT | 34 | CHF | Engineering estimate from CERN PH | 4 | LPGBT | Chip under development. Price for one packaged and tested chip assuming about 50k units total production. Production volumes: 50k 51CHF, 100k 34CHF, 150k 28CHF, 200k 25CHF, 270k 23CHF. Estimate of total production volume is being worked out.
| FEAST | 10W 4A switching regulator | 15 | CHF | Current price from CERN PH | 1 | FEAST | Existing ASIC. Used in the FEAST regulator modules
| upFEAST | 10W 4A switching regulator | 15 | CHF | Engineering estimate from CERN PH | 3 | upFEAST | Chip under development. Radiation tolerance improved compared to the FEAST in order to sustain tracker levels (>700Mrad, 5x10^14 n/cm2). Will be used in future FEAST regulator modules
| DCDC2s | 3W 3A switching regulator | 15 | CHF | Engineering estimate from CERN PH | 3 | DCDC2s | Chip under development. Radiation tolerance to sustain tracker levels (>100Mrad, 4x10^14 n/cm2). Bump bonded to be integrated directly on modules
| DCDCcoil | Inductor for switching regulator | 10 | CHF | Current price from CERN PH | 2 | DCDCcoil | Industrially manufactured air core inductor used for the FEASTMP and FEASTMP_CLP DCDC modules; series of 10k units
CMS lpGBT usage
Inner tracker | 1000
outer tracker | 15000
EB | 12000
HGCAL | 40000
Total | 68000

## Optics
20161111 | 20170209
|  | Standard Component ID | Short Description | Unit Cost | Currency of Unit Cost | Unit Basis of Estimate | Unit Cost Quality Flag | Standard Component ID | Documentation (URL); Note: An updated cost estimate for TRXMM and FIBMM is expected end Q1 2017.
|  | MPODMM | Minipod array + patch | 360 | USD | Vendor quote | 2 | MPODMM | G. Iles and F. Vasey; 12 times 10Gb Rx or 12 times 10Gb Tx, intended for off detector use (no rad or B field)
|  | MPOD25 | Minipod array + patch | 400 | USD | Engineering estimate | 3 | MPOD25 | 12 times 25Gb Rx or 12 times 25Gb Tx, intended for off detector use (no rad or B field)
|  | SFP_10G | 10G SFP | 36 | USD | Vendor quote | 2 | SFP_10G | F. Vasey; this is one receiver and one transmitter up to 10Gb intended for off detector use (no rad or B field)
|  | TRXMM | Laser or PIN, MM | 30 | USD | Vendor quote | 2 | TRXMM | F. Vasey; this is one radiation and magnetic field tolerant receiver or transmitter (detector end) up to 10G for one optical fibre (cost for Tx or Rx identical). If one up fibre connection, as TTC, and two down fibre connections, as TPG and DAQ, three are required.
|  | FIBMM | 100m with radtol patch | 68 | USD | Vendor quote | 2 | FIBMM | F. Vasey; this is one SINGLE fiber including necessary connectors, bundling, etc. The bundle size is 144.
|  | FANOUT48MM | 5m MTP48 to LC | 10 | USD | Based on previous orders | 3 | FANOUT48MM | G. Iles; 48 way optical fan-out, intended for off detector (trigger) use. Cost PER FIBER connection. Typically connecting to a patch panel
|  | PPMM | MM fiber patch panel | 10 | USD | Based on previous orders | 4 | PPMM | G. Iles; Optical fiber patch panel, intended for off detector (trigger) use. Cost PER FIBER connection. Typically one per fiber between processing cards

## Power
20161216 | 20170209
|  | Standard Component ID | Short Description | Unit Cost | Currency of Unit Cost | Unit Basis of Estimate | Unit Cost Quality Flag | Standard Component ID | Documentation (URL)
|  | CPOWER | UXC55 PS per W | 30.0691 | EUR | Vendor price list | 2 | CPOWER | CAEN style front end power system; power per watt before the cable to the detector, loaded to 50% of max capacity assuming full packing fraction
|  | A3100 | Power module | 5676 | EUR | List price |  |  | Single unit price; request quote for system cost
|  | A3486 | AC/DC converter | 12940 | EUR | List price |  |  | Single unit price; request quote for system cost
|  | SY4527 | Mainframe | 7400 | EUR | List price |  |  | Single unit price; request quote for system cost
|  | Easy3000 | Power module carrier | 2799 | EUR | List price |  |  | Single unit price; request quote for system cost
|  | A1676 | Branch controller | 1468 | EUR | List price |  |  | Single unit price; request quote for system cost
|  | WPOWER | UXC55 PS per W | 7.3234 | EUR | Vendor price list | 2 | WPOWER | WIENER style front end power system; power per watt before the cable to the detector, loaded to 50% of max capacity assuming full packing fraction
|  | OM02 | Monitoring and Control unit | 464 | EUR | List price |  |  | Single unit price; request quote for system cost
|  | 0B18 | Power bin | 873 | EUR | List price |  |  | Single unit price; request quote for system cost
|  | 0M01 | 3kW Power supply | 8303 | EUR | List price |  |  | Single unit price; request quote for system cost
|  | OPFC | 3kW rectifier | 1322 | EUR | List price |  |  | Single unit price; request quote for system cost
|  | OB07 | OPFC box | 138.3333 | EUR | List price |  |  | Single unit price; request quote for system cost
|  | DCDC | FE DCDC converter pluggable module | 35 | CHF | CERN PH cost | 2 | DCDC | Radiation and magnetic field tolerant DCDC converter module based on FEAST or upFEAST and DCDCcoil intended for use in front ends. 12V input voltage, 75% efficient. 4A max capacity - design for 3A. Price for total 20k units.
|  | PCABYBE123 | Cable | 2 | CHF | 2*copper price 20140301 | 4 | PCABYBE123 | Power cable pair to supply 1A from Tower to non-YB0 Front End (10m) with 5% loss using DCDC conversion in the FE; based on 2*copper price (CHF7/kg)
|  | PCABYB0 | Cable | 18 | CHF | 2*copper price 20140301 | 4 | PCABYB0 | Power cable pair to supply 1A from Balcony to YB0 Front End (30m) with 5% loss using DCDC conversion in the FE; based on 2*copper price (CHF7/kg)

## COST ESTIMATE TEMPLATE_GLASS
17/1/2017
Item Number | Item name | KCHF (2014) | Standard Component ID | Unit Defiinition | Unit Cost | Currency of Unit Cost | Unit Basis of Estimate | Unit Cost Quality Flag | Quantity of Units in CMS | Quantity of Units for Production Test Stands | Quantity of Production spares | Quantity of Units | Item Cost
2.4.1 | TOTAL | #REF!
2.4.1.1 | CHAMBER COMPONENTS | 1024.425
2.4.1.1.1 | Low glass for double RPC | 702.5018 |  | Price 1.4 m^2. We need 6 pieces for bi-double gap and 4 for double gap, of 1.4 m^2 per chamber | 1820 | EUR | January 2017 |  | 288 | 2 | 29 | 319 | 580580
2.4.1.1.2 | Chamber Mechanics & Strip | 70.0832 |  | Mechanical structure | 724 | EUR | RE4 system |  | 72 | 1 | 7 | 80 | 57920
2.4.1.1.3 | Gap Production | 115.84 |  | Gas box | 1448 | CHF | January 2017 |  | 72 | 1 | 7 | 80 | 115840
2.4.1.1.4 | Chamber Cooling Circuit | 56 |  | Copper pipes with unions and T joints | 700 | CHF | January 2017 |  | 72 | 1 | 7 | 80 | 56000
2.4.1.1.5 | Chamber Assembly Components | 80 |  | Connectors, Al foils, screws, Adhesive copper tape | 1000 | CHF | January 2017 |  | 72 | 1 | 7 | 80 | 80000
2.4.1.2 | FE ELECTRONICS | #REF!
2.4.1.2.1 | ASICs | 13.8386 |  | 192x2 = 384 channels per chamber and 4$ per channel | 138 | USD | quotation from TSMC company |  | 72 | 4 | 33 | 109 | 15042
2.4.1.2.2 | PCB | 300.84 |  | 1 board per chamber | 3000 | USD | quotation from TSMC company |  | 72 | 4 | 33 | 109 | 327000
2.4.1.2.3 | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
2.4.1.3 | Back End Electronics | #REF!
2.4.1.3.1 | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
2.4.1.3.2 | Concentrator | 84.7 |  | Readout for DAQ | 5000 | EUR | approximative cost based on estimated price of fpgas and pcb in fall 016: design phase |  | 12 | 1 | 1 | 14 | 70000
2.4.1.3.3 | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
2.4.1.3.4 | Micro TCA crates and processing boards | 43.4382 |  | Readout for DAQ | 14479.4 | CHF | approximative cost based on estimated price of fpgas and pcb in fall 016 |  | 1 | 1 | 1 | 3 | 43438.2
2.4.1.4 | Signal and DAQ Cables | 36.52
2.4.1.4.1 | Signal Cables | 34.1 |  | Flat Cables & connectors | 110 | CHF | Extrapolation from the RE4 |  | 288 | 15 | 7 | 310 | 34100
2.4.1.4.2 | Optical Fibers | 2.42 |  | from DAQ to Trigger | 110 | CHF | Extrapolation from the RE4 |  | 20 | 1 | 1 | 22 | 2420
2.4.1.5 | Power Sytem | 352.7696
2.4.1.5.1 | Power system HV | 188.6293
2.5.5.1.1 | HV crates | 16.9521 |  | CAEN EASY3000 | 2802 | EUR | CAEN catalogue in the CERN epool, spring 2017 |  | 4 | 1 | 0 | 5 | 14010
2.5.5.1.2 | 48V Service Cable | 0.10648 |  | 48V 4m | 8 | EUR | CAEN catalogue in the CERN epool, spring 2017 |  | 8 | 1 | 2 | 11 | 88
2.5.5.1.3 | Anderson Connectors | 0.242 |  | for Service Power | 10 | EUR | CAEN catalogue in the CERN epool, spring 2017 |  | 16 | 1 | 3 | 20 | 200
2.5.5.1.4 | HV board | 132.8241 |  | CAEN A3512N HV | 8444 | EUR | CAEN catalogue in the CERN epool, spring 2017 |  | 12 | 1 | 0 | 13 | 109772
2.5.5.1.5 | HV distribution board | 0.3025 |  | Custom made, material aluminium | 50 | EUR | CAEN catalogue in the CERN epool, spring 2017 |  | 4 | 1 | 0 | 5 | 250
2.5.5.1.6 | Jupiter connectors male | 3.2489 |  | 0 | 15 | EUR | Company quotation |  | 144 | 8 | 27 | 179 | 2685
2.5.5.1.7 | Jupiter connectors female | 3.2489 |  | 0 | 15 | EUR | Company quotation |  | 144 | 8 | 27 | 179 | 2685
2.5.5.1.8 | Umbilical cables | 29.9475 |  | One cable will be left from GE1/1 slice test, so we need 7 | 2250 | EUR | Company quotation |  | 8 | 1 | 2 | 11 | 24750
2.5.5.1.9 | HV CPE connectors male | 2.178 |  | 72 connectors for 8 umbilical cables | 20 | EUR | CPE company quotation |  | 72 | 4 | 14 | 90 | 1800
2.5.5.1.10 | HV CPE connectors female | 2.178 |  | 72 connectors for 8 umbilical cables | 20 | EUR | CPE company quotation |  | 72 | 4 | 14 | 90 | 1800
2.5.5.1.11 | HV cables | 12.5235 |  | Asumming 25m of cable per connector. Cost 4 EUR per metter | 115 | EUR | Company quotation |  | 72 | 4 | 14 | 90 | 10350
2.5.5.1.12 | HV CPE connectors CH-side | 2.178 |  | Assuming that the on-detector HV connector is already taken into account in the chamber construction cost | 20 | EUR | Company quotation |  | 72 | 4 | 14 | 90 | 1800
2.4.1.5.2 | Power System LV - ASIC TDC | 164.1402 |  | 60º per channel (3 chambers) | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
2.4.1.5.2.1 | LV board | 75.533 |  | CAEN A3016 boards | 6936 | EUR | CAEN catalogue in the CERN epool, spring 2017 |  | 8 | 1 | 0 | 9 | 62424
2.4.1.5.2.2 | LV crates | 16.9521 |  | CAEN EASY3000S | 2802 | EUR | CAEN catalogue in the CERN epool, spring 2017 |  | 4 | 1 | 0 | 5 | 14010
2.4.1.5.2.3 | LV branch | 5.3361 |  | CAEN A1676A branch controller | 1470 | EUR | CAEN catalogue in the CERN epool, spring 2017 |  | 2 | 1 | 0 | 3 | 4410
2.4.1.5.2.4 | LV power cables | 21.78 |  | 0 | 200 | EUR | Company quotation |  | 72 | 4 | 14 | 90 | 18000
2.4.1.5.2.5 | DCS Control Optical Fiber | 3.267 |  | 0 | 30 | EUR | Company quotation |  | 72 | 4 | 14 | 90 | 2700
2.4.1.5.2.6 | Cable Connectorization | 13.684 |  | HV-LV-Signal | 22 | CHF | Extrapolation from the RE4 |  | 592 | 30 | 0 | 622 | 13684
2.4.1.5.2.7 | LV mainframes | 27.588 |  | SY1527 | 5700 | EUR | CAEN catalogue in the CERN epool, spring 2017 |  | 3 | 1 | 0 | 4 | 22800
2.4.1.6 | Services | 128.314 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
2.4.1.6.1 | Cooling System | 50 |  | Cost and installation the cooling pipes from the chambers to the patch panel | 50000 | CHF | CERN quotation from DT-PH-CERN group |  | 1 | 0 | 0 | 1 | 50000
2.4.1.6.2 | Gas System: Infrastructure on disks | 50 |  | connectors, plastic, flow cells, distribution mainfolds, copper pipes € 200 per 100 m. We need 1000 m per disk. Man Power : 64 CHF per hour per person | 50000 | CHF | CERN quotation from DT-PH-CERN group |  | 1 | 0 | 0 | 1 | 50000
2.4.1.6.3 | Temperature Sensor (DCS) | 28.314 |  | One sensors per chamber and installation of the fiber from the chamber to the periferic | 300 | EUR | CERN quotation from DT-PH-CERN group |  | 72 | 4 | 2 | 78 | 23400
2.4.1.7 | Chamber Assembly and QC | 190 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
2.4.1.7.1 | Component for assembling | 35 |  | Tables and tools at 904 | 35000 | CHF | Extrapolation from the recent RE4 experience (installed in LS1) |  | 1 | 0 | 0 | 1 | 35000
2.4.1.7.2 | Components for Testing | 50 |  | Material needed at 904 test [Electronics Pool, Gas] | 50000 | CHF | Extrapolation from the recent RE4 experience (installed in LS1) |  | 1 | 0 | 0 | 1 | 50000
2.4.1.7.3 | Testing consumables | 50 |  | Test at the sites | 50000 | CHF | Extrapolation from the recent RE4 experience (installed in LS1) |  | 1 | 0 | 0 | 1 | 50000
2.4.1.7.4 | Shipment to CERN/COMPANY/Production sites | 55 |  | Bakelite and Gap and chambers | 55000 | CHF | Extrapolation from the recent RE4 experience (installed in LS1) |  | 1 | 0 | 0 | 1 | 55000
2.4.1.8 | LOGISTIC & INSTALLATION | 151 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
2.4.1.8.1 | Consumables for Installations | 66 |  | Mounting posts, frames to install the RE4-1 table | 66000 | CHF | design phase based on the recent experience with installation of RE4 chambers |  | 1 | 0 | 0 | 1 | 66000
2.4.1.8.2 | Mechanics for Logistics | 40 |  | Troleys and installation AG (dinamic components) | 40000 | CHF | design phase based on the recent experience with installation of RE4 chambers |  | 1 | 0 | 0 | 1 | 40000
2.4.1.8.3 | Mechanics for Installation | 45 |  | Material for mounting (static components) | 45000 | CHF | design phase based on the recent experience with installation of RE4 chambers |  | 1 | 0 | 0 | 1 | 45000

## Instructions
Column | Description
A | Item Number in WBS-like format
B | Item Name
C | Item cost and roll-up in KCHF (note: the unit costs must be in currency unit, not kilo unit for the formula to work as-is). Currency USD, CHF, EUR, YEN)
D | Standard Component ID (Tab=chip_technology, ASICs, Optiics, Power, Modules from Magnus's template) where applicable
E | Fill right from D if this is a SC, otherwise enter description or definition of unit
F | Fill right from D if this is a SC, otherwise enter unit cost (2014 exchange rate for time being).
G | Fill right from D if this is a SC, otherwise enter appropriate currency: USD,YEN, CHF or EUR are the currencies considered in the "Rates" tab.
H | Fill right from D if this is a SC, otherwise enter brief text describing or referencing source of information
I | Fill right from D if this is a SC, otherwise enter unit cost quality flag
J | Number of units installed in the detector or system at P5
K | Number of additional units needed for test stands (e.g. at B904). 5% suggested in the formula
L | Set = M-(J+K). This corresponds to the number of spares needed for production and initial commissioning - this should include production wastage that is paid for. This does not include the number of spares needed during the operation (the costs for the spares needed during the operation, which are charged to the MO&B budget.
M | Set = (J+K)/"PYxx" where PYxx is the production yield for xx, where xx can be either standard item (with xx=ASIS/Module/FPGA/etc or project defined item according to recent purchase -see "rates" tab). Put PYxx=1 here if the unit cost (column F) is already adjusted to includes the production yield (extra cost for the waste included in the cost unit).
N | Set = F x M
in TAB = "Rates" , provide the informations about the production yield -PYproject defined - for specific project item.

## New DAQ
Describe the components in the VFE and the concentrators (a scheme can be included)
What FPGA is used (for DT they are using one called IGLOO)
List of components - number per board - cost - to be linked to the table cost
Include the schem with the links and conextions
Item | Description | Number in the board | Estimated cost