## HL and LL (4)
3/24/20173/24/2017
| TASK | LL | HL | Planned End |  | SECTIONS |  | SCOPE DOCUMENT |  | YEAR
LONG | RPC First Review of L1 and readout design done (LM)-Link System | LM |  | 2016-10-26 |  |  |  | Desing and Prototyping |  | 2016
DEV | RPC First Review of L1 and readout design done (LM) | LM |  | 2016-10-26
DEV | RPC Assesment of performance of small prototypes | LM |  | 2017-02-14 | [5 empty] | 2017
SIM | RPC design: definition of performance requirements from simulation (LM) | LM |  | 2017-03-21
DEV | RPC design : Front-end and chamber requirements defined |  | HM | 2017-03-21
DEV | RPC full size prototypes assembly completed (LM) | LM |  | 2017-04-18 |  | Desing
LONG | RPC Preliminary results of longevity studies at HL-LHC luminosity for the TDR (LM) | LM |  | 2017-06-06 |  | and Prototyping
DEV | RPC Power system specs ready (HV) (LM) | LM |  | 2017-06-13
DEV | RPC full size prototypes and FE prototypes tested: preliminary resutls (HM) |  | HM | 2017-06-13
| MUON TDR SUBMISSION |  |  | 2017-06-22 | MUON TDR | SUBMISSION
LONG | RPC Second Review L1 and readout design done (LM) - Link system | LM |  | 2017-12-12
DEV | RPC Second Review L1 and readout design done (LM) | LM |  | 2017-12-12
DEV | RPC Power system specs ready (LV) (LM) | LM |  | 2017-12-12
DEV | RPC protoype FE finalized (HM) |  | HM | 2017-12-12
Prototyping
DEV | RPC FE design finalized (RM) |  | RM | 2018-03-20 | [5 empty] | 2018
DEV | RPC technology choice (RM) |  | RM | 2018-03-20
DEV | RPC FE final engeneering design ready (LM) | LM |  | 2018-04-03
DEV | RPC Chamber Cooling: Preliminary Desing ready (LM) | LM |  | 2018-05-15
DEV | RPC L1 and readout design finalized (HM) |  | HM | 2018-06-05 |  |  |  | MUON TDR
DEV | RPC FE pre-production : Close Market survey (LM) | LM |  | 2018-06-26 |  |  |  | Prototyping
DEV | RPC On-Chamber FE Electronics final engineering prototype ready (HM) |  | HM | 2018-12-18 |  | Engineering and Preproduction
PREPROD | RPC Chamber ready for pre-production (LM) | LM |  | 2019-01-08 | [5 empty] | 2019
DEV | RPC Completion of chamber engineering prototype and integration (HM) |  | HM | 2019-01-08
EDR | RPC EDR (HM) |  | HM | 2019-01-08 | EDR
DEV | RPC Completion of chamber design and integration |  | RM | 2019-04-02
DEV | RPC L1 and readout prototypes validated (HM) |  | HM | 2019-06-05 |  | Preproduction
LONG | RPC Link system finalized (HM) - Link System |  | HM | 2019-06-25
DEV | RPC Power system specs defined and prototypes validated (HM) |  | HM | 2019-11-12
DEV | RPC Power system specs defined and prototypes validated (HM) |  | HM | 2019-11-12
ESR | RPC ESR (HM) |  | HM | 2019-12-09 | ESR | [5 empty] | LS2
PREPROD | RPC Chamber pre-production Chambers and FE completed and validated (HM) |  | HM | 2019-12-24
PROD | RPC Chamber ready for start of production (HM) |  | HM | 2020-01-07 | [5 empty] | 2020
LONG | RPC Link system prototypes validated (HM) - Link System |  | HM | 2020-01-12
LONG | RPC Final assessment of operation procedure and longevity performance at HL-LHC (LM) | LM | LM | 2020-02-18
PREPROD | RPC LV and HV Power System Supply pre-production validated (LM) | LM |  | 2020-02-25
PREPROD | RPC Chamber Pre-production Chambers and FE ready (RM) |  | RM | 2020-04-14 |  |  | Service
PREPROD | RPC L1 and readout pre-production completed and validated (HM) |  | HM | 2020-04-28 |  |  | Installation
PROD | RPC production: On-chamber Electronics (FE) completed and validated (HM) |  | HM | 2020-05-26
PROD | RPC Chambers ready for Start Assembly Endcap 1 (HM) |  | HM | 2020-06-23
PREPROD | RPC L1 and readout pre-production ready (RM) |  | RM | 2020-08-18
PROD | RPC Chambers Ready for Assembly Endcap 1 (RM) |  | RM | 2021-04-15 | [5 empty] | 2021
INSTALL | RPC Detector Ready for Installation Endcap 1 (HM) |  | HM | 2021-06-22 |  |  |  | EDR
PROD | RPC Chamber Production completed and validated (HM) |  | HM | 2021-06-29
PROD | RPC Chamber Production completed and validated (HM) |  | HM | 2021-06-29 |  |  |  | RE3/1 and RE4/1 Production
PROD | RPC Chambers Ready for Assembly Endcap 2 (HM) |  | HM | 2021-06-29 | RE3/1 and RE4/1
INSTALL | RPC Detector Ready for Installation disk 1 (RM) |  | RM | 2021-09-21 | Production
| RPC Installation time window from TC for Endcap 1 (TBF) |  |  | 2021-12-17
PROD | RPC Chambers Ready for Assembly Endcap 2 (RM) |  | RM | 2022-03-22 |  | Instalation |  |  |  | 2022
INSTALL | RPC Detector Ready for Installation Endcap 2 (HM) |  | HM | 2022-06-28 |  | & Commissioning
INSTALL | RPC Detector Ready for Installation disck 2 (RM) |  | RM | 2022-09-27
| RPC Installation time window from TC for Endcap 2 (TBF) |  |  | 2022-12-19
2022
[9 empty] | Test and preparation | 2023
2024
Instalation & Commissioning
[10 empty] | 2025 | LS3
2026
TDR | Technical Detector Review
ESR | Engineering Design Reviews
EDR | Electronics System Reviews
EYETS | Extended Year-end Technical Stop
LM | Low level milestone
HM | High level milestone
EM | External Milestone
RM | Reporting Milestone ~EM

## HL and LL (3)
3/24/20173/24/2017
|  | SECTIONS |  | SCOPE DOCUMENT |  | YEAR
LONG |  |  |  | Desing and Prototyping |  | 2016
DEV
Desing
DEV |  | and Prototyping |  |  |  | 2017
DEV
| MUON TDR | SUBMISSION
LONG
DEV
DEV
Prototyping
DEV | [5 empty] | 2018
DEV
DEV |  |  |  | MUON TDR
DEV |  |  |  | Prototyping
DEV |  | Engineering and Preproduction
PREPROD | [5 empty] | 2019
DEV
EDR | EDR
DEV
DEV |  | Preproduction
ESR | ESR | [5 empty] | LS2
PREPROD
PROD | [5 empty] | 2020
PREPROD |  |  | Service
PREPROD |  |  | Installation
PROD
PROD | [5 empty] | 2021
INSTALL |  |  |  | EDR
PROD | RE3/1 and RE4/1
INSTALL | Production
PROD |  | Instalation |  |  |  | 2022
INSTALL |  | & Commissioning
INSTALL
2023
2024
Test and preparation
2024
Instalation & Commissioning
[6 empty] | 2025 | LS3
2026
TDR
ESR
EDR
EYETS
LM
HM
EM
RM