**Summary iRPC P5 Services**

**HV cable in main cable-chain**

Date: 15th Jan 2019

Ref. Person : Ian Crotty

Order date : no (already available)

Delivery date : no

Job to be done in 904/firm before go to P5: to cut in length and no connectorized (!?)

By whom in 904/firm : ?

Job to be done in P5 : ?

By whom in P5 : ?

Other correlated jobs in P5: Labels from Daniels and log in DB ?

**HV**

Date: 21st March 2019

Ref. Person : Ian Crotty

Order (Jupiter and cables) to CPE date : ?

Delivery date : ?

Job to be done in 904/firm before go to P5: ?

By whom in 904/firm : ?

Job to be done in P5 : ?

By whom in P5 : ?

Other correlated jobs in P5: modify the patch panels, by whom/when ? when do we order the HV modules? Labels from Daniels and log in DB.

**LV cables**

Date: 21st March 2019

Ref. Person : Ian Crotty

Cable Order date : no (already available both cable)

Delivery date : no

Connectors (chamber/module side) order date: ?

Delivery date : ?

Job to be done in 904/firm before go to P5: cut in right length and connectorize

By whom in 904/firm : firm ?

Job to be done in P5 : install in mini-cable-chain

By whom in P5 : ?

Other correlated jobs in P5: communication cable US-UX, by whom/when ?/in Jan 2019. When do we order the LV modules? Labels from Daniels and log in DB.

**Cooling**

Date: 16th March 2019

Ref. Person : Ian Crotty

Order (list of US-4.1 and EU-3.1 material) date : now ?

Delivery date : Jan 2019 ?

Job to be done in 904/firm before go to P5: ?

By whom in 904/firm : ?

Job to be done in P5 :

By whom in P5 :

Other correlated jobs in P5: Labels from Daniels and log in DB.

**Gas pipes**

Date: 6th March 2019

Ref. Person : Alexander Alexandrov

Order (impedence boxes) date : ?

Delivery date : ?

Job to be done in 904/firm before go to P5: ?

By whom in 904/firm : ?

Job to be done in P5 : installation on disk perifery

By whom in P5 : ZEC

Other correlated jobs in P5: pipes provided by ZEC? Rack modification by gas group. Labels from Daniels and log in DB ?

**Optical fibers**

Date: 21st March 2019 (cable 1-2), apr 2020 (cable 3), anytime (cable 4)

Ref. Person : Andres/Ian

Order (cable 1-2) date : ?

Delivery date : ?

Job to be done in 904/firm before go to P5: ?

By whom in 904/firm : ?

Job to be done in P5 : install in disks

By whom in P5 : ?