## Slide 1: Main Cable Chain installation
Ian
16 Jane2016

## Slide 2
Routing done by S. Bally from Integration Office
8 Cables required, one used from GEM slice test

## Slide 3
Main Cable Chain entry and clamping Access. Yes there are available clamps

## Slide 4
Main Cable chains. Open easies installation

## Slide 5
USC
Installation under the racks

## Slide 6
X0, the long path from under the USC to the Main Cable Chains

## Slide 7
Down from the USC to the X0 Galleries (UL) approx. 10m !

## Slide 8
Massive installation of RPC HV cables

## Slide 9
New Cables clamped into position

## Slide 11
Entry into the YE1 Patch Panel. New HV cables

## Slide 12
New HV Cables in the YE1 Patch Panel

## Slide 13
Oops excess length !
10 -15m.

## Slide 14
USC Rack S1H12
Ready for Connectorising

## Slide 15
Installation Team led by Lef.
Thanks to the tough Russian team

## Slide 16: Cable lengths as built !!

## Slide 17: Conclusion
Recovery of stored material. Quality approved by Piji.
Good preparation with IO
Tough job in the Main Cable chains
Job completed in 8 rather than 10 days
Cables cut to length on the spot as no connectors
Connectorising to be done on both ends, a big job.