## GEM
Items and cables from UXC to USC via the YE1 Cable chains
Slice Test
Qty. | Starting point X2V33 | Dimeter | Ending Point | Availabilty | mini CC | Main CC | Rack location | Rack space [U]
| Equipment in rack | [6 empty] | 31
1 | DCS 50P cable for the AC/DC converter and EASY3000 - May be it exsict should confirm with S.Lusin | ~15mm | USC | ? | no | yes (?mm) | X2V33 | 0
1 | 48V service Power cable (exist from the distributor box in the racks) should be confirmed with S.Lusin |  | USC | ? | no | yes (?mm) | X2V33 | 0
1 | 40mm fiber duct - To be installed during YETS 2016 | 40mm | USC S2 Level | no | no | yes (40mm) | X2V33 | 0
1 | HEX ??? |  |  | no | no | no | X2V33 | 1
1 | Radmon - DB9 Type cable | ~6mm | USC S1 | no | no | yes (6mm) | X2V33 | 0
10 | LV cables to GE1/1 PP | ~15mm | GE1/1 PP |  |  |  |  | 0
| TOTAL |  |  |  |  | yes (?+46mm) | X2V33 | 32
X1 YE-1 near side HV PP
2 | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12 mm | USC S1H12 | no | no | yes (2x12mm) | YE-1Near X1 PP | 0
Qty. | LS2 - GE1/1 |  |  | Availabilty | mini CC | Main CC | Rack location | Rack space [U]
Starting point X2V33 (in addition after the slice test)
1 | 40 mm fiber duct | 40mm | USC S2 Level
26 | LV cables to GE1/1 PP | ~15mm | GE1/1 PP
10 | Fiber patch cords | ~15mm | GE1/1 PP
X1 YE-1 Near Side HVpp
8+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC S1H12
| TOTAL X2V33 |  |  | yes | no | yes (86 + ?)mm | X2V33 | 32
X4S33
1 | DCS 50P cable for the AC/DC converter and EASY3000 Crate | ~15mm | USC
1 | 48V service Power cable (exist from the distributor box in the racks) should be confirmed with S.Lusin |  | USC
2 | 40 mm Fiber ducts to USC | 40 mm | USC S2 |  |  | yes (80mm)
36 | LV cables to GE1/1 PP | ~15mm | GE1/1 PP
26 | Fiber patch cords | ~15mm | GE1/1 PP
| TOTAL X4S33 |  |  | yes | no | yes (80 + ?)mm | X4S33 | 24
X1 YE-1 Far side HV PP
10+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC S1H12
X2J33
1 | DCS 50P cable for the AC/DC converter and EASY3000 Crate | ~15mm | USC
1 | 48V service Power cable (exist from the distributor box in the racks) should be confirmed with S.Lusin |  | USC
2 | 40 mm Fiber ducts to USC | 40 mm | USC S2
36 | LV cables to GE1/1 PP | ~15mm | GE1/1 PP
36 | Fiber patch cords | ~15mm | GE1/1 PP
| TOTAL X2J33 |  |  | yes | no | yes (86 + ?)mm | X2V33 | 32
X1 YE+1 Near side HV PP
10+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC S1H13
X4A33
1 | DCS 50P cable for the AC/DC converter and EASY3000 Crate | ~15mm | USC
1 | 48V service Power cable (exist from the distributor box in the racks) should be confirmed with S.Lusin |  | USC
2 | 40 mm Fiber ducts to USC | 40 mm | USC S2
36 | LV cables to GE1/1 PP | ~15mm | GE1/1 PP
36 | Fiber patch cords | ~15mm | GE1/1 PP
| TOTAL X4A33 |  |  | yes | no | yes (80 + ?)mm | X4S33 | 24
X1 YE+1 Far side HV PP
10+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC S1H13
TOTAL
LS2-GE2/1 Services Installation
| Gas Pipes from S2A30 to the GE2/1 detectors |  | GE2/1 PP
12 | Supply | 8mm
12 | Return | 8mm
Pipes for S2S30 to USC - Should be confirmed
2 |  | 22mm | USC Gas room
Cooling
From the Perifery of the YE-1 to GE2/1 detectors
18 | Suppy | 8mm | GE2/1 PP
18 | Return | 8mm | GE2/1 PP
| Gas Pipes from S2S30 to the GE2/1 detectors |  | GE2/1 PP
12 | Supply | 8mm
12 | Return | 8mm
Pipes for S2S30 to USC - Should be confirmed
2 |  | 22mm | USC Gas room
Cooling
From the Perifery of the YE+1 to GE2/1 detectors
18 | Suppy | 8mm | GE2/1 PP
18 | Return | 8mm | GE2/1 PP
HV cables
X1 YE+1 Near side HV PP
20+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC
X1 YE+1 Far side HV PP
20+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC
X1 YE-1 Near side HV PP
20+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC
X1 YE-1 Far side HV PP
20+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC
LV Cables
36 | LV cables to GE2/1 PP from the YE-1 near side perifery? Racks space is not known | ~15mm | GE2/1 PP
36 | LV cables to GE2/1 PP from the YE-1 Far side perifery? Racks space is not known | ~15mm | GE2/1 PP
36 | LV cables to GE2/1 PP from the YE-+ Far side perifery? Racks space is not known | ~15mm | GE2/1 PP
36 | LV cables to GE2/1 PP from the YE-+ Near side perifery? Racks space is not known | ~15mm | GE2/1 PP
| TOTAL X4A33 ? |  |  | yes | no | yes (80 + ?)mm | X4A33 | 32
| TOTAL X4S33 ? |  |  | yes | no | yes (80 + ?)mm | X4S33 | 32
| TOTAL X2J33 |  |  | yes | no | yes (86 + ?)mm | X2J33 | 24
| TOTAL X2V33 |  |  | yes | no | yes (86 + ?)mm | X2V33 | 24
Fibers GE2/1
36 | Fiber patch cords from the periphery of YE-1 Near to the GE2/1 PP | ~15mm | GE2/1 PP
36 | Fiber patch cords from the periphery of YE-1 Far to the GE2/1 PP | ~15mm | GE2/1 PP
36 | Fiber patch cords from the periphery of YE+1 Far to the GE2/1 PP | ~15mm | GE2/1 PP
36 | Fiber patch cords from the periphery of YE+1 Near to the GE2/1 PP | ~15mm | GE2/1 PP
2 | Fibers ducts from YE-1 Near to USC (GE2/1) | 40mm | USC S2
2 | Fibers ducts from YE-1 Far to USC (GE2/1) | 40mm | USC S2
2 | Fibers ducts from YE+ Near to USC (GE2/1) | 40mm | USC S2
2 | Fibers ducts from YE+ Far to USC (GE2/1) | 40mm | USC S2

## CSC
EYETS16/17 | No request
Qty. | Starting point X2V33 | Dimeter | Ending Point | Availabilty | mini CC | Main CC | Rack location | Rack space [U]
LS2
12 | Marathon | [6 empty] | 3
12 | HEX | [6 empty] | 1
| TOTAL X4J41 |  |  | no! | ? | ? | X*J* ? | 4
| TOTAL X2A41 |  |  | no! | ? | ? | X*A* ? | 4
| TOTAL X2J41 |  |  | yes | ? | ? | X2J41 | 4
| TOTAL X4A41 |  |  | yes | ? | ? | X4A41 | 4
| TOTAL X4V41 |  |  | no! | ? | ? | X*V* ? | 4
| TOTAL X2S41 |  |  | no! | ? | ? | X*S* ? | 4
| TOTAL X2V41 |  |  | yes | ? | ? | X2V41 | 4
| TOTAL X4S41 |  |  | yes | ? | ? | X4S41 | 4
| TOTAL X4A51 |  |  | ? | ? | ? | X4A51 | 4
| TOTAL X2J52 |  |  | ? | ? | ? | X2J52 | 4
| TOTAL X4S51 |  |  | ? | ? | ? | X4S51 | 4
| TOTAL X2V52 |  |  | ? | ? | ? | X2V52 | 4
| TOTAL S4F04 |  |  | no! | yes | yes | S4F0* | 10 or 12

## RPC
EYETS16/17 | No request
LS2
Qty. | Component | Dimeter [mm] | Start Point | End Point | Availabilty | mini CC | Main CC | Rack location | Rack space [U] | Comment
HV Services for RE3/1 & RE4/1
72 | Coaxial cables from chambers to HV PP | 6 | Chambers | X1 HV PP | no | yes | no | no | 0 | 18 HV cables per mini CC, 4 x 18 for the entire system
4 | X1 HV PP: Passive element | 0 | X1 HV PP | X1 HV PP | yes | no | no | no | 0
8 | Umbelical cables from USC to UXC | 40 |  | S1H* | no | no | yes | no | 0
4 | EASY3000 crate in USC |  | S1H | S1H | no | no | no | S1H08, S1H09, S1H10, S1H11 | 6 | 4 x 6U in each rack
8 | HV Distribution box |  | S1H | S1H | no | no | no | S1H08, S1H09, S1H10, S1H11 | 6 | 4 x 6U in each rack
12 | A3512N HV boards |  | S1H | S1H | no | no | no | S1H08, S1H09, S1H10, S1H11 | 0 | boards are hosted in EASY3000 crates
1 | A3485S |  | S1H07 | S1H07 | yes | no | no | S1H07 | 3 | should be new, more porewful module
| TOTAL S1H07 |  |  |  | yes | no | no | S1H07 | 3
| TOTAL S1H08 |  |  |  | no | no | no | S1H08 | 12
| TOTAL S1H09 |  |  |  | no | no | no | S1H09 | 12
| TOTAL S1H10 |  |  |  | no | no | no | S1H10 | 12
| TOTAL S1H11 |  |  |  | no | no | no | S1H11 | 12
| TOTAL |  |  |  | no | no | no | S1H* | 51
LV Services for RE3/1 & RE4/1
8 | A3016 LV boards |  | X3 | X3 | no | no | no | X3A51, X3J51, X3V51, X3S51 | 0 | boards are hosted in EASY3000S crates
4 | EASY3000S crates |  | X3 | X3 | no | no | no | X3A51, X3J51, X3V51, X3S51 | 6 | 4 x 6U in each rack
72 | LV power cables | 10 | Chamber | X3 | no | no | no | X3A51, X3J51, X3V51, X3S51 | 0
72 | DCS cables | 5 | Chamber | X3 | no | no | no | X3A51, X3J51, X3V51, X3S51 | 0
2 | A16761 branch controller |  | S4F03 | S4F03 | yes | no | no | S4F03 | 0 | branches in available SY1527 mainframe
2 | Control cables from S4 to YE1 PP |  | S4F03 | YE1 PP | ? | ? | yes ? | no | 0
Option I: | Signal Readout Services for RE3/1 & RE4/1 using standard/present RPC FE electronics
16 | RPC LBB (RPC Link system crates) |  | X3 ¦¦ (X2&X4) |  | no | no | no | X3 ¦¦ (X2 && X4) | 48U Near + 48U Far | 4 x 24U for each side && end (positive near, positive far, negative near, negative far)
1440 | LVDS signal cables | 10 | chmabers | LBB | no | no | no | X3 ¦¦ (X2 && X4) | 0 | 20 signal cables per 20° chamber
240 | Link Boards |  | X3 ¦¦ (X2&X4) |  | no |  |  | X3 ¦¦ (X2 && X4) | 0 | boards are hosted in LBB crates
32 | Control Boards |  | X3 ¦¦ (X2&X4) |  | no | no | no | X3 ¦¦ (X2 && X4) | 0 | boards are hosted in LBB crates
Option II: | Signal Readout Services for RE3/1 & RE4/1 using new R&D electronics
4 | Data Conentrator Card (DCC) |  | X3 ¦¦ X2 ¦¦ X4 |  | no | no | no | X3 ¦¦ X2 ¦¦ X4 | 0 | 4 x 1 DCC per station per end, can be hosted in any rack
72 | Optical fibre links | 40 | chambers | DCC | no | no | no | X3 ¦¦ X2 ¦¦ X4 | 0 | 1 OF link per chamber + spares to be envisaged
| TOTAL X3A5* |  |  |  | no | no | no | X3A5* | 30
| TOTAL X3J5* |  |  |  | no | no | no | X3J5* | 30
| TOTAL X3V5* |  |  |  | no | no | no | X3V5* | 30
| TOTAL X3S5* |  |  |  | no | no | no | X3S5* | 30
| TOTAL |  |  |  | no | no | no |  | 120
LV | power redistribution on X3
Signal | 2 options | signal calblesyst |  |  | Lynk system Rack space |  |  | fibres Data concentration card
DCS
Fibres
Qty. | Starting point X2V33 | Dimeter |  | Ending Point | Availabilty | mini CC | Main CC | Rack location | Rack space [U]