## GEM
Items and cables from UXC to USC via the YE1 Cable chains
Slice Test
Qty. | Starting point X2V33 | Dimeter | Ending Point | Availabilty | mini CC | Main CC | Rack location | Rack space [U]
| Equipment in rack | [6 empty] | 31
1 | DCS 50P cable for the AC/DC converter and EASY3000 - May be it exsict should confirm with S.Lusin | ~15mm | USC | ? | no | yes (?mm) | X2V33 | 0
1 | 48V service Power cable (exist from the distributor box in the racks) should be confirmed with S.Lusin |  | USC | ? | no | yes (?mm) | X2V33 | 0
1 | 40mm fiber duct - To be installed during YETS 2016 | 40mm | USC S2 Level | no | no | yes (40mm) | X2V33 | 0
1 | HEX ??? |  |  | no | no | no | X2V33 | 1
1 | Radmon - DB9 Type cable | ~6mm | USC S1 | no | no | yes (6mm) | X2V33 | 0
10 | LV cables to GE1/1 PP | ~15mm | GE1/1 PP |  |  |  |  | 0
| TOTAL |  |  |  |  | yes (?+46mm) | X2V33 | 32
X1 YE-1 near side HV PP
2 | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12 mm | USC S1H12 | no | no | yes (2x12mm) | YE-1Near X1 PP | 0
Qty. | LS2 - GE1/1 |  |  | Availabilty | mini CC | Main CC | Rack location | Rack space [U]
Starting point X2V33 (in addition after the slice test)
1 | 40 mm fiber duct | 40mm | USC S2 Level | no | no | Yes (40mm)
26 | LV cables to GE1/1 PP | ~15mm | GE1/1 PP | no | no | no | X2V33
10 | Fiber patch cords | ~15mm | GE1/1 PP | no | no | no | X2V33
| TOTAL X2V33 |  |  | yes | no | yes (86 + ?)mm | X2V33 | 32
X1 YE-1 Near Side HVpp
8+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC S1H12 | no | no | yes (160)mm | to S1H12
X4S33
1 | DCS 50P cable for the AC/DC converter and EASY3000 Crate | ~15mm | USC | ? | no | ? | X4S33
1 | 48V service Power cable (exist from the distributor box in the racks) should be confirmed with S.Lusin |  | USC | no | no | no | X4S33
2 | 40 mm Fiber ducts to USC | 40 mm | USC S2 | no | no | yes (80mm) | X4S33
36 | LV cables to GE1/1 PP | ~15mm | GE1/1 PP | no | no | no | X4S33
26 | Fiber patch cords | ~15mm | GE1/1 PP | no | no | no | X4S33
| TOTAL X4S33 |  |  | yes | no | yes (80 + ?)mm | X4S33 | 24
X1 YE-1 Far side HV PP
10+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC S1H12 | no | no | yes (160)mm | to S1H12
X2J33
1 | DCS 50P cable for the AC/DC converter and EASY3000 Crate | ~15mm | USC
1 | 48V service Power cable (exist from the distributor box in the racks) should be confirmed with S.Lusin |  | USC | no | no | no | X4J33
2 | 40 mm Fiber ducts to USC | 40 mm | USC S2 | no | no | yes (80mm) | X4J33
36 | LV cables to GE1/1 PP | ~15mm | GE1/1 PP | no | no | no | X4J33
36 | Fiber patch cords | ~15mm | GE1/1 PP | no | no | no | X4J33
| TOTAL X2J33 |  |  | yes | no | yes (86 + ?)mm | X2J33 | 32
X1 YE+1 Near side HV PP
10+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC S1H12 | no | no | yes (160)mm | to S1H12
X4A33
1 | DCS 50P cable for the AC/DC converter and EASY3000 Crate | ~15mm | USC
1 | 48V service Power cable (exist from the distributor box in the racks) should be confirmed with S.Lusin |  | USC | no | no | no | X4A33
2 | 40 mm Fiber ducts to USC | 40 mm | USC S2 | no | no | yes (80mm) | X4A33
36 | LV cables to GE1/1 PP | ~15mm | GE1/1 PP | no | no | no | X4A33
36 | Fiber patch cords | ~15mm | GE1/1 PP | no | no | no | X4A33
| TOTAL X4A33 |  |  | yes | no | yes (80 + ?)mm | X4A33 | 24
X1 YE+1 Far side HV PP
10+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC S1H12 | no | no | yes (160)mm | to S1H12
TOTAL
GAS Information for - LS2
GE1/1 Gas YE-1 After the the slice test - LS2
X2A31 - YE+1 gas rack for the GE+1/1 (in GCS is rack 79)
| Pipes from UXC to USC |  |  | Yes | no | Yes (exist)
| pipes from the X2A31 to GE1/1 PP (the existing RE1/1 gas pipes) |  |  | yes | no | no
GE1/1 Gas YE-1 After the the slice test - LS2
X2S31 - YE-1 gas rack for the GE-1/1 (in GCS is rack 61)
| Pipes from UXC to USC |  |  | Yes | no | Yes (exist)
| pipes from the X2S31 to GE1/1 PP (the existing RE1/1 gas pipes) |  |  | yes | no | no
LS2-GE2/1 Services Installation
GE2/1 Gas YE+1 - LS2
X2L31 - YE+1 gas rack for the GE+2/1 (in GCS is rack 80)
| Pipes from UXC to USC |  |  | ? | no | Yes (?)
| pipes from the X2L31 to GE2/1 PP |  |  | no | no | no | ?
12 | Supply | 8mm
12 | Return | 8mm
GE2/1 Gas YE-1 - LS2
X2R31 - YE-1 gas rack for the GE-2/1 (in GCS is rack 62)
| Pipes from UXC to USC |  |  | ? | no | Yes (?)
| pipes from the X2R31 to GE2/1 PP |  |  | no | no | no | ?
12 | Supply | 8mm
12 | Return | 8mm
Cooling GE1/1 Slice and LS2 will be connected to the RBX loops
Power of the GE1/1 Super-chamber is ~120W
The power for one GE1/1 disk is 36x120 = 4.32kW
Rack Power per disk
Cooling GE2/1
From the Perifery of the YE+1 to GE2/1 detectors
18 | Suppy | 8mm | GE2/1 PP
18 | Return | 8mm | GE2/1 PP
Power of the GE2/1 Super-chamber is ~240W
The power for one GE2/1 disk is 18x240 = 4.32kW
Rack Power per disk
GE2/1 HV cables
X1 YE+1 Near side HV PP
20+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC
X1 YE+1 Far side HV PP
20+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC
X1 YE-1 Near side HV PP
20+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC
X1 YE-1 Far side HV PP
20+spares | HV Cables 16-18 conductors AWG 26 (0,16 mm) | 12mm | USC
GE2/1 LV Cables
36 | LV cables to GE2/1 PP from the YE-1 near side perifery? Racks space is not known | ~15mm | GE2/1 PP
36 | LV cables to GE2/1 PP from the YE-1 Far side perifery? Racks space is not known | ~15mm | GE2/1 PP
36 | LV cables to GE2/1 PP from the YE-+ Far side perifery? Racks space is not known | ~15mm | GE2/1 PP
36 | LV cables to GE2/1 PP from the YE-+ Near side perifery? Racks space is not known | ~15mm | GE2/1 PP
| TOTAL X4A33 ? (Not sure if there will be enough space in the racks for GE2/1 modules) |  |  | yes | no | yes (80 + ?)mm | X4A33 | 32
| TOTAL X4S33 ? |  |  | yes | no | yes (80 + ?)mm | X4S33 | 32
| TOTAL X2J33 ? |  |  | yes | no | yes (86 + ?)mm | X2J33 | 24
| TOTAL X2V33 ? |  |  | yes | no | yes (86 + ?)mm | X2V33 | 24
Fibers GE2/1
36 | Fiber patch cords from the periphery of YE-1 Near to the GE2/1 PP | ~15mm | GE2/1 PP | no | no | no
36 | Fiber patch cords from the periphery of YE-1 Far to the GE2/1 PP | ~15mm | GE2/1 PP
36 | Fiber patch cords from the periphery of YE+1 Far to the GE2/1 PP | ~15mm | GE2/1 PP
36 | Fiber patch cords from the periphery of YE+1 Near to the GE2/1 PP | ~15mm | GE2/1 PP
36 | Fiber patch cords from the periphery of YE-2 Near CSC ME2/1 TMB | ~10mm | GE2/1 PP | no | yes (360mm)
36 | Fiber patch cords from the periphery of YE-2 Far CSC ME2/1 TMB | ~10mm | GE2/1 PP | no | yes (360mm)
36 | Fiber patch cords from the periphery of YE+2 Far CSC ME2/1 TMB | ~10mm | GE2/1 PP | no | yes (360mm)
36 | Fiber patch cords from the periphery of YE+2 Near CSC ME2/1 TMB | ~10mm | GE2/1 PP | no | yes (360mm)
2 | Fibers ducts from YE-1 Near to USC (GE2/1) | 40mm | USC S2
2 | Fibers ducts from YE-1 Far to USC (GE2/1) | 40mm | USC S2
2 | Fibers ducts from YE+ Near to USC (GE2/1) | 40mm | USC S2
2 | Fibers ducts from YE+ Far to USC (GE2/1) | 40mm | USC S2

## CSC
EYETS16/17 | No request
Qty. | Starting point X2V33 | Dimeter | Ending Point | Availabilty | mini CC | Main CC | Rack location | Rack space [U]
LS2
12 | Marathon | [6 empty] | 3
12 | HEX | [6 empty] | 1
| TOTAL X4J41 |  |  | no! | ? | ? | X*J* ? | 4
| TOTAL X2A41 |  |  | no! | ? | ? | X*A* ? | 4
| TOTAL X2J41 |  |  | yes | ? | ? | X2J41 | 4
| TOTAL X4A41 |  |  | yes | ? | ? | X4A41 | 4
| TOTAL X4V41 |  |  | no! | ? | ? | X*V* ? | 4
| TOTAL X2S41 |  |  | no! | ? | ? | X*S* ? | 4
| TOTAL X2V41 |  |  | yes | ? | ? | X2V41 | 4
| TOTAL X4S41 |  |  | yes | ? | ? | X4S41 | 4
| TOTAL X4A51 |  |  | ? | ? | ? | X4A51 | 4
| TOTAL X2J52 |  |  | ? | ? | ? | X2J52 | 4
| TOTAL X4S51 |  |  | ? | ? | ? | X4S51 | 4
| TOTAL X2V52 |  |  | ? | ? | ? | X2V52 | 4
| TOTAL S4F04 |  |  | no! | yes | yes | S4F0* | 10 or 12
GAS CSC - No New Service Needed
Cooling CSC
Change flow restricters for all ring 1 (ME2/1, ME3/1, ME4/1)
New power - To be corrected by Misha
Rack Power per disk

## RPC
EYETS16/17 | No request
LS2
Qty. | Component | Dimeter [mm] | Start Point | End Point | Availabilty | mini CC | Main CC | Rack location | Rack space [U] | Comment
HV Services for RE3/1 & RE4/1
72 | Coaxial cables from chambers to HV PP | 6 | Chambers | X1 HV PP | no | yes | no | no | 0 | 18 HV cables per mini CC, 4 x 18 for the entire system
4 | X1 HV PP: Passive element | 0 | X1 HV PP | X1 HV PP | yes | no | no | no | 0
8 | Umbelical cables from USC to UXC | 40 |  | S1H* | no | no | yes | no | 0
4 | EASY3000 crate in USC |  | S1H | S1H | no | no | no | S1H08, S1H09, S1H10, S1H11 | 6 | 4 x 6U in each rack
8 | HV Distribution box |  | S1H | S1H | no | no | no | S1H08, S1H09, S1H10, S1H11 | 6 | 4 x 6U in each rack
12 | A3512N HV boards |  | S1H | S1H | no | no | no | S1H08, S1H09, S1H10, S1H11 | 0 | boards are hosted in EASY3000 crates
1 | A3485S |  | S1H07 | S1H07 | yes | no | no | S1H07 | 3 | should be new, more porewful module
| TOTAL S1H07 |  |  |  | yes | no | no | S1H07 | 3
| TOTAL S1H08 |  |  |  | no | no | no | S1H08 | 12
| TOTAL S1H09 |  |  |  | no | no | no | S1H09 | 12
| TOTAL S1H10 |  |  |  | no | no | no | S1H10 | 12
| TOTAL S1H11 |  |  |  | no | no | no | S1H11 | 12
| TOTAL |  |  |  | no | no | no | S1H* | 51
LV Services for RE3/1 & RE4/1
8 | A3016 LV boards |  | X3 | X3 | no | no | no | X3A51, X3J51, X3V51, X3S51 | 0 | boards are hosted in EASY3000S crates
4 | EASY3000S crates |  | X3 | X3 | no | no | no | X3A51, X3J51, X3V51, X3S51 | 6 | 4 x 6U in each rack
72 | LV power cables | 10 | Chamber | X3 | no | no | no | X3A51, X3J51, X3V51, X3S51 | 0
72 | DCS cables | 5 | Chamber | X3 | no | no | no | X3A51, X3J51, X3V51, X3S51 | 0
2 | A16761 branch controller |  | S4F03 | S4F03 | yes | no | no | S4F03 | 0 | branches in available SY1527 mainframe
2 | Control cables from S4 to YE1 PP |  | S4F03 | YE1 PP | ? | ? | yes ? | no | 0
Option I: | Signal Readout Services for RE3/1 & RE4/1 using standard/present RPC FE electronics
16 | RPC LBB (RPC Link system crates) |  | X3 ¦¦ (X2&X4) |  | no | no | no | X3 ¦¦ (X2 && X4) | 48U Near + 48U Far | 4 x 24U for each side && end (positive near, positive far, negative near, negative far)
1440 | LVDS signal cables | 10 | chmabers | LBB | no | no | no | X3 ¦¦ (X2 && X4) | 0 | 20 signal cables per 20° chamber
240 | Link Boards |  | X3 ¦¦ (X2&X4) |  | no |  |  | X3 ¦¦ (X2 && X4) | 0 | boards are hosted in LBB crates
32 | Control Boards |  | X3 ¦¦ (X2&X4) |  | no | no | no | X3 ¦¦ (X2 && X4) | 0 | boards are hosted in LBB crates
Option II: | Signal Readout Services for RE3/1 & RE4/1 using new R&D electronics
4 | Data Conentrator Card (DCC) |  | X3 ¦¦ X2 ¦¦ X4 |  | no | no | no | X3 ¦¦ X2 ¦¦ X4 | 0 | 4 x 1 DCC per station per end, can be hosted in any rack
72 | Optical fibre links | 40 | chambers | DCC | no | no | no | X3 ¦¦ X2 ¦¦ X4 | 0 | 1 OF link per chamber + spares to be envisaged
| TOTAL X3A5* |  |  |  | no | no | no | X3A5* | 30
| TOTAL X3J5* |  |  |  | no | no | no | X3J5* | 30
| TOTAL X3V5* |  |  |  | no | no | no | X3V5* | 30
| TOTAL X3S5* |  |  |  | no | no | no | X3S5* | 30
| TOTAL |  |  |  | no | no | no |  | 120
FEB version
Cooling RPC
| Power per chamber | 28W
| Chamber Power per disk | 503W
| Rack Power per disk | 600W
| Present configuration Power per disc | 1632W
| Original configuation with up scope, Power per disc | 3050W
| Reference Doc 27 May 2016 TCO meet | http://project-cms-rpc-endcap.web.cern.ch/project-cms-rpc-endcap/rpc/UpscopeHighEta/RPCDevelopements/RE31and41/Services/LV/Power/PowerRE27May2016V2.pptx
Gas RPC
RE+(3,4)/1 YEP3
1 - 2 ? | Gas pipes from USC gas room to UXC gas rack | ? | USC gas room | X2A31 | no | no | yes? | no | 0
12 | Supply copper gas pipes from gas rack to chamber RE+(3,4)/1 PP | 6mm | X2A31 | RE+(3,4)/1 PP | no | no | no | no | 0
12 | Return copper gas pipes from ga rack to chamber RE+(3,4)/1 PP | 6mm | X2A31 | RE+(3,4)/1 PP | no | no | no | no | 0
RE-(3,4)/1 YEN3
1 - 2 ? | Gas pipes from USC gas room to UXC gas rack | ? | USC gas room | X2S31 | no | no | yes? | no | 0
12 | Supply copper gas pipes from gas rack to chamber RE-(3,4)/1 PP | 6mm | X2S31 | RE-(3,4)/1 PP | no | no | no | no | 0
12 | Return copper gas pipes from ga rack to chamber RE-(3,4)/1 PP | 6mm | X2S31 | RE-(3,4)/1 PP | no | no | no | no | 0